## Executive Dashboard
PROCUREMENT & PAYMENT CONTROL CENTER
Executive Procurement Visibility ¦ PR → PO → Delivery → Invoice → Payment ¦ Aging & Vendor Exposure
13165000 | 9812903 | 3352097 |  | 26 |  | 16
Total Commitments | Outstanding Balance | Paid to Date |  | Overdue Payment Items |  | High-Priority Items
PROCUREMENT WORKFLOW STATUS
3 | 4 | 8 |  | 6 | 9 |  | 8
PR Raised | PR Approved | PO Issued |  | Delievered | Invoice Received |  | Under Review
PR Raised • PR Approved • PO Issued • Delivered • Invoice Received • Under Review • Approved for Payment • Paid
OVERDUE ITEMS |  |  | MANAGEMENT ATTENTION |  |  | TOP VENDOR EXPOSURE
26 |  |  | Overdue exposure: 3,111,170 SAR High-priority open items: 13 |  |  | Vendor | Outstanding
[6 empty] | Atlas Services | 1221840
[6 empty] | Prime Logistics | 1375997
HIGH PRIORITY | [5 empty] | Gulf Technical | 1628709
16 | [5 empty] | Horizon Supply | 601988
[6 empty] | Vertex Trading | 1624007
|  |  | AGING PROFILE |  |  | Nexa Facilities | 1792757
|  |  | Aging Band | Items |  | Summit Industrial | 886605
|  |  | 0 Days | 34 |  | BlueLine Services | 681000
|  |  | 1-30 Days | 6
|  |  | 31-60 Days | 7
|  |  | 60+ Days | 13 |  | Department | Outstanding
[6 empty] | Operations | 898403
[6 empty] | Administration | 218991
[6 empty] | Logistics | 1332066
[6 empty] | Procurement | 1026822
[6 empty] | Document Control | 1574502
[6 empty] | Finance | 2069950
[6 empty] | Executive Office | 1200738
[6 empty] | Facilities | 1491431
Portfolio note Synthetic / anonymized procurement data. No confidential company or vendor information is included.

## Procurement Register
Ref No. | Department | Vendor | PR No. | PO No. | Description | Commitment (SAR) | Invoice Value (SAR) | Paid (SAR) | Outstanding (SAR) | Status | Priority | PR Date | PO Date | Invoice Date | Due Date | Days Aging | Owner | Management Note
PCR-001 | Facilities | Vertex Trading | PR-2601 | PO-8101 | IT equipment | 91000 | 76932 | 57569 | 33431 | Approved for Payment | Medium | 2026-03-11 | 2026-03-22 | 2026-04-27 | 2026-05-27 | 61 | M. Ali | Escalate overdue item
PCR-002 | Operations | Gulf Technical | PR-2602 | PO-8102 | Professional services | 191000 | 186510 | 186510 | 4490 | Paid | Medium | 2026-06-27 | 2026-07-06 | 2026-07-17 | 2026-08-16 | 0 | S. Ahmed | Routine follow-up
PCR-003 | Executive Office | Prime Logistics | PR-2603 | 77 | Transport services | 356000 | 0 | 0 | 356000 | PR Raised | High | 2026-03-04 |  |  |  | 0 | A. Khan | Routine follow-up
PCR-004 | Executive Office | BlueLine Services | PR-2604 | 77 | Technical materials | 87000 | 0 | 0 | 87000 | PR Approved | Medium | 2026-02-24 |  |  |  | 0 | F. Malik | Routine follow-up
PCR-005 | Logistics | Atlas Services | PR-2605 | PO-8105 | IT equipment | 60000 | 51007 | 0 | 60000 | Under Review | Medium | 2026-03-27 | 2026-04-14 | 2026-05-21 | 2026-06-20 | 37 | R. Hassan | Escalate overdue item
PCR-006 | Operations | Prime Logistics | PR-2606 | PO-8106 | Manpower services | 357000 | 291094 | 291094 | 65906 | Paid | Low | 2026-04-11 | 2026-04-26 | 2026-05-22 | 2026-06-21 | 36 | S. Ahmed | Escalate overdue item
PCR-007 | Procurement | Nexa Facilities | PR-2607 | PO-8107 | Equipment rental | 409000 | 0 | 0 | 409000 | Delivered | Medium | 2026-03-06 | 2026-03-14 |  |  | 0 | R. Hassan | Routine follow-up
PCR-008 | Executive Office | Atlas Services | PR-2608 | PO-8108 | Transport services | 236000 | 179565 | 0 | 236000 | Invoice Received | High | 2026-05-21 | 2026-05-27 | 2026-07-08 | 2026-08-07 | 0 | M. Ali | Routine follow-up
PCR-009 | Administration | Vertex Trading | PR-2609 | 77 | Equipment rental | 194000 | 0 | 0 | 194000 | PR Raised | High | 2026-02-08 |  |  |  | 0 | F. Malik | Routine follow-up
PCR-010 | Facilities | Nexa Facilities | PR-2610 | PO-8110 | Office supplies | 261000 | 0 | 0 | 261000 | PO Issued | High | 2026-03-11 | 2026-03-21 |  |  | 0 | R. Hassan | Routine follow-up
PCR-011 | Finance | Gulf Technical | PR-2611 | PO-8111 | Technical materials | 328000 | 0 | 0 | 328000 | PO Issued | Medium | 2026-07-11 | 2026-07-22 |  |  | 0 | M. Ali | Routine follow-up
PCR-012 | Procurement | Atlas Services | PR-2612 | PO-8112 | Technical materials | 77000 | 76688 | 0 | 77000 | Invoice Received | High | 2026-02-23 | 2026-03-02 | 2026-03-10 | 2026-04-09 | 109 | S. Ahmed | Escalate overdue item
PCR-013 | Administration | Horizon Supply | PR-2613 | PO-8113 | Site consumables | 268000 | 243009 | 243009 | 24991 | Paid | Medium | 2026-05-06 | 2026-05-23 | 2026-06-09 | 2026-07-09 | 18 | S. Ahmed | Routine follow-up
PCR-014 | Operations | Vertex Trading | PR-2614 | PO-8114 | Maintenance works | 345000 | 0 | 0 | 345000 | Delivered | Low | 2026-03-21 | 2026-03-30 |  |  | 0 | F. Malik | Routine follow-up
PCR-015 | Document Control | Atlas Services | PR-2615 | PO-8115 | Accommodation services | 85000 | 75607 | 28951 | 56049 | Approved for Payment | Medium | 2026-06-07 | 2026-06-17 | 2026-07-06 | 2026-08-05 | 0 | R. Hassan | Routine follow-up
PCR-016 | Operations | Vertex Trading | PR-2616 | PO-8116 | Professional services | 319000 | 246656 | 246656 | 72344 | Paid | Medium | 2026-03-31 | 2026-04-09 | 2026-05-23 | 2026-06-22 | 35 | S. Ahmed | Escalate overdue item
PCR-017 | Finance | Summit Industrial | PR-2617 | PO-8117 | Accommodation services | 381000 | 300554 | 0 | 381000 | Under Review | High | 2026-07-05 | 2026-07-09 | 2026-07-20 | 2026-08-19 | 0 | F. Malik | Routine follow-up
PCR-018 | Procurement | Summit Industrial | PR-2618 | PO-8118 | Transport services | 114000 | 94395 | 94395 | 19605 | Paid | Medium | 2026-02-24 | 2026-03-14 | 2026-03-28 | 2026-04-27 | 91 | F. Malik | Escalate overdue item
PCR-019 | Executive Office | Horizon Supply | PR-2619 | 77 | Office supplies | 60000 | 0 | 0 | 60000 | PR Approved | Medium | 2026-04-18 |  |  |  | 0 | A. Khan | Routine follow-up
PCR-020 | Document Control | Vertex Trading | PR-2620 | PO-8120 | Site consumables | 355000 | 322795 | 151071 | 203929 | Approved for Payment | Medium | 2026-05-28 | 2026-05-31 | 2026-06-20 | 2026-07-20 | 7 | F. Malik | Routine follow-up
PCR-021 | Facilities | BlueLine Services | PR-2621 | PO-8121 | Technical materials | 192000 | 0 | 0 | 192000 | PO Issued | Medium | 2026-03-18 | 2026-03-28 |  |  | 0 | A. Khan | Routine follow-up
PCR-022 | Procurement | Atlas Services | PR-2622 | PO-8122 | Office supplies | 121000 | 111576 | 111576 | 9424 | Paid | Medium | 2026-04-28 | 2026-05-08 | 2026-06-17 | 2026-07-17 | 10 | F. Malik | Routine follow-up
PCR-023 | Finance | Gulf Technical | PR-2623 | PO-8123 | Equipment rental | 274000 | 263237 | 0 | 274000 | Invoice Received | Medium | 2026-05-10 | 2026-05-27 | 2026-07-02 | 2026-08-01 | 0 | M. Ali | Routine follow-up
PCR-024 | Executive Office | Summit Industrial | PR-2624 | PO-8124 | Equipment rental | 44000 | 43696 | 0 | 44000 | Invoice Received | Medium | 2026-02-21 | 2026-03-05 | 2026-04-03 | 2026-05-03 | 85 | S. Ahmed | Escalate overdue item
PCR-025 | Facilities | Nexa Facilities | PR-2625 | PO-8125 | Site consumables | 262000 | 211281 | 0 | 262000 | Under Review | High | 2026-02-23 | 2026-03-02 | 2026-03-25 | 2026-04-24 | 94 | A. Khan | Escalate overdue item
PCR-026 | Executive Office | Nexa Facilities | PR-2626 | PO-8126 | IT equipment | 324000 | 0 | 0 | 324000 | PO Issued | Low | 2026-05-01 | 2026-05-16 |  |  | 0 | S. Ahmed | Routine follow-up
PCR-027 | Logistics | Gulf Technical | PR-2627 | PO-8127 | Accommodation services | 355000 | 0 | 0 | 355000 | PO Issued | High | 2026-02-07 | 2026-02-22 |  |  | 0 | R. Hassan | Routine follow-up
PCR-028 | Document Control | Nexa Facilities | PR-2628 | PO-8128 | Maintenance works | 214000 | 210784 | 0 | 214000 | Invoice Received | Medium | 2026-05-27 | 2026-06-04 | 2026-06-24 | 2026-07-24 | 3 | A. Khan | Routine follow-up
PCR-029 | Document Control | Atlas Services | PR-2629 | PO-8129 | Maintenance works | 397000 | 379249 | 379249 | 17751 | Paid | Medium | 2026-04-12 | 2026-04-24 | 2026-05-09 | 2026-06-08 | 49 | M. Ali | Escalate overdue item
PCR-030 | Operations | Vertex Trading | PR-2630 | 77 | Transport services | 118000 | 0 | 0 | 118000 | PR Raised | Low | 2026-06-01 |  |  |  | 0 | S. Ahmed | Routine follow-up
PCR-031 | Procurement | Gulf Technical | PR-2631 | PO-8131 | Professional services | 29000 | 26149 | 26149 | 2851 | Paid | Medium | 2026-06-16 | 2026-06-30 | 2026-08-07 | 2026-09-06 | 0 | M. Ali | Routine follow-up
PCR-032 | Facilities | Prime Logistics | PR-2632 | PO-8132 | Technical materials | 219000 | 191914 | 0 | 219000 | Under Review | Medium | 2026-01-31 | 2026-02-12 | 2026-03-20 | 2026-04-19 | 99 | R. Hassan | Escalate overdue item
PCR-033 | Executive Office | Atlas Services | PR-2633 | PO-8133 | Accommodation services | 97000 | 84669 | 57384 | 39616 | Approved for Payment | High | 2026-06-16 | 2026-07-02 | 2026-08-13 | 2026-09-12 | 0 | F. Malik | Routine follow-up
PCR-034 | Finance | Prime Logistics | PR-2634 | PO-8134 | Equipment rental | 49000 | 39588 | 39588 | 9412 | Paid | High | 2026-03-26 | 2026-03-31 | 2026-04-10 | 2026-05-10 | 78 | M. Ali | Escalate overdue item
PCR-035 | Operations | Prime Logistics | PR-2635 | PO-8135 | Site consumables | 389000 | 385160 | 240094 | 148906 | Approved for Payment | Medium | 2026-07-05 | 2026-07-15 | 2026-08-28 | 2026-09-27 | 0 | M. Ali | Routine follow-up
PCR-036 | Facilities | Nexa Facilities | PR-2636 | PO-8136 | Technical materials | 179000 | 170054 | 0 | 179000 | Invoice Received | Medium | 2026-04-03 | 2026-04-08 | 2026-05-23 | 2026-06-22 | 35 | A. Khan | Escalate overdue item
PCR-037 | Finance | Gulf Technical | PR-2637 | PO-8137 | Equipment rental | 325000 | 0 | 0 | 325000 | Delivered | Low | 2026-06-08 | 2026-06-19 |  |  | 0 | M. Ali | Routine follow-up
PCR-038 | Procurement | Prime Logistics | PR-2638 | PO-8138 | Technical materials | 225000 | 211348 | 0 | 225000 | Invoice Received | Medium | 2026-04-17 | 2026-05-02 | 2026-06-09 | 2026-07-09 | 18 | M. Ali | Routine follow-up
PCR-039 | Finance | Prime Logistics | PR-2639 | PO-8139 | Professional services | 331000 | 0 | 0 | 331000 | PO Issued | Medium | 2026-02-18 | 2026-02-25 |  |  | 0 | R. Hassan | Routine follow-up
PCR-040 | Document Control | Vertex Trading | PR-2640 | PO-8140 | Office supplies | 79000 | 0 | 0 | 79000 | Delivered | Low | 2026-02-12 | 2026-03-02 |  |  | 0 | S. Ahmed | Routine follow-up
PCR-041 | Logistics | Vertex Trading | PR-2641 | PO-8141 | Manpower services | 199000 | 0 | 0 | 199000 | Delivered | Medium | 2026-04-19 | 2026-05-06 |  |  | 0 | M. Ali | Routine follow-up
PCR-042 | Executive Office | Horizon Supply | PR-2642 | PO-8142 | Technical materials | 333000 | 278878 | 278878 | 54122 | Paid | Medium | 2026-06-06 | 2026-06-18 | 2026-07-16 | 2026-08-15 | 0 | R. Hassan | Routine follow-up
PCR-043 | Operations | Nexa Facilities | PR-2643 | PO-8143 | Maintenance works | 361000 | 318175 | 217243 | 143757 | Approved for Payment | High | 2026-06-01 | 2026-06-19 | 2026-07-01 | 2026-07-31 | 0 | M. Ali | Routine follow-up
PCR-044 | Facilities | Horizon Supply | PR-2644 | PO-8144 | Maintenance works | 137000 | 0 | 0 | 137000 | PO Issued | Low | 2026-05-25 | 2026-06-03 |  |  | 0 | A. Khan | Routine follow-up
PCR-045 | Procurement | Gulf Technical | PR-2645 | PO-8145 | Site consumables | 252000 | 197344 | 0 | 252000 | Invoice Received | Low | 2026-03-11 | 2026-03-26 | 2026-04-30 | 2026-05-30 | 58 | R. Hassan | Escalate overdue item
PCR-046 | Finance | Vertex Trading | PR-2646 | PO-8146 | Accommodation services | 140000 | 125658 | 80697 | 59303 | Approved for Payment | Medium | 2026-03-10 | 2026-03-23 | 2026-04-21 | 2026-05-21 | 67 | S. Ahmed | Escalate overdue item
PCR-047 | Logistics | Atlas Services | PR-2647 | 77 | Maintenance works | 167000 | 0 | 0 | 167000 | PR Approved | Medium | 2026-04-04 |  |  |  | 0 | R. Hassan | Routine follow-up
PCR-048 | Logistics | Summit Industrial | PR-2648 | PO-8148 | Site consumables | 234000 | 199708 | 0 | 234000 | Under Review | High | 2026-06-29 | 2026-07-06 | 2026-07-16 | 2026-08-15 | 0 | A. Khan | Routine follow-up
PCR-049 | Document Control | Horizon Supply | PR-2649 | 77 | Professional services | 300000 | 0 | 0 | 300000 | PR Approved | High | 2026-04-06 |  |  |  | 0 | R. Hassan | Routine follow-up
PCR-050 | Document Control | Prime Logistics | PR-2650 | PO-8150 | Technical materials | 134000 | 113227 | 113227 | 20773 | Paid | High | 2026-02-27 | 2026-03-10 | 2026-04-19 | 2026-05-19 | 69 | M. Ali | Escalate overdue item
PCR-051 | Logistics | Horizon Supply | PR-2651 | PO-8151 | Site consumables | 140000 | 114125 | 114125 | 25875 | Paid | Medium | 2026-02-26 | 2026-03-15 | 2026-03-28 | 2026-04-27 | 91 | F. Malik | Escalate overdue item
PCR-052 | Logistics | Atlas Services | PR-2652 | PO-8152 | Professional services | 270000 | 228425 | 0 | 270000 | Invoice Received | High | 2026-04-01 | 2026-04-06 | 2026-04-17 | 2026-05-17 | 71 | F. Malik | Escalate overdue item
PCR-053 | Facilities | Summit Industrial | PR-2653 | PO-8153 | Manpower services | 208000 | 177580 | 0 | 208000 | Under Review | Low | 2026-06-06 | 2026-06-09 | 2026-07-07 | 2026-08-06 | 0 | F. Malik | Routine follow-up
PCR-054 | Document Control | Vertex Trading | PR-2654 | PO-8154 | Equipment rental | 281000 | 0 | 0 | 281000 | PO Issued | Medium | 2026-04-03 | 2026-04-08 |  |  | 0 | S. Ahmed | Routine follow-up
PCR-055 | Finance | Vertex Trading | PR-2655 | PO-8155 | Manpower services | 39000 | 0 | 0 | 39000 | Delivered | Medium | 2026-06-13 | 2026-06-20 |  |  | 0 | F. Malik | Routine follow-up
PCR-056 | Logistics | Gulf Technical | PR-2656 | PO-8156 | Equipment rental | 103000 | 81809 | 81809 | 21191 | Paid | Medium | 2026-04-13 | 2026-04-23 | 2026-05-25 | 2026-06-24 | 33 | M. Ali | Escalate overdue item
PCR-057 | Document Control | BlueLine Services | PR-2657 | PO-8157 | Accommodation services | 402000 | 318362 | 0 | 402000 | Under Review | Medium | 2026-05-09 | 2026-05-12 | 2026-06-06 | 2026-07-06 | 21 | R. Hassan | Routine follow-up
PCR-058 | Procurement | Gulf Technical | PR-2658 | PO-8158 | Accommodation services | 199000 | 167058 | 167058 | 31942 | Paid | Low | 2026-06-18 | 2026-07-06 | 2026-08-05 | 2026-09-04 | 0 | S. Ahmed | Routine follow-up
PCR-059 | Finance | Atlas Services | PR-2659 | PO-8159 | IT equipment | 289000 | 261688 | 0 | 289000 | Under Review | Medium | 2026-02-20 | 2026-02-23 | 2026-03-21 | 2026-04-20 | 98 | F. Malik | Escalate overdue item
PCR-060 | Finance | Gulf Technical | PR-2660 | PO-8160 | Manpower services | 180000 | 145765 | 145765 | 34235 | Paid | High | 2026-02-23 | 2026-03-04 | 2026-03-18 | 2026-04-17 | 101 | A. Khan | Escalate overdue item
Formulas:
Days Aging = IF(AND([Due Date]<>"",[Outstanding (SAR)]>0),MAX(TODAY()-[Due Date],0),0)

## Vendor Summary
Vendor | Total Commitment | Invoiced | Paid | Outstanding | Open Items
Atlas Services | 1799000 | 1448474 | 577160 | 1221840 | 8
Prime Logistics | 2060000 | 1232331 | 684003 | 1375997 | 5
Gulf Technical | 2236000 | 1067872 | 607291 | 1628709 | 5
Horizon Supply | 1238000 | 636012 | 636012 | 601988 | 3
Vertex Trading | 2160000 | 772041 | 535993 | 1624007 | 10
Nexa Facilities | 2010000 | 910294 | 217243 | 1792757 | 7
Summit Industrial | 981000 | 815933 | 94395 | 886605 | 4
BlueLine Services | 681000 | 318362 | 0 | 681000 | 3

## Lists
Statuses | Departments | Vendors
PR Raised | Operations | Atlas Services
PR Approved | Administration | Prime Logistics
PO Issued | Logistics | Gulf Technical
Delivered | Procurement | Horizon Supply
Invoice Received | Document Control | Vertex Trading
Under Review | Finance | Nexa Facilities
Approved for Payment | Executive Office | Summit Industrial
Paid | Facilities | BlueLine Services