## Dashboard
Board Secretariat Dashboard
Desert Horizon JV Board of Directors • Meetings, resolutions, DocuSign signatures and action follow-up • Demo data
MEETINGS HELD |  | RESOLUTIONS |  |  | AWAITING SIGNATURE |  |  | OPEN ACTIONS |  | OVERDUE
Board meetings in 2026 |  | Meeting + circular |  |  | Circular resolutions in DocuSign |  |  | Open + in progress |  | Past due date
NEXT BOARD CYCLE
Next meeting | Meeting No. |  | Type |  | Papers deadline |  | Days to papers |  | Days to meeting
RESOLUTIONS BY CATEGORY |  |  |  |  | RESOLUTIONS MIX
Category | Meeting | Circular | Total | Awaiting
Contracts & Subcontracts
Finance & Budget
Banking & LCs
HR & Appointments
Governance
HSE & Quality
Total
BOARD ACTIONS BY OWNER |  |  |  |  | ACTION STATUS BY OWNER
Owner | Open | In Progress | Closed | Overdue
Project Director
Commercial Manager
Finance Manager
HR Manager
HSE Director
Board Secretary
Total
CIRCULAR RESOLUTIONS AWAITING DOCUSIGN SIGNATURES
Subject |  |  |  | Resolution No. |  | Circulated |  | Signed |  | Days waiting
Formulas:
Days to papers = [AWAITING SIGNATURE]-TODAY()
Days to meeting = [MEETINGS HELD]-TODAY()
OVERDUE = IFERROR(TODAY()-[Circulated],"")

## Board Members
Board Members
Desert Horizon JV • JV of Rimal Contracting Co. (KSA) & Anatolia Yapı A.Ş. (Türkiye) • Demo data
Member ID | Name | Board Role | Partner Company | Attendance 2026
BM-01 | Eng. Khalid Al-Mansour | Chairman | Rimal Contracting Co.
BM-02 | Mr. Emre Kaya | Vice Chairman | Anatolia Yapı A.Ş.
BM-03 | Mr. Saud Al-Harbi | Board Member | Rimal Contracting Co.
BM-04 | Mr. Burak Demir | Board Member | Anatolia Yapı A.Ş.
BM-05 | Ms. Layla Al-Zahrani | Board Member | Rimal Contracting Co.
BM-06 | Mr. Selim Aydın | Board Member | Anatolia Yapı A.Ş.
SEC | Board Secretariat | Secretary (non-voting) | Desert Horizon JV | —

## Meeting Calendar
Board Meeting Calendar 2026
Desert Horizon JV • JV of Rimal Contracting Co. (KSA) & Anatolia Yapı A.Ş. (Türkiye) • Demo data • Papers deadline = 7 days before meeting
Meeting No. | Meeting Date | Type | Venue / Mode | Agenda Items | Members Present | Quorum | Papers Deadline | Papers Circulated | Minutes Issued | Minutes Signed | Status
BOD-2026-01 | 2026-01-22 | Ordinary | Riyadh HQ | 9 | 6 |  |  | 2026-01-14 | 2026-01-28 | 2026-02-06 | Held
BOD-2026-02 | 2026-03-19 | Ordinary | Site Office | 9 | 6 |  |  | 2026-03-13 | 2026-03-25 | 2026-04-03 | Held
BOD-2026-03 | 2026-04-08 | Extraordinary | Virtual (Teams) | 10 | 6 |  |  | 2026-03-31 | 2026-04-12 | 2026-04-17 | Held
BOD-2026-04 | 2026-05-21 | Ordinary | Istanbul Office | 8 | 5 |  |  | 2026-05-13 | 2026-05-27 | 2026-06-01 | Held
BOD-2026-05 | 2026-07-23 | Ordinary | Riyadh HQ | 7 | 6 |  |  | 2026-07-17 | 2026-07-26 | 2026-08-02 | Held
BOD-2026-06 | 2026-09-24 | Ordinary | Site Office | 10 | 6 |  |  | 2026-09-17 | 2026-09-27 | 2026-10-04 | Held
BOD-2026-07 | 2026-11-19 | Ordinary | Riyadh HQ | 10 | [6 empty] | Scheduled
BOD-2026-08 | 2026-12-17 | Extraordinary | Virtual (Teams) | 9 | [6 empty] | Scheduled

## Resolutions Register
Board Resolutions Register
Desert Horizon JV • JV of Rimal Contracting Co. (KSA) & Anatolia Yapı A.Ş. (Türkiye) • Demo data • Circular resolutions signed via DocuSign
Resolution No. | Date | Meeting Ref | Type | Category | Subject | Signatories Req. | Signed | Signed % | DocuSign Envelope | Status | Effective Date | Pending #
BR-2026-001 | 2026-01-22 | BOD-2026-01 | Meeting | HSE & Quality | Approval of emergency response plan | 6 | 6 |  | DS-124352 | Completed | 2026-02-06
BR-2026-002 | 2026-01-22 | BOD-2026-01 | Meeting | Finance & Budget | Approval of revised project budget | 6 | 6 |  | DS-230943 | Completed | 2026-02-06
BR-2026-003 | 2026-01-22 | BOD-2026-01 | Meeting | Contracts & Subcontracts | Extension of equipment rental agreement | 6 | 6 |  | DS-268924 | Completed | 2026-02-06
BR-2026-004 | 2026-02-11 | Circular | Circular | Banking & LCs | Opening of letter of credit for TBM spares | 6 | 6 |  | DS-271008 | Completed | 2026-02-19
BR-2026-005 | 2026-02-26 | Circular | Circular | Contracts & Subcontracts | Award of muck-removal subcontract | 6 | 6 |  | DS-719203 | Completed | 2026-03-01
BR-2026-006 | 2026-03-19 | BOD-2026-02 | Meeting | HR & Appointments | Approval of staff incentive scheme | 6 | 6 |  | DS-258437 | Completed | 2026-04-03
BR-2026-007 | 2026-03-19 | BOD-2026-02 | Meeting | Finance & Budget | Approval of revised project budget | 6 | 6 |  | DS-592769 | Completed | 2026-04-03
BR-2026-008 | 2026-03-19 | BOD-2026-02 | Meeting | Finance & Budget | Approval of revised project budget | 6 | 6 |  | DS-918161 | Completed | 2026-04-03
BR-2026-009 | 2026-03-19 | BOD-2026-02 | Meeting | Finance & Budget | Approval of quarterly financial statements | 6 | 6 |  | DS-806524 | Completed | 2026-04-03
BR-2026-010 | 2026-03-19 | BOD-2026-02 | Meeting | HSE & Quality | Endorsement of quality audit findings | 6 | 6 |  | DS-865206 | Completed | 2026-04-03
BR-2026-011 | 2026-04-08 | BOD-2026-03 | Meeting | Contracts & Subcontracts | Extension of equipment rental agreement | 6 | 6 |  | DS-686093 | Completed | 2026-04-17
BR-2026-012 | 2026-04-08 | BOD-2026-03 | Meeting | HR & Appointments | Approval of manpower plan | 6 | 6 |  | DS-457806 | Completed | 2026-04-17
BR-2026-013 | 2026-04-08 | BOD-2026-03 | Meeting | Finance & Budget | Approval of insurance renewal | 6 | 6 |  | DS-406170 | Completed | 2026-04-17
BR-2026-014 | 2026-04-29 | Circular | Circular | Finance & Budget | Approval of insurance renewal | 6 | 6 |  | DS-463446 | Completed | 2026-05-05
BR-2026-015 | 2026-05-21 | BOD-2026-04 | Meeting | HR & Appointments | Approval of staff incentive scheme | 6 | 6 |  | DS-433396 | Completed | 2026-06-01
BR-2026-016 | 2026-05-21 | BOD-2026-04 | Meeting | HR & Appointments | Approval of staff incentive scheme | 6 | 6 |  | DS-378611 | Completed | 2026-06-01
BR-2026-017 | 2026-05-21 | BOD-2026-04 | Meeting | Contracts & Subcontracts | Award of tunnelling subcontract package | 6 | 6 |  | DS-266664 | Completed | 2026-06-01
BR-2026-018 | 2026-05-21 | BOD-2026-04 | Meeting | HSE & Quality | Endorsement of quality audit findings | 6 | 6 |  | DS-620104 | Completed | 2026-06-01
BR-2026-019 | 2026-05-21 | BOD-2026-04 | Meeting | Contracts & Subcontracts | Extension of equipment rental agreement | 6 | 6 |  | DS-173522 | Completed | 2026-06-01
BR-2026-020 | 2026-06-15 | Circular | Circular | Banking & LCs | Change of authorised bank signatories | 6 | 6 |  | DS-630719 | Completed | 2026-06-21
BR-2026-021 | 2026-07-23 | BOD-2026-05 | Meeting | Governance | Approval of previous minutes | 6 | 6 |  | DS-683518 | Completed | 2026-08-02
BR-2026-022 | 2026-07-23 | BOD-2026-05 | Meeting | Governance | Approval of delegation of authority matrix | 6 | 6 |  | DS-289453 | Completed | 2026-08-02
BR-2026-023 | 2026-07-23 | BOD-2026-05 | Meeting | HSE & Quality | Approval of HSE annual plan | 6 | 6 |  | DS-756929 | Completed | 2026-08-02
BR-2026-024 | 2026-07-23 | BOD-2026-05 | Meeting | Banking & LCs | Change of authorised bank signatories | 6 | 6 |  | DS-463450 | Completed | 2026-08-02
BR-2026-025 | 2026-08-12 | Circular | Circular | Contracts & Subcontracts | Extension of equipment rental agreement | 6 | 6 |  | DS-799333 | Completed | 2026-08-16
BR-2026-026 | 2026-08-30 | Circular | Circular | HR & Appointments | Appointment of Deputy Project Director | 6 | 6 |  | DS-357815 | Completed | 2026-09-03
BR-2026-027 | 2026-09-10 | Circular | Circular | Contracts & Subcontracts | Award of segment supply contract | 6 | 6 |  | DS-689107 | Completed | 2026-09-13
BR-2026-028 | 2026-09-24 | BOD-2026-06 | Meeting | Finance & Budget | Approval of revised project budget | 6 | 6 |  | DS-276886 | Completed | 2026-10-04
BR-2026-029 | 2026-09-24 | BOD-2026-06 | Meeting | Contracts & Subcontracts | Approval of design consultant amendment | 6 | 6 |  | DS-914763 | Completed | 2026-10-04
BR-2026-030 | 2026-09-24 | BOD-2026-06 | Meeting | HR & Appointments | Appointment of HSE Director | 6 | 6 |  | DS-267651 | Completed | 2026-10-04
BR-2026-031 | 2026-09-24 | BOD-2026-06 | Meeting | HSE & Quality | Approval of HSE annual plan | 6 | 6 |  | DS-808734 | Completed | 2026-10-04
BR-2026-032 | 2026-09-24 | BOD-2026-06 | Meeting | Governance | Adoption of board calendar | 6 | 6 |  | DS-526785 | Completed | 2026-10-04
BR-2026-033 | 2026-10-01 | Circular | Circular | Banking & LCs | Renewal of performance bond | 6 | 4 |  | DS-944399 | Awaiting Signatures
BR-2026-034 | 2026-10-06 | Circular | Circular | Finance & Budget | Approval of Q3 cash-flow forecast | 6 | 4 |  | DS-911510 | Awaiting Signatures
BR-2026-035 | 2026-10-11 | Circular | Circular | Contracts & Subcontracts | Award of tunnel ventilation subcontract | 6 | 5 |  | DS-606643 | Awaiting Signatures

## Action Log
Board Action Log
Desert Horizon JV • JV of Rimal Contracting Co. (KSA) & Anatolia Yapı A.Ş. (Türkiye) • Demo data • Days overdue calculated against today
Action ID | Meeting Ref | Action | Owner | Due Date | Status | Closed Date | Days Overdue
ACT-001 | BOD-2026-01 | Submit claim status report to the client | Finance Manager | 2026-02-21 | Closed | 2026-02-19
ACT-002 | BOD-2026-01 | Present insurance renewal options | Project Director | 2026-02-05 | Closed | 2026-02-01
ACT-003 | BOD-2026-01 | Present TBM progress recovery plan | Board Secretary | 2026-02-21 | Closed | 2026-02-17
ACT-004 | BOD-2026-01 | Submit claim status report to the client | HSE Director | 2026-03-08 | Closed | 2026-03-04
ACT-005 | BOD-2026-01 | Report on manpower localisation | Commercial Manager | 2026-03-08 | Closed | 2026-03-05
ACT-006 | BOD-2026-02 | Share bank signatory forms with both partners | Commercial Manager | 2026-05-03 | Closed | 2026-05-04
ACT-007 | BOD-2026-02 | Submit revised cash-flow to the board | HR Manager | 2026-04-18 | Closed | 2026-04-23
ACT-008 | BOD-2026-02 | Submit revised cash-flow to the board | Finance Manager | 2026-04-09 | In Progress
ACT-009 | BOD-2026-02 | Present insurance renewal options | Finance Manager | 2026-04-18 | Closed | 2026-04-21
ACT-010 | BOD-2026-02 | Present TBM progress recovery plan | Commercial Manager | 2026-05-03 | Closed | 2026-04-29
ACT-011 | BOD-2026-02 | Submit revised cash-flow to the board | Board Secretary | 2026-04-02 | Closed | 2026-03-29
ACT-012 | BOD-2026-02 | Circulate signed subcontract to partners | Board Secretary | 2026-05-03 | Closed | 2026-04-28
ACT-013 | BOD-2026-03 | Present insurance renewal options | HR Manager | 2026-04-29 | Closed | 2026-04-28
ACT-014 | BOD-2026-03 | Present TBM progress recovery plan | HR Manager | 2026-04-29 | Closed | 2026-04-25
ACT-015 | BOD-2026-03 | Submit revised cash-flow to the board | HSE Director | 2026-04-29 | Closed | 2026-05-01
ACT-016 | BOD-2026-03 | Present insurance renewal options | HR Manager | 2026-04-22 | Closed | 2026-04-16
ACT-017 | BOD-2026-03 | Present TBM progress recovery plan | Board Secretary | 2026-04-22 | Closed | 2026-04-25
ACT-018 | BOD-2026-03 | Prepare board calendar for next year | Finance Manager | 2026-04-29 | Closed | 2026-05-04
ACT-019 | BOD-2026-03 | Share bank signatory forms with both partners | Board Secretary | 2026-04-22 | Closed | 2026-04-18
ACT-020 | BOD-2026-04 | Circulate signed subcontract to partners | HSE Director | 2026-07-05 | In Progress
ACT-021 | BOD-2026-04 | Report on manpower localisation | HSE Director | 2026-06-04 | Closed | 2026-06-09
ACT-022 | BOD-2026-04 | Share HSE statistics with lessons learned | HSE Director | 2026-06-20 | Closed | 2026-06-23
ACT-023 | BOD-2026-04 | Update delegation of authority in Oracle | Finance Manager | 2026-06-11 | Closed | 2026-06-10
ACT-024 | BOD-2026-04 | Circulate signed subcontract to partners | Project Director | 2026-06-04 | Closed | 2026-06-04
ACT-025 | BOD-2026-04 | Share HSE statistics with lessons learned | HSE Director | 2026-06-04 | Closed | 2026-06-05
ACT-026 | BOD-2026-04 | Close internal audit observations | HR Manager | 2026-06-04 | Closed | 2026-06-09
ACT-027 | BOD-2026-05 | Submit revised cash-flow to the board | Project Director | 2026-09-06 | Closed | 2026-09-03
ACT-028 | BOD-2026-05 | Share bank signatory forms with both partners | Board Secretary | 2026-09-06 | Closed | 2026-09-03
ACT-029 | BOD-2026-05 | Close internal audit observations | Commercial Manager | 2026-09-06 | In Progress
ACT-030 | BOD-2026-05 | Report on manpower localisation | HR Manager | 2026-09-06 | In Progress
ACT-031 | BOD-2026-05 | Circulate signed subcontract to partners | Project Director | 2026-08-13 | Closed | 2026-08-17
ACT-032 | BOD-2026-05 | Close internal audit observations | Finance Manager | 2026-09-06 | In Progress
ACT-033 | BOD-2026-05 | Submit claim status report to the client | HSE Director | 2026-08-13 | Closed | 2026-08-17
ACT-034 | BOD-2026-05 | Present insurance renewal options | Finance Manager | 2026-08-22 | Closed | 2026-08-23
ACT-035 | BOD-2026-06 | Report on manpower localisation | Commercial Manager | 2026-10-08 | In Progress
ACT-036 | BOD-2026-06 | Update risk register and top-10 risks | Commercial Manager | 2026-10-24 | In Progress
ACT-037 | BOD-2026-06 | Circulate signed subcontract to partners | HSE Director | 2026-10-08 | In Progress
ACT-038 | BOD-2026-06 | Update risk register and top-10 risks | Board Secretary | 2026-10-24 | Closed | 2026-10-14
ACT-039 | BOD-2026-06 | Present TBM progress recovery plan | Board Secretary | 2026-11-08 | Open
ACT-040 | BOD-2026-06 | Submit claim status report to the client | Finance Manager | 2026-11-08 | Open
ACT-041 | BOD-2026-06 | Submit claim status report to the client | Commercial Manager | 2026-10-24 | Closed | 2026-10-14
ACT-042 | BOD-2026-06 | Submit revised cash-flow to the board | Finance Manager | 2026-10-24 | Open
Formulas:
Days Overdue = IF(AND([Status]<>"Closed",[Due Date]<TODAY()),TODAY()-[Due Date],"")

## Attendance
Board Attendance Matrix 2026
Desert Horizon JV • JV of Rimal Contracting Co. (KSA) & Anatolia Yapı A.Ş. (Türkiye) • Demo data • P = Present, A = Apology
Member | Role | BOD-01 | BOD-02 | BOD-03 | BOD-04 | BOD-05 | BOD-06 | Attendance %
Eng. Khalid Al-Mansour | Chairman | P | P | P | P | P | P
Mr. Emre Kaya | Vice Chairman | P | P | P | P | P | P
Mr. Saud Al-Harbi | Board Member | P | P | P | P | P | P
Mr. Burak Demir | Board Member | P | P | P | P | P | P
Ms. Layla Al-Zahrani | Board Member | P | P | P | A | P | P
Mr. Selim Aydın | Board Member | P | P | P | P | P | P