## Dashboard
Document Control Dashboard
Coastal Tunnel Package (CTP) • Desert Horizon JV • Reviewer: Meridian Engineering Partners • Demo data
TOTAL DOCUMENTS |  |  | APPROVED (A + B) |  |  | UNDER REVIEW |  | RESUBMIT (C + D)
Registered submissions |  |  | Cleared for use |  |  |  |  | Revise or new submission
REVIEW STATUS BY DOCUMENT TYPE | [6 empty] | OVERALL REVIEW STATUS
Document Type | Code A | Code B | Code C | Code D | In Review | Total
Drawing
Method Statement
Material Submittal
Inspection Report
Procedure
Calculation
Total
DOCUMENTS BY DISCIPLINE | [6 empty] | APPROVED VS RESUBMIT BY DISCIPLINE
Discipline | Approved | In Review | Resubmit | Total
Tunnelling
Civil
Geotechnical
MEP
HSE
Quality

## Search
Document Search
Type any part of a document number, title, type, discipline, transmittal or status in the yellow box
Search:
Document No. | Title | Type | Discipline | Rev | Submitted | Review Status | File Location

## Document Register
Document Control Register
Coastal Tunnel Package (CTP) – Desert Horizon JV • Client: Coastal Gateway Development Authority • Demo data
Document No. | Title | Type | Discipline | Rev | Submitted | Transmittal No. | Reviewer | Review Status | Response | Days in Review | Next Action | File Location
CTP-DHJ-HSE-MAT-0003 | Ventilation fans | Material Submittal | HSE | A | 2026-03-02 | TRN-01059 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-08 |  | Incorporate comments | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0003
CTP-DHJ-HSE-MAT-0001 | Precast segment gaskets | Material Submittal | HSE | A | 2026-03-04 | TRN-01003 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-03-10 |  | Revise and resubmit | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0001
CTP-DHJ-MEP-MAT-0003 | Ventilation fans | Material Submittal | MEP | A | 2026-03-06 | TRN-01034 | Meridian Engineering Partners | Code A – Approved | 2026-03-26 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0003
CTP-DHJ-HSE-RPT-0004 | Weld inspection | Inspection Report | HSE | A | 2026-03-06 | TRN-01086 | Meridian Engineering Partners | Code A – Approved | 2026-03-18 |  | Issue for construction | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0004
CTP-DHJ-TUN-MAT-0011 | Precast segment gaskets | Material Submittal | Tunnelling | 1 | 2026-03-06 | TRN-01215 | Meridian Engineering Partners | Code D – Rejected | 2026-03-25 |  | Prepare new submission | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0011
CTP-DHJ-GEO-DWG-0010 | Drainage layout | Drawing | Geotechnical | A | 2026-03-07 | TRN-01178 | Meridian Engineering Partners | Code A – Approved | 2026-03-26 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0010
CTP-DHJ-GEO-MAT-0008 | Precast segment gaskets | Material Submittal | Geotechnical | B | 2026-03-08 | TRN-01231 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-15 |  | Incorporate comments | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0008
CTP-DHJ-MEP-DWG-0011 | Portal structure details | Drawing | MEP | 1 | 2026-03-09 | TRN-01165 | Meridian Engineering Partners | Code A – Approved | 2026-03-17 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0011
CTP-DHJ-TUN-MST-0002 | Waterproofing installation | Method Statement | Tunnelling | 1 | 2026-03-10 | TRN-01053 | Meridian Engineering Partners | Code A – Approved | 2026-03-23 |  | Issue for construction | \\DC\Tunnelling\Method Statement\CTP-DHJ-TUN-MST-0002
CTP-DHJ-MEP-MAT-0010 | Grout admixture | Material Submittal | MEP | B | 2026-03-11 | TRN-01217 | Meridian Engineering Partners | Code A – Approved | 2026-03-17 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0010
CTP-DHJ-HSE-MST-0007 | TBM launching | Method Statement | HSE | 1 | 2026-03-13 | TRN-01087 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-18 |  | Incorporate comments | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0007
CTP-DHJ-QAQ-MST-0005 | Waterproofing installation | Method Statement | Quality | B | 2026-03-15 | TRN-01208 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-03 |  | Incorporate comments | \\DC\Quality\Method Statement\CTP-DHJ-QAQ-MST-0005
CTP-DHJ-QAQ-DWG-0008 | Segment ring layout | Drawing | Quality | 0 | 2026-03-16 | TRN-01181 | Meridian Engineering Partners | Code A – Approved | 2026-04-05 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0008
CTP-DHJ-MEP-MAT-0006 | Rebar 16 mm | Material Submittal | MEP | 0 | 2026-03-17 | TRN-01119 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-24 |  | Incorporate comments | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0006
CTP-DHJ-HSE-MAT-0009 | Rebar 16 mm | Material Submittal | HSE | 0 | 2026-03-17 | TRN-01161 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-27 |  | Incorporate comments | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0009
CTP-DHJ-MEP-RPT-0001 | Concrete cube results | Inspection Report | MEP | A | 2026-03-18 | TRN-01008 | Meridian Engineering Partners | Code D – Rejected | 2026-03-29 |  | Prepare new submission | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0001
CTP-DHJ-MEP-MAT-0002 | Precast segment gaskets | Material Submittal | MEP | 0 | 2026-03-18 | TRN-01028 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-03-27 |  | Incorporate comments | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0002
CTP-DHJ-QAQ-MST-0002 | Shaft excavation | Method Statement | Quality | A | 2026-03-19 | TRN-01123 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-06 |  | Incorporate comments | \\DC\Quality\Method Statement\CTP-DHJ-QAQ-MST-0002
CTP-DHJ-HSE-MST-0010 | Cable pulling | Method Statement | HSE | A | 2026-03-19 | TRN-01188 | Meridian Engineering Partners | Code A – Approved | 2026-03-24 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0010
CTP-DHJ-TUN-MAT-0010 | Ventilation fans | Material Submittal | Tunnelling | B | 2026-03-19 | TRN-01198 | Meridian Engineering Partners | Code A – Approved | 2026-03-31 |  | Issue for construction | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0010
CTP-DHJ-MEP-MAT-0009 | Rebar 16 mm | Material Submittal | MEP | 0 | 2026-03-19 | TRN-01212 | Meridian Engineering Partners | Code A – Approved | 2026-04-04 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0009
CTP-DHJ-MEP-DWG-0002 | Drainage layout | Drawing | MEP | B | 2026-03-20 | TRN-01030 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-03-25 |  | Revise and resubmit | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0002
CTP-DHJ-TUN-DWG-0007 | Drainage layout | Drawing | Tunnelling | A | 2026-03-20 | TRN-01111 | Meridian Engineering Partners | Code A – Approved | 2026-04-03 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0007
CTP-DHJ-GEO-DWG-0008 | Drainage layout | Drawing | Geotechnical | 1 | 2026-03-21 | TRN-01110 | Meridian Engineering Partners | Code A – Approved | 2026-04-10 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0008
CTP-DHJ-MEP-RPT-0004 | Weld inspection | Inspection Report | MEP | B | 2026-03-23 | TRN-01200 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-09 |  | Incorporate comments | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0004
CTP-DHJ-QAQ-MST-0003 | TBM launching | Method Statement | Quality | 1 | 2026-03-24 | TRN-01140 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-04 |  | Incorporate comments | \\DC\Quality\Method Statement\CTP-DHJ-QAQ-MST-0003
CTP-DHJ-TUN-MAT-0001 | Precast segment gaskets | Material Submittal | Tunnelling | 0 | 2026-03-25 | TRN-01072 | Meridian Engineering Partners | Code A – Approved | 2026-04-10 |  | Issue for construction | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0001
CTP-DHJ-CIV-MAT-0006 | Grout admixture | Material Submittal | Civil | A | 2026-03-26 | TRN-01051 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-06 |  | Incorporate comments | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0006
CTP-DHJ-TUN-DWG-0001 | Drainage layout | Drawing | Tunnelling | 0 | 2026-03-27 | TRN-01021 | Meridian Engineering Partners | Code A – Approved | 2026-04-08 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0001
CTP-DHJ-MEP-DWG-0006 | Portal structure details | Drawing | MEP | A | 2026-03-27 | TRN-01065 | Meridian Engineering Partners | Code A – Approved | 2026-04-17 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0006
CTP-DHJ-QAQ-DWG-0005 | Cross passage reinforcement | Drawing | Quality | A | 2026-03-27 | TRN-01120 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-04-01 |  | Revise and resubmit | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0005
CTP-DHJ-MEP-DWG-0010 | Shaft general arrangement | Drawing | MEP | B | 2026-03-28 | TRN-01155 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-18 |  | Incorporate comments | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0010
CTP-DHJ-MEP-MAT-0005 | Ventilation fans | Material Submittal | MEP | A | 2026-03-31 | TRN-01098 | Meridian Engineering Partners | Code A – Approved | 2026-04-16 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0005
CTP-DHJ-MEP-DWG-0016 | Drainage layout | Drawing | MEP | A | 2026-03-31 | TRN-01224 | Meridian Engineering Partners | Code A – Approved | 2026-04-20 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0016
CTP-DHJ-CIV-MST-0006 | Shaft excavation | Method Statement | Civil | B | 2026-04-01 | TRN-01177 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-04-06 |  | Revise and resubmit | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0006
CTP-DHJ-QAQ-MAT-0007 | Rebar 16 mm | Material Submittal | Quality | 0 | 2026-04-01 | TRN-01223 | Meridian Engineering Partners | Code D – Rejected | 2026-04-13 |  | Prepare new submission | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0007
CTP-DHJ-GEO-MAT-0006 | Precast segment gaskets | Material Submittal | Geotechnical | A | 2026-04-03 | TRN-01187 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-22 |  | Incorporate comments | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0006
CTP-DHJ-TUN-CAL-0001 | Segment design check | Calculation | Tunnelling | A | 2026-04-04 | TRN-01011 | Meridian Engineering Partners | Code A – Approved | 2026-04-09 |  | Issue for construction | \\DC\Tunnelling\Calculation\CTP-DHJ-TUN-CAL-0001
CTP-DHJ-CIV-MST-0004 | Cable pulling | Method Statement | Civil | B | 2026-04-04 | TRN-01133 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-04-25 |  | Revise and resubmit | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0004
CTP-DHJ-HSE-RPT-0006 | Monthly settlement monitoring | Inspection Report | HSE | 1 | 2026-04-04 | TRN-01203 | Meridian Engineering Partners | Code A – Approved | 2026-04-25 |  | Issue for construction | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0006
CTP-DHJ-QAQ-MST-0004 | Annulus grouting | Method Statement | Quality | 1 | 2026-04-05 | TRN-01164 | Meridian Engineering Partners | Code A – Approved | 2026-04-10 |  | Issue for construction | \\DC\Quality\Method Statement\CTP-DHJ-QAQ-MST-0004
CTP-DHJ-MEP-RPT-0003 | Weld inspection | Inspection Report | MEP | B | 2026-04-06 | TRN-01179 | Meridian Engineering Partners | Code A – Approved | 2026-04-12 |  | Issue for construction | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0003
CTP-DHJ-TUN-DWG-0013 | Cross passage reinforcement | Drawing | Tunnelling | 0 | 2026-04-09 | TRN-01214 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-18 |  | Incorporate comments | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0013
CTP-DHJ-QAQ-MAT-0002 | Rebar 16 mm | Material Submittal | Quality | 1 | 2026-04-10 | TRN-01094 | Meridian Engineering Partners | Code A – Approved | 2026-04-16 |  | Issue for construction | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0002
CTP-DHJ-QAQ-MAT-0008 | Rebar 16 mm | Material Submittal | Quality | B | 2026-04-10 | TRN-01238 | Meridian Engineering Partners | Code D – Rejected | 2026-04-20 |  | Prepare new submission | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0008
CTP-DHJ-CIV-DWG-0004 | Portal structure details | Drawing | Civil | B | 2026-04-14 | TRN-01075 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-04-22 |  | Revise and resubmit | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0004
CTP-DHJ-MEP-MST-0001 | Cable pulling | Method Statement | MEP | B | 2026-04-15 | TRN-01012 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-04 |  | Incorporate comments | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0001
CTP-DHJ-TUN-DWG-0002 | Shaft general arrangement | Drawing | Tunnelling | B | 2026-04-15 | TRN-01025 | Meridian Engineering Partners | Code A – Approved | 2026-04-22 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0002
CTP-DHJ-HSE-MAT-0012 | Rebar 16 mm | Material Submittal | HSE | 1 | 2026-04-16 | TRN-01213 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-04-27 |  | Incorporate comments | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0012
CTP-DHJ-GEO-MAT-0004 | Rebar 16 mm | Material Submittal | Geotechnical | A | 2026-04-18 | TRN-01147 | Meridian Engineering Partners | Code A – Approved | 2026-05-03 |  | Issue for construction | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0004
CTP-DHJ-HSE-RPT-0002 | Survey control check | Inspection Report | HSE | 1 | 2026-04-20 | TRN-01020 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-10 |  | Incorporate comments | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0002
CTP-DHJ-MEP-PRC-0001 | Permit to work | Procedure | MEP | 0 | 2026-04-26 | TRN-01038 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-07 |  | Incorporate comments | \\DC\MEP\Procedure\CTP-DHJ-MEP-PRC-0001
CTP-DHJ-QAQ-DWG-0012 | Segment ring layout | Drawing | Quality | A | 2026-04-26 | TRN-01235 | Meridian Engineering Partners | Code A – Approved | 2026-05-13 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0012
CTP-DHJ-CIV-MAT-0004 | Ventilation fans | Material Submittal | Civil | 0 | 2026-04-27 | TRN-01047 | Meridian Engineering Partners | Code A – Approved | 2026-05-18 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0004
CTP-DHJ-GEO-MAT-0001 | Grout admixture | Material Submittal | Geotechnical | A | 2026-04-28 | TRN-01019 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-09 |  | Revise and resubmit | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0001
CTP-DHJ-CIV-DWG-0002 | Shaft general arrangement | Drawing | Civil | 0 | 2026-04-28 | TRN-01064 | Meridian Engineering Partners | Code A – Approved | 2026-05-13 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0002
CTP-DHJ-GEO-DWG-0002 | Drainage layout | Drawing | Geotechnical | A | 2026-04-30 | TRN-01044 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-08 |  | Incorporate comments | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0002
CTP-DHJ-HSE-MAT-0010 | Precast segment gaskets | Material Submittal | HSE | 1 | 2026-05-01 | TRN-01174 | Meridian Engineering Partners | Code A – Approved | 2026-05-13 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0010
CTP-DHJ-MEP-DWG-0012 | Drainage layout | Drawing | MEP | 1 | 2026-05-02 | TRN-01173 | Meridian Engineering Partners | Code A – Approved | 2026-05-08 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0012
CTP-DHJ-CIV-CAL-0001 | Temporary works design | Calculation | Civil | A | 2026-05-02 | TRN-01190 | Meridian Engineering Partners | Code A – Approved | 2026-05-12 |  | Issue for construction | \\DC\Civil\Calculation\CTP-DHJ-CIV-CAL-0001
CTP-DHJ-MEP-MST-0004 | Cable pulling | Method Statement | MEP | B | 2026-05-04 | TRN-01096 | Meridian Engineering Partners | Code D – Rejected | 2026-05-10 |  | Prepare new submission | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0004
CTP-DHJ-HSE-MAT-0011 | Rebar 16 mm | Material Submittal | HSE | A | 2026-05-04 | TRN-01189 | Meridian Engineering Partners | Code A – Approved | 2026-05-14 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0011
CTP-DHJ-TUN-DWG-0003 | Portal structure details | Drawing | Tunnelling | B | 2026-05-05 | TRN-01032 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-22 |  | Revise and resubmit | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0003
CTP-DHJ-MEP-MAT-0004 | Grout admixture | Material Submittal | MEP | B | 2026-05-05 | TRN-01035 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-19 |  | Revise and resubmit | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0004
CTP-DHJ-MEP-DWG-0004 | Portal structure details | Drawing | MEP | A | 2026-05-05 | TRN-01046 | Meridian Engineering Partners | Code A – Approved | 2026-05-25 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0004
CTP-DHJ-HSE-MST-0005 | Shaft excavation | Method Statement | HSE | 1 | 2026-05-05 | TRN-01057 | Meridian Engineering Partners | Code A – Approved | 2026-05-16 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0005
CTP-DHJ-CIV-RPT-0003 | Survey control check | Inspection Report | Civil | A | 2026-05-06 | TRN-01136 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-19 |  | Revise and resubmit | \\DC\Civil\Inspection Report\CTP-DHJ-CIV-RPT-0003
CTP-DHJ-CIV-MAT-0009 | Rebar 16 mm | Material Submittal | Civil | B | 2026-05-08 | TRN-01185 | Meridian Engineering Partners | Code A – Approved | 2026-05-29 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0009
CTP-DHJ-TUN-CAL-0002 | Temporary works design | Calculation | Tunnelling | B | 2026-05-09 | TRN-01014 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-14 |  | Revise and resubmit | \\DC\Tunnelling\Calculation\CTP-DHJ-TUN-CAL-0002
CTP-DHJ-MEP-DWG-0003 | Portal structure details | Drawing | MEP | B | 2026-05-10 | TRN-01040 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-27 |  | Revise and resubmit | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0003
CTP-DHJ-QAQ-MAT-0005 | Rebar 16 mm | Material Submittal | Quality | 0 | 2026-05-11 | TRN-01114 | Meridian Engineering Partners | Code A – Approved | 2026-05-30 |  | Issue for construction | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0005
CTP-DHJ-HSE-RPT-0001 | Monthly settlement monitoring | Inspection Report | HSE | A | 2026-05-13 | TRN-01007 | Meridian Engineering Partners | Code A – Approved | 2026-05-30 |  | Issue for construction | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0001
CTP-DHJ-HSE-MST-0008 | Shaft excavation | Method Statement | HSE | A | 2026-05-14 | TRN-01127 | Meridian Engineering Partners | Code A – Approved | 2026-06-03 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0008
CTP-DHJ-HSE-RPT-0005 | Monthly settlement monitoring | Inspection Report | HSE | B | 2026-05-14 | TRN-01193 | Meridian Engineering Partners | Code A – Approved | 2026-05-24 |  | Issue for construction | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0005
CTP-DHJ-TUN-DWG-0010 | Portal structure details | Drawing | Tunnelling | 1 | 2026-05-15 | TRN-01171 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-01 |  | Incorporate comments | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0010
CTP-DHJ-QAQ-MAT-0006 | Ventilation fans | Material Submittal | Quality | A | 2026-05-16 | TRN-01222 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-27 |  | Incorporate comments | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0006
CTP-DHJ-HSE-MST-0009 | TBM launching | Method Statement | HSE | A | 2026-05-18 | TRN-01142 | Meridian Engineering Partners | Code D – Rejected | 2026-06-03 |  | Prepare new submission | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0009
CTP-DHJ-GEO-DWG-0011 | Cross passage reinforcement | Drawing | Geotechnical | B | 2026-05-18 | TRN-01180 | Meridian Engineering Partners | Code A – Approved | 2026-06-07 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0011
CTP-DHJ-TUN-PRC-0002 | Document control procedure | Procedure | Tunnelling | 0 | 2026-05-19 | TRN-01052 | Meridian Engineering Partners | Code A – Approved | 2026-06-01 |  | Issue for construction | \\DC\Tunnelling\Procedure\CTP-DHJ-TUN-PRC-0002
CTP-DHJ-GEO-PRC-0003 | Permit to work | Procedure | Geotechnical | B | 2026-05-19 | TRN-01207 | Meridian Engineering Partners | Code A – Approved | 2026-05-25 |  | Issue for construction | \\DC\Geotechnical\Procedure\CTP-DHJ-GEO-PRC-0003
CTP-DHJ-QAQ-MAT-0004 | Rebar 16 mm | Material Submittal | Quality | B | 2026-05-23 | TRN-01112 | Meridian Engineering Partners | Code A – Approved | 2026-06-04 |  | Issue for construction | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0004
CTP-DHJ-MEP-RPT-0005 | Air quality monitoring | Inspection Report | MEP | A | 2026-05-23 | TRN-01216 | Meridian Engineering Partners | Code A – Approved | 2026-06-06 |  | Issue for construction | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0005
CTP-DHJ-QAQ-DWG-0011 | Segment ring layout | Drawing | Quality | A | 2026-05-23 | TRN-01229 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-05-28 |  | Revise and resubmit | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0011
CTP-DHJ-MEP-DWG-0001 | Segment ring layout | Drawing | MEP | B | 2026-05-24 | TRN-01026 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-05-30 |  | Incorporate comments | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0001
CTP-DHJ-HSE-DWG-0011 | Segment ring layout | Drawing | HSE | 1 | 2026-05-24 | TRN-01170 | Meridian Engineering Partners | Code A – Approved | 2026-06-11 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0011
CTP-DHJ-CIV-MST-0002 | Shaft excavation | Method Statement | Civil | 1 | 2026-05-26 | TRN-01062 | Meridian Engineering Partners | Code A – Approved | 2026-06-16 |  | Issue for construction | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0002
CTP-DHJ-GEO-DWG-0004 | Portal structure details | Drawing | Geotechnical | 1 | 2026-05-27 | TRN-01088 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-17 |  | Incorporate comments | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0004
CTP-DHJ-MEP-MST-0007 | Annulus grouting | Method Statement | MEP | A | 2026-05-27 | TRN-01132 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-16 |  | Incorporate comments | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0007
CTP-DHJ-MEP-MAT-0007 | Fire-rated cables | Material Submittal | MEP | 1 | 2026-05-28 | TRN-01168 | Meridian Engineering Partners | Code A – Approved | 2026-06-11 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0007
CTP-DHJ-CIV-DWG-0009 | Segment ring layout | Drawing | Civil | B | 2026-05-29 | TRN-01226 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-19 |  | Incorporate comments | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0009
CTP-DHJ-HSE-MST-0006 | TBM launching | Method Statement | HSE | 0 | 2026-05-30 | TRN-01077 | Meridian Engineering Partners | Code A – Approved | 2026-06-04 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0006
CTP-DHJ-TUN-RPT-0004 | Air quality monitoring | Inspection Report | Tunnelling | A | 2026-05-30 | TRN-01138 | Meridian Engineering Partners | Code A – Approved | 2026-06-19 |  | Issue for construction | \\DC\Tunnelling\Inspection Report\CTP-DHJ-TUN-RPT-0004
CTP-DHJ-GEO-MST-0003 | Cable pulling | Method Statement | Geotechnical | 1 | 2026-06-02 | TRN-01092 | Meridian Engineering Partners | Code A – Approved | 2026-06-15 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0003
CTP-DHJ-GEO-MAT-0002 | Ventilation fans | Material Submittal | Geotechnical | B | 2026-06-02 | TRN-01113 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-06-21 |  | Revise and resubmit | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0002
CTP-DHJ-HSE-DWG-0005 | Shaft general arrangement | Drawing | HSE | B | 2026-06-03 | TRN-01029 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-18 |  | Incorporate comments | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0005
CTP-DHJ-QAQ-PRC-0003 | Permit to work | Procedure | Quality | B | 2026-06-03 | TRN-01082 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-20 |  | Incorporate comments | \\DC\Quality\Procedure\CTP-DHJ-QAQ-PRC-0003
CTP-DHJ-CIV-CAL-0002 | Pump capacity | Calculation | Civil | A | 2026-06-06 | TRN-01209 | Meridian Engineering Partners | Code A – Approved | 2026-06-17 |  | Issue for construction | \\DC\Civil\Calculation\CTP-DHJ-CIV-CAL-0002
CTP-DHJ-CIV-PRC-0004 | Material receiving | Procedure | Civil | B | 2026-06-07 | TRN-01090 | Meridian Engineering Partners | Code A – Approved | 2026-06-27 |  | Issue for construction | \\DC\Civil\Procedure\CTP-DHJ-CIV-PRC-0004
CTP-DHJ-MEP-PRC-0004 | Emergency response plan | Procedure | MEP | B | 2026-06-07 | TRN-01233 | Meridian Engineering Partners | Code A – Approved | 2026-06-28 |  | Issue for construction | \\DC\MEP\Procedure\CTP-DHJ-MEP-PRC-0004
CTP-DHJ-QAQ-PRC-0001 | Document control procedure | Procedure | Quality | 1 | 2026-06-08 | TRN-01049 | Meridian Engineering Partners | Code A – Approved | 2026-06-19 |  | Issue for construction | \\DC\Quality\Procedure\CTP-DHJ-QAQ-PRC-0001
CTP-DHJ-TUN-DWG-0005 | Segment ring layout | Drawing | Tunnelling | 1 | 2026-06-08 | TRN-01085 | Meridian Engineering Partners | Code A – Approved | 2026-06-19 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0005
CTP-DHJ-GEO-MST-0004 | Cable pulling | Method Statement | Geotechnical | B | 2026-06-08 | TRN-01108 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-06-17 |  | Revise and resubmit | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0004
CTP-DHJ-CIV-MAT-0005 | Fire-rated cables | Material Submittal | Civil | A | 2026-06-09 | TRN-01048 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-06-16 |  | Revise and resubmit | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0005
CTP-DHJ-MEP-MST-0006 | Waterproofing installation | Method Statement | MEP | 0 | 2026-06-09 | TRN-01122 | Meridian Engineering Partners | Code A – Approved | 2026-06-18 |  | Issue for construction | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0006
CTP-DHJ-GEO-PRC-0001 | Permit to work | Procedure | Geotechnical | B | 2026-06-12 | TRN-01037 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-06-30 |  | Incorporate comments | \\DC\Geotechnical\Procedure\CTP-DHJ-GEO-PRC-0001
CTP-DHJ-GEO-MST-0005 | Shaft excavation | Method Statement | Geotechnical | 0 | 2026-06-12 | TRN-01131 | Meridian Engineering Partners | Code A – Approved | 2026-07-02 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0005
CTP-DHJ-MEP-MAT-0011 | Precast segment gaskets | Material Submittal | MEP | 0 | 2026-06-12 | TRN-01220 | Meridian Engineering Partners | Code A – Approved | 2026-06-24 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0011
CTP-DHJ-TUN-DWG-0014 | Portal structure details | Drawing | Tunnelling | 1 | 2026-06-12 | TRN-01228 | Meridian Engineering Partners | Code A – Approved | 2026-07-02 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0014
CTP-DHJ-CIV-RPT-0001 | Concrete cube results | Inspection Report | Civil | 0 | 2026-06-13 | TRN-01078 | Meridian Engineering Partners | Code A – Approved | 2026-06-30 |  | Issue for construction | \\DC\Civil\Inspection Report\CTP-DHJ-CIV-RPT-0001
CTP-DHJ-MEP-PRC-0002 | Permit to work | Procedure | MEP | B | 2026-06-14 | TRN-01061 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-06-27 |  | Revise and resubmit | \\DC\MEP\Procedure\CTP-DHJ-MEP-PRC-0002
CTP-DHJ-MEP-MST-0010 | TBM launching | Method Statement | MEP | B | 2026-06-15 | TRN-01184 | Meridian Engineering Partners | Code A – Approved | 2026-06-29 |  | Issue for construction | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0010
CTP-DHJ-GEO-DWG-0006 | Cross passage reinforcement | Drawing | Geotechnical | A | 2026-06-17 | TRN-01104 | Meridian Engineering Partners | Code A – Approved | 2026-06-25 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0006
CTP-DHJ-QAQ-DWG-0006 | Portal structure details | Drawing | Quality | B | 2026-06-17 | TRN-01121 | Meridian Engineering Partners | Code A – Approved | 2026-07-07 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0006
CTP-DHJ-GEO-DWG-0012 | Shaft general arrangement | Drawing | Geotechnical | 0 | 2026-06-17 | TRN-01199 | Meridian Engineering Partners | Code A – Approved | 2026-07-08 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0012
CTP-DHJ-MEP-MAT-0008 | Rebar 16 mm | Material Submittal | MEP | A | 2026-06-17 | TRN-01205 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-06-29 |  | Revise and resubmit | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0008
CTP-DHJ-TUN-MAT-0004 | Ventilation fans | Material Submittal | Tunnelling | 1 | 2026-06-18 | TRN-01091 | Meridian Engineering Partners | Code D – Rejected | 2026-07-02 |  | Prepare new submission | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0004
CTP-DHJ-TUN-DWG-0009 | Drainage layout | Drawing | Tunnelling | A | 2026-06-20 | TRN-01151 | Meridian Engineering Partners | Code A – Approved | 2026-07-05 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0009
CTP-DHJ-GEO-DWG-0005 | Portal structure details | Drawing | Geotechnical | 1 | 2026-06-22 | TRN-01099 | Meridian Engineering Partners | Code A – Approved | 2026-07-11 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0005
CTP-DHJ-TUN-MST-0004 | Cable pulling | Method Statement | Tunnelling | B | 2026-06-24 | TRN-01160 | Meridian Engineering Partners | Code D – Rejected | 2026-07-06 |  | Prepare new submission | \\DC\Tunnelling\Method Statement\CTP-DHJ-TUN-MST-0004
CTP-DHJ-QAQ-DWG-0010 | Shaft general arrangement | Drawing | Quality | B | 2026-06-24 | TRN-01219 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-07-05 |  | Incorporate comments | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0010
CTP-DHJ-QAQ-DWG-0002 | Drainage layout | Drawing | Quality | A | 2026-06-27 | TRN-01076 | Meridian Engineering Partners | Code A – Approved | 2026-07-12 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0002
CTP-DHJ-QAQ-DWG-0003 | Segment ring layout | Drawing | Quality | B | 2026-06-28 | TRN-01097 | Meridian Engineering Partners | Code A – Approved | 2026-07-06 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0003
CTP-DHJ-TUN-PRC-0001 | Document control procedure | Procedure | Tunnelling | 1 | 2026-06-29 | TRN-01009 | Meridian Engineering Partners | Code A – Approved | 2026-07-17 |  | Issue for construction | \\DC\Tunnelling\Procedure\CTP-DHJ-TUN-PRC-0001
CTP-DHJ-CIV-MST-0001 | Cable pulling | Method Statement | Civil | 1 | 2026-06-29 | TRN-01055 | Meridian Engineering Partners | Code A – Approved | 2026-07-19 |  | Issue for construction | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0001
CTP-DHJ-HSE-CAL-0001 | Pump capacity | Calculation | HSE | 0 | 2026-06-29 | TRN-01148 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-07-18 |  | Incorporate comments | \\DC\HSE\Calculation\CTP-DHJ-HSE-CAL-0001
CTP-DHJ-GEO-MAT-0007 | Grout admixture | Material Submittal | Geotechnical | B | 2026-06-29 | TRN-01211 | Meridian Engineering Partners | Code A – Approved | 2026-07-19 |  | Issue for construction | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0007
CTP-DHJ-GEO-DWG-0014 | Shaft general arrangement | Drawing | Geotechnical | B | 2026-06-30 | TRN-01234 | Meridian Engineering Partners | Code D – Rejected | 2026-07-11 |  | Prepare new submission | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0014
CTP-DHJ-MEP-DWG-0015 | Portal structure details | Drawing | MEP | B | 2026-07-01 | TRN-01218 | Meridian Engineering Partners | Code A – Approved | 2026-07-22 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0015
CTP-DHJ-HSE-MST-0003 | Annulus grouting | Method Statement | HSE | A | 2026-07-02 | TRN-01018 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-07-19 |  | Revise and resubmit | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0003
CTP-DHJ-GEO-DWG-0007 | Shaft general arrangement | Drawing | Geotechnical | B | 2026-07-02 | TRN-01106 | Meridian Engineering Partners | Code A – Approved | 2026-07-17 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0007
CTP-DHJ-HSE-DWG-0003 | Cross passage reinforcement | Drawing | HSE | B | 2026-07-04 | TRN-01022 | Meridian Engineering Partners | Code A – Approved | 2026-07-11 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0003
CTP-DHJ-HSE-MAT-0006 | Rebar 16 mm | Material Submittal | HSE | 0 | 2026-07-05 | TRN-01141 | Meridian Engineering Partners | Code A – Approved | 2026-07-20 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0006
CTP-DHJ-GEO-PRC-0004 | NCR handling | Procedure | Geotechnical | B | 2026-07-06 | TRN-01225 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-07-16 |  | Incorporate comments | \\DC\Geotechnical\Procedure\CTP-DHJ-GEO-PRC-0004
CTP-DHJ-TUN-DWG-0006 | Shaft general arrangement | Drawing | Tunnelling | B | 2026-07-07 | TRN-01101 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-07-20 |  | Revise and resubmit | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0006
CTP-DHJ-CIV-DWG-0005 | Segment ring layout | Drawing | Civil | B | 2026-07-07 | TRN-01103 | Meridian Engineering Partners | Code D – Rejected | 2026-07-13 |  | Prepare new submission | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0005
CTP-DHJ-HSE-DWG-0010 | Cross passage reinforcement | Drawing | HSE | B | 2026-07-07 | TRN-01157 | Meridian Engineering Partners | Code A – Approved | 2026-07-28 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0010
CTP-DHJ-CIV-MAT-0007 | Rebar 16 mm | Material Submittal | Civil | 0 | 2026-07-08 | TRN-01080 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-07-21 |  | Incorporate comments | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0007
CTP-DHJ-TUN-MAT-0002 | Fire-rated cables | Material Submittal | Tunnelling | 0 | 2026-07-10 | TRN-01079 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-07-17 |  | Incorporate comments | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0002
CTP-DHJ-CIV-MAT-0001 | Precast segment gaskets | Material Submittal | Civil | 0 | 2026-07-11 | TRN-01005 | Meridian Engineering Partners | Code A – Approved | 2026-07-31 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0001
CTP-DHJ-CIV-MAT-0003 | Fire-rated cables | Material Submittal | Civil | 0 | 2026-07-11 | TRN-01036 | Meridian Engineering Partners | Code A – Approved | 2026-07-30 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0003
CTP-DHJ-QAQ-DWG-0004 | Segment ring layout | Drawing | Quality | 0 | 2026-07-11 | TRN-01115 | Meridian Engineering Partners | Code A – Approved | 2026-07-27 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0004
CTP-DHJ-CIV-RPT-0002 | Monthly settlement monitoring | Inspection Report | Civil | B | 2026-07-11 | TRN-01118 | Meridian Engineering Partners | Code A – Approved | 2026-07-25 |  | Issue for construction | \\DC\Civil\Inspection Report\CTP-DHJ-CIV-RPT-0002
CTP-DHJ-GEO-MST-0006 | TBM launching | Method Statement | Geotechnical | B | 2026-07-12 | TRN-01166 | Meridian Engineering Partners | Code A – Approved | 2026-07-27 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0006
CTP-DHJ-HSE-RPT-0003 | Air quality monitoring | Inspection Report | HSE | 1 | 2026-07-13 | TRN-01058 | Meridian Engineering Partners | Code A – Approved | 2026-07-24 |  | Issue for construction | \\DC\HSE\Inspection Report\CTP-DHJ-HSE-RPT-0003
CTP-DHJ-HSE-MAT-0008 | Rebar 16 mm | Material Submittal | HSE | 0 | 2026-07-14 | TRN-01154 | Meridian Engineering Partners | Code A – Approved | 2026-07-25 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0008
CTP-DHJ-TUN-DWG-0011 | Drainage layout | Drawing | Tunnelling | 0 | 2026-07-21 | TRN-01192 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-05 |  | Incorporate comments | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0011
CTP-DHJ-QAQ-DWG-0009 | Segment ring layout | Drawing | Quality | B | 2026-07-22 | TRN-01182 | Meridian Engineering Partners | Code A – Approved | 2026-08-02 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0009
CTP-DHJ-QAQ-MAT-0003 | Grout admixture | Material Submittal | Quality | B | 2026-07-23 | TRN-01102 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-05 |  | Incorporate comments | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0003
CTP-DHJ-HSE-MAT-0005 | Rebar 16 mm | Material Submittal | HSE | A | 2026-07-23 | TRN-01117 | Meridian Engineering Partners | Code A – Approved | 2026-08-11 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0005
CTP-DHJ-GEO-MST-0008 | Waterproofing installation | Method Statement | Geotechnical | B | 2026-07-23 | TRN-01230 | Meridian Engineering Partners | Code A – Approved | 2026-08-12 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0008
CTP-DHJ-CIV-MAT-0008 | Grout admixture | Material Submittal | Civil | A | 2026-07-25 | TRN-01137 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-05 |  | Incorporate comments | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0008
CTP-DHJ-TUN-RPT-0002 | Concrete cube results | Inspection Report | Tunnelling | 0 | 2026-07-27 | TRN-01095 | Meridian Engineering Partners | Code D – Rejected | 2026-08-03 |  | Prepare new submission | \\DC\Tunnelling\Inspection Report\CTP-DHJ-TUN-RPT-0002
CTP-DHJ-MEP-MST-0005 | Waterproofing installation | Method Statement | MEP | B | 2026-07-28 | TRN-01116 | Meridian Engineering Partners | Code A – Approved | 2026-08-13 |  | Issue for construction | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0005
CTP-DHJ-CIV-DWG-0007 | Cross passage reinforcement | Drawing | Civil | 1 | 2026-07-29 | TRN-01130 | Meridian Engineering Partners | Code A – Approved | 2026-08-19 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0007
CTP-DHJ-QAQ-DWG-0007 | Cross passage reinforcement | Drawing | Quality | 0 | 2026-07-29 | TRN-01139 | Meridian Engineering Partners | Code A – Approved | 2026-08-03 |  | Issue for construction | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0007
CTP-DHJ-MEP-MST-0008 | TBM launching | Method Statement | MEP | A | 2026-07-30 | TRN-01150 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-11 |  | Incorporate comments | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0008
CTP-DHJ-CIV-DWG-0001 | Drainage layout | Drawing | Civil | 1 | 2026-08-01 | TRN-01004 | Meridian Engineering Partners | Code A – Approved | 2026-08-16 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0001
CTP-DHJ-GEO-PRC-0002 | Permit to work | Procedure | Geotechnical | B | 2026-08-02 | TRN-01069 | Meridian Engineering Partners | Code A – Approved | 2026-08-13 |  | Issue for construction | \\DC\Geotechnical\Procedure\CTP-DHJ-GEO-PRC-0002
CTP-DHJ-TUN-DWG-0012 | Drainage layout | Drawing | Tunnelling | 1 | 2026-08-03 | TRN-01197 | Meridian Engineering Partners | Code A – Approved | 2026-08-24 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0012
CTP-DHJ-HSE-DWG-0007 | Shaft general arrangement | Drawing | HSE | B | 2026-08-04 | TRN-01068 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-16 |  | Incorporate comments | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0007
CTP-DHJ-TUN-RPT-0005 | Survey control check | Inspection Report | Tunnelling | 0 | 2026-08-04 | TRN-01156 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-18 |  | Incorporate comments | \\DC\Tunnelling\Inspection Report\CTP-DHJ-TUN-RPT-0005
CTP-DHJ-GEO-DWG-0013 | Drainage layout | Drawing | Geotechnical | A | 2026-08-04 | TRN-01221 | Meridian Engineering Partners | Code A – Approved | 2026-08-09 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0013
CTP-DHJ-MEP-MAT-0012 | Fire-rated cables | Material Submittal | MEP | 0 | 2026-08-04 | TRN-01232 | Meridian Engineering Partners | Code A – Approved | 2026-08-11 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0012
CTP-DHJ-HSE-MAT-0004 | Ventilation fans | Material Submittal | HSE | B | 2026-08-05 | TRN-01067 | Meridian Engineering Partners | Code A – Approved | 2026-08-16 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0004
CTP-DHJ-MEP-DWG-0005 | Segment ring layout | Drawing | MEP | 0 | 2026-08-06 | TRN-01063 | Meridian Engineering Partners | Code A – Approved | 2026-08-15 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0005
CTP-DHJ-CIV-DWG-0008 | Cross passage reinforcement | Drawing | Civil | B | 2026-08-07 | TRN-01149 | Meridian Engineering Partners | Code A – Approved | 2026-08-17 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0008
CTP-DHJ-MEP-DWG-0009 | Cross passage reinforcement | Drawing | MEP | 1 | 2026-08-07 | TRN-01153 | Meridian Engineering Partners | Code A – Approved | 2026-08-22 |  | Issue for construction | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0009
CTP-DHJ-TUN-CAL-0004 | Pump capacity | Calculation | Tunnelling | 1 | 2026-08-07 | TRN-01191 | Meridian Engineering Partners | Code A – Approved | 2026-08-12 |  | Issue for construction | \\DC\Tunnelling\Calculation\CTP-DHJ-TUN-CAL-0004
CTP-DHJ-TUN-MAT-0007 | Grout admixture | Material Submittal | Tunnelling | A | 2026-08-08 | TRN-01158 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-17 |  | Incorporate comments | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0007
CTP-DHJ-QAQ-RPT-0001 | Survey control check | Inspection Report | Quality | 1 | 2026-08-10 | TRN-01002 | Meridian Engineering Partners | Code A – Approved | 2026-08-29 |  | Issue for construction | \\DC\Quality\Inspection Report\CTP-DHJ-QAQ-RPT-0001
CTP-DHJ-HSE-DWG-0002 | Portal structure details | Drawing | HSE | 0 | 2026-08-10 | TRN-01017 | Meridian Engineering Partners | Code A – Approved | 2026-08-26 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0002
CTP-DHJ-CIV-DWG-0006 | Cross passage reinforcement | Drawing | Civil | B | 2026-08-10 | TRN-01126 | Meridian Engineering Partners | Code A – Approved | 2026-08-25 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0006
CTP-DHJ-TUN-RPT-0001 | Air quality monitoring | Inspection Report | Tunnelling | A | 2026-08-11 | TRN-01089 | Meridian Engineering Partners | Code A – Approved | 2026-08-17 |  | Issue for construction | \\DC\Tunnelling\Inspection Report\CTP-DHJ-TUN-RPT-0001
CTP-DHJ-HSE-DWG-0001 | Cross passage reinforcement | Drawing | HSE | A | 2026-08-12 | TRN-01015 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-21 |  | Incorporate comments | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0001
CTP-DHJ-GEO-MAT-0003 | Fire-rated cables | Material Submittal | Geotechnical | B | 2026-08-13 | TRN-01128 | Meridian Engineering Partners | Code A – Approved | 2026-08-19 |  | Issue for construction | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0003
CTP-DHJ-CIV-PRC-0005 | NCR handling | Procedure | Civil | B | 2026-08-13 | TRN-01152 | Meridian Engineering Partners | Code A – Approved | 2026-08-30 |  | Issue for construction | \\DC\Civil\Procedure\CTP-DHJ-CIV-PRC-0005
CTP-DHJ-CIV-RPT-0004 | Monthly settlement monitoring | Inspection Report | Civil | A | 2026-08-14 | TRN-01176 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-21 |  | Incorporate comments | \\DC\Civil\Inspection Report\CTP-DHJ-CIV-RPT-0004
CTP-DHJ-MEP-MAT-0001 | Rebar 16 mm | Material Submittal | MEP | A | 2026-08-15 | TRN-01006 | Meridian Engineering Partners | Code A – Approved | 2026-08-28 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0001
CTP-DHJ-HSE-DWG-0004 | Cross passage reinforcement | Drawing | HSE | A | 2026-08-15 | TRN-01023 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-08-28 |  | Revise and resubmit | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0004
CTP-DHJ-HSE-DWG-0006 | Cross passage reinforcement | Drawing | HSE | 0 | 2026-08-15 | TRN-01045 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-22 |  | Incorporate comments | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0006
CTP-DHJ-HSE-MST-0004 | Shaft excavation | Method Statement | HSE | B | 2026-08-15 | TRN-01050 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-03 |  | Revise and resubmit | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0004
CTP-DHJ-TUN-RPT-0003 | Weld inspection | Inspection Report | Tunnelling | A | 2026-08-16 | TRN-01134 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-05 |  | Revise and resubmit | \\DC\Tunnelling\Inspection Report\CTP-DHJ-TUN-RPT-0003
CTP-DHJ-HSE-MAT-0002 | Precast segment gaskets | Material Submittal | HSE | A | 2026-08-17 | TRN-01031 | Meridian Engineering Partners | Code A – Approved | 2026-08-24 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0002
CTP-DHJ-GEO-DWG-0003 | Portal structure details | Drawing | Geotechnical | B | 2026-08-18 | TRN-01084 | Meridian Engineering Partners | Code A – Approved | 2026-09-04 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0003
CTP-DHJ-TUN-MAT-0006 | Fire-rated cables | Material Submittal | Tunnelling | 1 | 2026-08-18 | TRN-01143 | Meridian Engineering Partners | Code A – Approved | 2026-08-26 |  | Issue for construction | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0006
CTP-DHJ-CIV-MAT-0010 | Rebar 16 mm | Material Submittal | Civil | 0 | 2026-08-19 | TRN-01194 | Meridian Engineering Partners | Code A – Approved | 2026-08-31 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0010
CTP-DHJ-HSE-DWG-0008 | Cross passage reinforcement | Drawing | HSE | B | 2026-08-22 | TRN-01100 | Meridian Engineering Partners | Code A – Approved | 2026-09-05 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0008
CTP-DHJ-MEP-DWG-0013 | Shaft general arrangement | Drawing | MEP | 1 | 2026-08-24 | TRN-01201 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-08-30 |  | Incorporate comments | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0013
CTP-DHJ-MEP-MST-0009 | Shaft excavation | Method Statement | MEP | A | 2026-08-26 | TRN-01159 | Meridian Engineering Partners | Code A – Approved | 2026-09-11 |  | Issue for construction | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0009
CTP-DHJ-GEO-MST-0007 | Waterproofing installation | Method Statement | Geotechnical | A | 2026-08-26 | TRN-01202 | Meridian Engineering Partners | Code A – Approved | 2026-09-04 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0007
CTP-DHJ-GEO-MST-0001 | Cable pulling | Method Statement | Geotechnical | A | 2026-08-27 | TRN-01027 | Meridian Engineering Partners | Code A – Approved | 2026-09-01 |  | Issue for construction | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0001
CTP-DHJ-CIV-DWG-0003 | Drainage layout | Drawing | Civil | 1 | 2026-08-27 | TRN-01066 | Meridian Engineering Partners | Code A – Approved | 2026-09-01 |  | Issue for construction | \\DC\Civil\Drawing\CTP-DHJ-CIV-DWG-0003
CTP-DHJ-CIV-MST-0005 | Annulus grouting | Method Statement | Civil | B | 2026-08-30 | TRN-01135 | Meridian Engineering Partners | Code A – Approved | 2026-09-17 |  | Issue for construction | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0005
CTP-DHJ-MEP-DWG-0008 | Portal structure details | Drawing | MEP | B | 2026-08-30 | TRN-01144 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-13 |  | Incorporate comments | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0008
CTP-DHJ-HSE-DWG-0012 | Shaft general arrangement | Drawing | HSE | 1 | 2026-08-30 | TRN-01196 | Meridian Engineering Partners | Code A – Approved | 2026-09-09 |  | Issue for construction | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0012
CTP-DHJ-GEO-MST-0002 | TBM launching | Method Statement | Geotechnical | B | 2026-08-31 | TRN-01041 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-15 |  | Revise and resubmit | \\DC\Geotechnical\Method Statement\CTP-DHJ-GEO-MST-0002
CTP-DHJ-QAQ-PRC-0004 | Permit to work | Procedure | Quality | A | 2026-08-31 | TRN-01093 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-05 |  | Incorporate comments | \\DC\Quality\Procedure\CTP-DHJ-QAQ-PRC-0004
CTP-DHJ-TUN-MAT-0009 | Fire-rated cables | Material Submittal | Tunnelling | B | 2026-09-01 | TRN-01167 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-18 |  | Incorporate comments | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0009
CTP-DHJ-GEO-MAT-0005 | Grout admixture | Material Submittal | Geotechnical | B | 2026-09-02 | TRN-01183 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-20 |  | Revise and resubmit | \\DC\Geotechnical\Material Submittal\CTP-DHJ-GEO-MAT-0005
CTP-DHJ-QAQ-PRC-0002 | Emergency response plan | Procedure | Quality | 1 | 2026-09-07 | TRN-01081 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-16 |  | Incorporate comments | \\DC\Quality\Procedure\CTP-DHJ-QAQ-PRC-0002
CTP-DHJ-CIV-PRC-0001 | NCR handling | Procedure | Civil | 0 | 2026-09-08 | TRN-01024 | Meridian Engineering Partners | Code A – Approved | 2026-09-26 |  | Issue for construction | \\DC\Civil\Procedure\CTP-DHJ-CIV-PRC-0001
CTP-DHJ-HSE-MAT-0007 | Ventilation fans | Material Submittal | HSE | 0 | 2026-09-08 | TRN-01146 | Meridian Engineering Partners | Code A – Approved | 2026-09-25 |  | Issue for construction | \\DC\HSE\Material Submittal\CTP-DHJ-HSE-MAT-0007
CTP-DHJ-TUN-MAT-0005 | Ventilation fans | Material Submittal | Tunnelling | B | 2026-09-10 | TRN-01105 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0005
CTP-DHJ-TUN-CAL-0003 | Lifting plan | Calculation | Tunnelling | 0 | 2026-09-11 | TRN-01056 | Meridian Engineering Partners | Code A – Approved | 2026-09-21 |  | Issue for construction | \\DC\Tunnelling\Calculation\CTP-DHJ-TUN-CAL-0003
CTP-DHJ-QAQ-MAT-0001 | Fire-rated cables | Material Submittal | Quality | B | 2026-09-11 | TRN-01073 | Meridian Engineering Partners | Code D – Rejected | 2026-09-18 |  | Prepare new submission | \\DC\Quality\Material Submittal\CTP-DHJ-QAQ-MAT-0001
CTP-DHJ-HSE-DWG-0009 | Portal structure details | Drawing | HSE | B | 2026-09-11 | TRN-01109 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-27 |  | Revise and resubmit | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0009
CTP-DHJ-TUN-DWG-0004 | Cross passage reinforcement | Drawing | Tunnelling | 1 | 2026-09-12 | TRN-01074 | Meridian Engineering Partners | Code A – Approved | 2026-09-21 |  | Issue for construction | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0004
CTP-DHJ-QAQ-DWG-0001 | Drainage layout | Drawing | Quality | A | 2026-09-13 | TRN-01013 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-30 |  | Incorporate comments | \\DC\Quality\Drawing\CTP-DHJ-QAQ-DWG-0001
CTP-DHJ-TUN-MST-0001 | TBM launching | Method Statement | Tunnelling | B | 2026-09-14 | TRN-01016 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-09-21 |  | Revise and resubmit | \\DC\Tunnelling\Method Statement\CTP-DHJ-TUN-MST-0001
CTP-DHJ-CIV-MAT-0002 | Precast segment gaskets | Material Submittal | Civil | 0 | 2026-09-16 | TRN-01010 | Meridian Engineering Partners | Code A – Approved | 2026-10-01 |  | Issue for construction | \\DC\Civil\Material Submittal\CTP-DHJ-CIV-MAT-0002
CTP-DHJ-QAQ-MST-0001 | Annulus grouting | Method Statement | Quality | 1 | 2026-09-19 | TRN-01043 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-10-08 |  | Incorporate comments | \\DC\Quality\Method Statement\CTP-DHJ-QAQ-MST-0001
CTP-DHJ-HSE-MST-0002 | Cable pulling | Method Statement | HSE | B | 2026-09-20 | TRN-01001 | Meridian Engineering Partners | Code A – Approved | 2026-09-27 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0002
CTP-DHJ-CIV-MST-0008 | Annulus grouting | Method Statement | Civil | B | 2026-09-20 | TRN-01210 | Meridian Engineering Partners | Code A – Approved | 2026-10-07 |  | Issue for construction | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0008
CTP-DHJ-QAQ-RPT-0002 | Concrete cube results | Inspection Report | Quality | A | 2026-09-20 | TRN-01237 | Meridian Engineering Partners | Code A – Approved | 2026-10-05 |  | Issue for construction | \\DC\Quality\Inspection Report\CTP-DHJ-QAQ-RPT-0002
CTP-DHJ-TUN-MAT-0003 | Ventilation fans | Material Submittal | Tunnelling | A | 2026-09-21 | TRN-01083 | Meridian Engineering Partners | Code A – Approved | 2026-10-07 |  | Issue for construction | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0003
CTP-DHJ-MEP-DWG-0007 | Cross passage reinforcement | Drawing | MEP | A | 2026-09-21 | TRN-01129 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0007
CTP-DHJ-HSE-PRC-0001 | Document control procedure | Procedure | HSE | A | 2026-09-22 | TRN-01060 | Meridian Engineering Partners | Code A – Approved | 2026-10-02 |  | Issue for construction | \\DC\HSE\Procedure\CTP-DHJ-HSE-PRC-0001
CTP-DHJ-TUN-MST-0003 | Annulus grouting | Method Statement | Tunnelling | 1 | 2026-09-22 | TRN-01125 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Tunnelling\Method Statement\CTP-DHJ-TUN-MST-0003
CTP-DHJ-GEO-RPT-0003 | Concrete cube results | Inspection Report | Geotechnical | A | 2026-09-22 | TRN-01186 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-10-06 |  | Revise and resubmit | \\DC\Geotechnical\Inspection Report\CTP-DHJ-GEO-RPT-0003
CTP-DHJ-MEP-RPT-0006 | Air quality monitoring | Inspection Report | MEP | 0 | 2026-09-22 | TRN-01227 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-09-27 |  | Incorporate comments | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0006
CTP-DHJ-MEP-MAT-0013 | Ventilation fans | Material Submittal | MEP | 0 | 2026-09-23 | TRN-01239 | Meridian Engineering Partners | Code A – Approved | 2026-10-09 |  | Issue for construction | \\DC\MEP\Material Submittal\CTP-DHJ-MEP-MAT-0013
CTP-DHJ-CIV-PRC-0002 | Material receiving | Procedure | Civil | A | 2026-09-24 | TRN-01054 | Meridian Engineering Partners | Code A – Approved | 2026-10-04 |  | Issue for construction | \\DC\Civil\Procedure\CTP-DHJ-CIV-PRC-0002
CTP-DHJ-TUN-MAT-0008 | Grout admixture | Material Submittal | Tunnelling | 0 | 2026-09-28 | TRN-01162 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Tunnelling\Material Submittal\CTP-DHJ-TUN-MAT-0008
CTP-DHJ-GEO-RPT-0002 | Monthly settlement monitoring | Inspection Report | Geotechnical | A | 2026-09-29 | TRN-01163 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-10-14 |  | Incorporate comments | \\DC\Geotechnical\Inspection Report\CTP-DHJ-GEO-RPT-0002
CTP-DHJ-MEP-MST-0003 | Waterproofing installation | Method Statement | MEP | B | 2026-09-30 | TRN-01071 | Meridian Engineering Partners | Code D – Rejected | 2026-10-11 |  | Prepare new submission | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0003
CTP-DHJ-MEP-RPT-0002 | Survey control check | Inspection Report | MEP | 1 | 2026-09-30 | TRN-01124 | Meridian Engineering Partners | Code A – Approved | 2026-10-05 |  | Issue for construction | \\DC\MEP\Inspection Report\CTP-DHJ-MEP-RPT-0002
CTP-DHJ-MEP-MST-0002 | Shaft excavation | Method Statement | MEP | A | 2026-10-01 | TRN-01033 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\MEP\Method Statement\CTP-DHJ-MEP-MST-0002
CTP-DHJ-GEO-DWG-0001 | Cross passage reinforcement | Drawing | Geotechnical | A | 2026-10-01 | TRN-01039 | Meridian Engineering Partners | Code A – Approved | 2026-10-14 |  | Issue for construction | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0001
CTP-DHJ-CIV-MST-0003 | Waterproofing installation | Method Statement | Civil | B | 2026-10-01 | TRN-01107 | Meridian Engineering Partners | Code C – Revise & Resubmit | 2026-10-12 |  | Revise and resubmit | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0003
CTP-DHJ-MEP-PRC-0003 | Material receiving | Procedure | MEP | 1 | 2026-10-01 | TRN-01169 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-10-09 |  | Incorporate comments | \\DC\MEP\Procedure\CTP-DHJ-MEP-PRC-0003
CTP-DHJ-MEP-DWG-0017 | Portal structure details | Drawing | MEP | A | 2026-10-04 | TRN-01236 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0017
CTP-DHJ-CIV-MST-0007 | Shaft excavation | Method Statement | Civil | 1 | 2026-10-05 | TRN-01195 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Civil\Method Statement\CTP-DHJ-CIV-MST-0007
CTP-DHJ-HSE-DWG-0013 | Segment ring layout | Drawing | HSE | 1 | 2026-10-05 | TRN-01206 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\HSE\Drawing\CTP-DHJ-HSE-DWG-0013
CTP-DHJ-HSE-MST-0001 | Cable pulling | Method Statement | HSE | B | 2026-10-06 | TRN-01000 | Meridian Engineering Partners | Code A – Approved | 2026-10-14 |  | Issue for construction | \\DC\HSE\Method Statement\CTP-DHJ-HSE-MST-0001
CTP-DHJ-TUN-DWG-0008 | Shaft general arrangement | Drawing | Tunnelling | B | 2026-10-06 | TRN-01145 | Meridian Engineering Partners | Code B – Approved with Comments | 2026-10-14 |  | Incorporate comments | \\DC\Tunnelling\Drawing\CTP-DHJ-TUN-DWG-0008
CTP-DHJ-GEO-RPT-0001 | Survey control check | Inspection Report | Geotechnical | 0 | 2026-10-10 | TRN-01042 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Geotechnical\Inspection Report\CTP-DHJ-GEO-RPT-0001
CTP-DHJ-QAQ-CAL-0001 | Lifting plan | Calculation | Quality | 1 | 2026-10-10 | TRN-01175 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Quality\Calculation\CTP-DHJ-QAQ-CAL-0001
CTP-DHJ-GEO-DWG-0009 | Cross passage reinforcement | Drawing | Geotechnical | A | 2026-10-12 | TRN-01172 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Geotechnical\Drawing\CTP-DHJ-GEO-DWG-0009
CTP-DHJ-CIV-PRC-0003 | Emergency response plan | Procedure | Civil | A | 2026-10-14 | TRN-01070 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\Civil\Procedure\CTP-DHJ-CIV-PRC-0003
CTP-DHJ-MEP-DWG-0014 | Drainage layout | Drawing | MEP | A | 2026-10-14 | TRN-01204 | Meridian Engineering Partners | Under Review |  |  | Follow up with consultant | \\DC\MEP\Drawing\CTP-DHJ-MEP-DWG-0014
Formulas:
Days in Review = IF([Response]="",TODAY()-[Submitted],[Response]-[Submitted])