## Slide 1: Executive Office Approval Workflows
PROCESS PLAYBOOK · DESERT HORIZON JV
How PR/PO, IPC, contract and client-letter approvals move through Oracle Fusion, DocuSign and Aconex
Oracle Fusion
DocuSign
Aconex
Prepared by the Executive Office · Version 1.0 · Demo data

## Slide 2: Three systems, one approval chain
Oracle Fusion
RAISE & APPROVE
Purchase requisitions and POs
Budget and cost-code checks
Supplier invoices and payments
DocuSign
SIGN & CERTIFY
Contracts and subcontracts
IPC certificates
Outgoing letters for signature
Aconex
ISSUE & RECORD
Transmittals to client and consultant
Incoming correspondence register
Signed copies as the record
Golden rule Nothing is treated as issued until the signed copy is uploaded and transmitted in Aconex.

## Slide 3: Workflow 1 – Purchase requisition to PO
1
Requester
Raises PR with specs and cost code
Oracle
SLA Day 0
2
Dept Manager
Reviews need and quantity
Oracle
SLA 1 day
3
Procurement
Collects 3 quotes, recommends supplier
Oracle
SLA 3 days
4
Cost Control
Confirms budget line and balance
Oracle
SLA 1 day
5
Project Director
Final approval per authority matrix
Oracle
SLA 1 day
6
Procurement
Issues PO and sends to supplier
Oracle + email
SLA 1 day
Executive Office role: track PRs waiting at Project Director level, chase anything older than 24 hours, and flag urgent site requests in the daily approval list.

## Slide 4: Workflow 2 – Subcontractor IPC certification
Subcontractor & site
Commercial
Executive & finance
1 Application submitted in Aconex
2 Site measurement verified by CM
3 QS valuation & deductions
4 Commercial Manager review
5 PD signs IPC in DocuSign
6 Finance books in Oracle & pays

## Slide 5: Workflow 3 – Contracts & subcontract agreements
1
Draft agreed
Commercial team finalises terms with the subcontractor
2
Legal review
Contracts & Legal confirm clauses and securities
3
Envelope prepared
Executive Office builds DocuSign envelope and signing order
4
Signatures
Subcontractor signs first, then Project Director
5
Filed & issued
Signed PDF uploaded to Aconex and Oracle contract record
Checklist before sending to DocuSign
Final version matches the approved draft
Signatory names and emails verified
Signing order: counterparty first
Annexures attached in correct order
Contract number taken from register
Reminder set every 2 days

## Slide 6: Workflow 4 – Outgoing letters to the client
01
Draft
Originator drafts on the approved letter template
02
Technical check
Discipline lead confirms facts and references
03
Reference number
Document Control issues the next letter number
04
Signature
Project Director signs via DocuSign
05
Transmit
Uploaded to Aconex as a formal transmittal
06
Track reply
Response due date logged and chased

## Slide 7: Approval authority matrix
Document | Band A · up to SAR 100K | Band B · up to SAR 1M | Band C · above SAR 1M | Final signatory
Purchase order | Dept Manager | Procurement Mgr | Project Director | Project Director
Subcontractor IPC | Construction Mgr | Commercial Mgr | Project Director | Project Director
Subcontract agreement | Commercial Mgr | Legal | Project Director | PD + JV Board rep
Client letter | Discipline Lead | Project Manager | Project Director | Project Director
Variation claim | QS Lead | Commercial Mgr | Project Director | PD + JV Board rep
Staff travel / expense | Line Manager | HR Manager | Project Director | Finance Manager
Demo thresholds for illustration only. Each level must approve before the next one sees the item.

## Slide 8: Turnaround: target vs actual
Chart: Average working days, Jan–Jun 2026 (demo)
| PR to PO | IPC | Subcontract | Client letter
Target (days) | 7 | 10 | 12 | 3
Actual (days) | 6.2 | 11.5 | 9.8 | 2.4
3 of 4
workflows ahead of target
+1.5 days
IPC over target – QS backlog
98%
letters sent with a tracked reply date

## Slide 9: Monthly approval volume
Chart: Items approved per month, 2026 (demo)
| Jan | Feb | Mar | Apr | May | Jun
Purchase orders | 42 | 38 | 51 | 47 | 55 | 49
IPCs | 12 | 14 | 13 | 16 | 15 | 18
Contracts | 4 | 6 | 3 | 5 | 7 | 4
Client letters | 26 | 22 | 31 | 28 | 34 | 30

## Slide 10: Common delays and how the office fixes them
DELAY
FIX
Approver travelling or on leave
Delegation of authority set in Oracle and DocuSign before travel
Wrong cost code on PR
Cost Control check moved before Project Director approval
DocuSign envelope ignored
Automatic reminders every 2 days plus a call on day 4
Letter sent without reply date
Aconex mail type set to 'reply required' with due date

## Slide 11: Five rules the Executive Office follows
1
One daily approval list sent to the Project Director by 08:00
2
Nothing waits more than 24 hours without a follow-up
3
Every signed document is filed in Aconex the same day
4
Reference numbers only from the official register
5
Weekly turnaround report shared every Sunday