## Slide 1: VIP Visit & TBM Breakthrough Ceremony
EVENT PLAN · COASTAL TUNNEL PACKAGE – LOT 3
Run-of-show, guest protocol, site access, transport and hospitality plan for the Al-Noor TBM breakthrough
Thu, 19 Nov 2026
North Portal Shaft, Site Camp 2
Prepared by Executive Office
Notes: Event plan for the VIP visit and TBM breakthrough ceremony. All names, companies and figures are fictional demo data.

## Slide 2: Event at a glance
120
Invited guests
14
VIP delegates
4 h 15 m
Gate-in to departure
22
Vehicles in movement plan
Objective
Celebrate the Al-Noor TBM breakthrough at the North Portal with the client leadership, deliver a safe and seamless VIP experience, and capture high-quality media for project communications.
Zero safety incidents
Program runs within 10 minutes of schedule
All guests accredited before entering Zone C
Key details
Chief guest
H.E. Faisal Al-Rashidi, CEO, CGDA
Host
Project Director, Desert Horizon JV
Consultant
Meridian Engineering Partners
Venue
North Portal Shaft, Site Camp 2
Dress code
Formal / national dress + full PPE
Media
Accredited press only, embargo till 14:00

## Slide 3: Run of show – ceremony day
08:30
Advance team on site
Security sweep, PPE and badges staged
09:15
VIP convoy departs
From Gateway Tower HQ, lead car + 6 vehicles
09:45
Arrival & accreditation
North Portal gate, wristbands issued
10:00
Welcome tea
VIP majlis tent, Arabic coffee and dates
10:20
Safety induction
5-minute briefing by HSE Manager
10:30
Project briefing
Project Director, progress and milestones
10:50
Move to viewing platform
Escorted in groups of 20
11:05
Breakthrough moment
TBM cutterhead emerges, plaque unveiling
11:25
Group photo & media
Statements by client and JV leadership
11:45
Lunch & departure
Hospitality tent, convoy departs 12:45

## Slide 4: Guest list by protocol tier
Tier | Group | Pax | Who | Escort / host | Seating
T1 | VIP delegation | 14 | CGDA CEO, board members | Project Director | Front row
T2 | Client & consultant | 28 | CGDA PMO, Meridian Engineering | Project Manager | Rows 2–4
T3 | JV partners & subs | 36 | JV leadership, key subcontractors | Construction Mgr | Rows 5–8
T4 | Media | 8 | Accredited press, in-house media | Comms Lead | Media riser
T5 | Workforce reps | 34 | TBM crew, HSE champions | Tunnel Manager | Standing area
Total |  | 120 | Final list frozen T-3; changes only via Executive Office |  | 
Chart: Guest mix
| T1 VIP | T2 Client | T3 JV | T4 Media | T5 Workforce
Guests | 14 | 28 | 36 | 8 | 34
T1 VIP
T2 Client
T3 JV
T4 Media
T5 Workforce

## Slide 5: Site access & security zones
ZONE A
Gate & vehicle check
Security screening, vehicle pass check, convoy holding bay
ZONE B
Accreditation desk
Badge and wristband issue, PPE kit, master list check
ZONE C
VIP majlis tent
Holding area, welcome tea, safety induction
ZONE D
TBM viewing platform
Escorted only, max 40 at a time, full PPE
Wristband colour code
Gold
VIP delegation
Teal
Client & consultant
Sand
JV & subcontractors
Rust
Media
No entry beyond Zone C without escort and full PPE
Drones and photography restricted to accredited media
Single entry gate; all other site gates closed 09:00–13:00

## Slide 6: Transport & movement plan
Ref | Role | Vehicle | Passengers | Driver | Depart
V-01 | Lead car | SUV | Security escort | Khalid M. | 09:10
V-02 | VIP 1 | Executive sedan | Chief guest + aide | Rashed K. | 09:15
V-03 | VIP 2 | Executive sedan | Board members (2) | Tariq A. | 09:15
V-04 | VIP 3 | Executive SUV | Board members (3) | Nabeel S. | 09:15
V-05 | Host car | Executive SUV | Project Director | Omar F. | 09:00
V-06 | Standby | Executive sedan | Backup, engine on | Hamza R. | 09:15
B-01–03 | Coasters | 30-seat bus | Guests T2–T3 | Fleet pool | 09:00
Movement notes
Pick-up: Gateway Tower, Gate 2
Drive time: approx. 30 min
Convoy speed: max 80 km/h, no overtaking
Drop-off: Zone A holding bay, VIPs walked to Zone B
Radio: Channel 4, call-sign PORTAL
Rehearsal: dry run T-1 at 09:15

## Slide 7: Catering & hospitality
Arrival welcome
Arabic coffee, dates, chilled water and fresh juices served at the majlis tent from 09:45.
Lunch service
Buffet for 130 covers with vegetarian and light options; VIP table served separately.
Gifts & memorabilia
Commemorative plaque, framed breakthrough photo and branded gift bags for T1–T2 guests.
Media & photography
Two photographers, one videographer, live feed screen in the tent and a group photo set-up.

## Slide 8: Roles & responsibilities
Workstream | Lead | Key deliverables
Overall coordination | Executive Office (EA to PD) | Master plan, run-of-show, daily status
Protocol & guest list | Executive Office | Invitations, RSVPs, seating, name cards
Security & access | Security Manager – Adel N. | Gate control, badges, wristbands, sweep
Transport | Fleet Supervisor – Imad Q. | Convoy, drivers, buses, standby car
HSE & PPE | HSE Manager – Liam O. | Induction, PPE kits, paramedic, heat plan
Catering & tent | Admin & Camp Services | Tent, cooling, power, coffee, lunch
Media | Comms Lead – Sara D. | Photo, video, press, live feed
TBM operation | Tunnel Manager – Viktor P. | Breakthrough timing, platform safety

## Slide 9: Readiness countdown
T-14
Guest list approved
Invitations issued
Tent & cooling booked
T-7
RSVPs chased
Convoy & drivers fixed
Gifts and plaque ready
T-3
Guest list frozen
Badges printed
Media brief sent
T-1
Full dry run 09:15
Site walkdown 15:00
Final brief to all leads
D-Day
Sweep by 08:30
Live status every 15 min
Close-out report by 18:00

## Slide 10: Risks & contingency plan
Risk | Rating | Mitigation | Owner
Extreme heat at midday | High | Shaded cooled tent, water stations, program ends before 12:00 on platform | HSE
VIP arrival delayed | Medium | 15-min buffer, flexible briefing length, live convoy updates | Exec Office
TBM breakthrough slips | Medium | Cutterhead held 1 m short till cue; rehearsed fallback with live feed | Tunnel Mgr
Guest not on master list | Low | Accreditation desk with escalation to Executive Office | Security
Medical incident | Low | Paramedic and ambulance on standby at Zone A | HSE

## Slide 11: Command centre & contacts
Event Coordinator
Executive Office
+966 50 000 1101
Security Control
Gate A – Radio Ch. 4
+966 50 000 1102
HSE & Medical
Paramedic post, Zone A
+966 50 000 1103
One plan. One team. One moment.
Final site walkdown: Wednesday 18 Nov 2026, 15:00 at North Portal. All workstream leads to attend with their checklists.