## Dashboard
WIR Status Dashboard
Coastal Tunnel Package (CTP) • Desert Horizon JV • Consultant: Meridian Engineering Partners • Demo data
TOTAL WIRs |  |  | APPROVED |  |  | PENDING |  | OVERDUE
Submitted since July |  |  | Including approved with comments |  |  | Awaiting consultant response |  | Pending more than 3 days
STATUS BY DISCIPLINE | [6 empty] | MIX BY DISCIPLINE
Discipline | Approved | With Comments | Rejected | Pending | Total | Approval %
Geotechnical
Civil
Tunnelling
MEP
Survey
Total
MONTHLY SUBMISSIONS | [6 empty] | MONTHLY TREND
Month | Geotechnical | Civil | Tunnelling | MEP | Survey | Total
2026-07-01
2026-08-01
2026-09-01
2026-10-01
Formulas:
Approved = COUNTIFS('WIR Register'!$C5:C2000,"Geotechnical",'WIR Register'!$B5:B2000,">="&[TOTAL WIRs],'WIR Register'!$B5:B2000,"<="&EOMONTH([TOTAL WIRs],0))
With Comments = COUNTIFS('WIR Register'!$C5:C2000,"Civil",'WIR Register'!$B5:B2000,">="&[TOTAL WIRs],'WIR Register'!$B5:B2000,"<="&EOMONTH([TOTAL WIRs],0))
APPROVED = COUNTIFS('WIR Register'!$C5:C2000,"Tunnelling",'WIR Register'!$B5:B2000,">="&[TOTAL WIRs],'WIR Register'!$B5:B2000,"<="&EOMONTH([TOTAL WIRs],0))
Pending = COUNTIFS('WIR Register'!$C5:C2000,"MEP",'WIR Register'!$B5:B2000,">="&[TOTAL WIRs],'WIR Register'!$B5:B2000,"<="&EOMONTH([TOTAL WIRs],0))
Total = COUNTIFS('WIR Register'!$C5:C2000,"Survey",'WIR Register'!$B5:B2000,">="&[TOTAL WIRs],'WIR Register'!$B5:B2000,"<="&EOMONTH([TOTAL WIRs],0))

## WIR Register
WIR Register – Work Inspection Requests
Coastal Tunnel Package (CTP) – Desert Horizon JV • Consultant: Meridian Engineering Partners • Demo data
WIR No. | Submitted | Discipline | Activity | Location | Inspection Date | Consultant Inspector | Status | Response Date | Days Open | Remarks
CTP-WIR-CIV-0001 | 2026-07-01 | Civil | Formwork inspection | CH 6+071 | 2026-07-02 | Eng. Ali Haddad | Approved | 2026-07-04
CTP-WIR-GEO-0001 | 2026-07-01 | Geotechnical | Borehole drilling & logging | CH 1+840 | 2026-07-02 | Eng. Sara Nasser | Approved | 2026-07-02
CTP-WIR-MEP-0001 | 2026-07-01 | MEP | Ventilation duct alignment | CH 8+879 | 2026-07-01 | Eng. Sara Nasser | Rejected | 2026-07-01 |  | Re-inspection required
CTP-WIR-SUR-0001 | 2026-07-01 | Survey | Setting-out check | CH 2+105 | 2026-07-01 | Eng. Sara Nasser | Approved | 2026-07-04
CTP-WIR-TUN-0001 | 2026-07-01 | Tunnelling | Segment ring build | CH 3+645 | 2026-07-01 | Eng. Hana Saleh | Approved with Comments | 2026-07-01 |  | Minor comments to close
CTP-WIR-CIV-0002 | 2026-07-02 | Civil | Concrete pouring | CH 8+437 | 2026-07-02 | Eng. Pedro Alves | Approved | 2026-07-04
CTP-WIR-CIV-0003 | 2026-07-02 | Civil | Formwork inspection | CH 2+715 | 2026-07-04 | Eng. Ali Haddad | Approved | 2026-07-05
CTP-WIR-MEP-0002 | 2026-07-02 | MEP | Cable tray installation | CH 7+431 | 2026-07-03 | Eng. Ali Haddad | Approved with Comments | 2026-07-04 |  | Minor comments to close
CTP-WIR-SUR-0002 | 2026-07-02 | Survey | Settlement monitoring | CH 9+508 | 2026-07-03 | Eng. Ali Haddad | Approved | 2026-07-04
CTP-WIR-SUR-0003 | 2026-07-02 | Survey | As-built survey | CH 1+062 | 2026-07-02 | Eng. Hana Saleh | Rejected | 2026-07-04 |  | Re-inspection required
CTP-WIR-TUN-0002 | 2026-07-02 | Tunnelling | Segment ring build | CH 4+623 | 2026-07-04 | Eng. Ali Haddad | Approved with Comments | 2026-07-06 |  | Minor comments to close
CTP-WIR-CIV-0004 | 2026-07-04 | Civil | Backfilling & compaction | CH 4+723 | 2026-07-05 | Eng. Sara Nasser | Approved with Comments | 2026-07-08 |  | Minor comments to close
CTP-WIR-GEO-0002 | 2026-07-04 | Geotechnical | Ground anchor installation | CH 5+023 | 2026-07-06 | Eng. Sara Nasser | Approved | 2026-07-08
CTP-WIR-GEO-0003 | 2026-07-04 | Geotechnical | Rock bolt pull-out test | CH 0+223 | 2026-07-05 | Eng. Mark Collins | Approved | 2026-07-07
CTP-WIR-GEO-0004 | 2026-07-04 | Geotechnical | Ground anchor installation | CH 1+170 | 2026-07-05 | Eng. Pedro Alves | Approved | 2026-07-07
CTP-WIR-SUR-0004 | 2026-07-04 | Survey | Tunnel alignment survey | CH 9+670 | 2026-07-05 | Eng. Pedro Alves | Rejected | 2026-07-08 |  | Re-inspection required
CTP-WIR-TUN-0003 | 2026-07-04 | Tunnelling | TBM cutter change | CH 1+180 | 2026-07-06 | Eng. Mark Collins | Rejected | 2026-07-07 |  | Re-inspection required
CTP-WIR-TUN-0004 | 2026-07-04 | Tunnelling | Annulus grouting | CH 2+269 | 2026-07-05 | Eng. Ali Haddad | Approved | 2026-07-08
CTP-WIR-CIV-0005 | 2026-07-05 | Civil | Concrete pouring | CH 8+103 | 2026-07-05 | Eng. Hana Saleh | Approved | 2026-07-06
CTP-WIR-GEO-0005 | 2026-07-05 | Geotechnical | Ground anchor installation | CH 1+493 | 2026-07-07 | Eng. Ali Haddad | Approved | 2026-07-09
CTP-WIR-GEO-0006 | 2026-07-05 | Geotechnical | Borehole drilling & logging | CH 7+166 | 2026-07-06 | Eng. Sara Nasser | Approved | 2026-07-07
CTP-WIR-MEP-0003 | 2026-07-05 | MEP | Pump station testing | CH 5+616 | 2026-07-07 | Eng. Pedro Alves | Approved | 2026-07-08
CTP-WIR-MEP-0004 | 2026-07-05 | MEP | Lighting installation | CH 7+491 | 2026-07-05 | Eng. Sara Nasser | Approved | 2026-07-07
CTP-WIR-CIV-0006 | 2026-07-06 | Civil | Formwork inspection | CH 8+023 | 2026-07-07 | Eng. Hana Saleh | Approved | 2026-07-08
CTP-WIR-MEP-0005 | 2026-07-06 | MEP | Pump station testing | CH 8+554 | 2026-07-07 | Eng. Mark Collins | Approved | 2026-07-08
CTP-WIR-SUR-0005 | 2026-07-06 | Survey | Settlement monitoring | CH 3+204 | 2026-07-07 | Eng. Sara Nasser | Approved with Comments | 2026-07-09 |  | Minor comments to close
CTP-WIR-TUN-0005 | 2026-07-06 | Tunnelling | Annulus grouting | CH 1+712 | 2026-07-06 | Eng. Hana Saleh | Approved with Comments | 2026-07-07 |  | Minor comments to close
CTP-WIR-CIV-0007 | 2026-07-07 | Civil | Rebar inspection before concrete | CH 9+860 | 2026-07-08 | Eng. Pedro Alves | Approved | 2026-07-11
CTP-WIR-GEO-0007 | 2026-07-07 | Geotechnical | Rock bolt pull-out test | CH 4+198 | 2026-07-07 | Eng. Pedro Alves | Approved with Comments | 2026-07-09 |  | Minor comments to close
CTP-WIR-GEO-0008 | 2026-07-07 | Geotechnical | Borehole drilling & logging | CH 1+225 | 2026-07-08 | Eng. Mark Collins | Rejected | 2026-07-09 |  | Re-inspection required
CTP-WIR-SUR-0006 | 2026-07-07 | Survey | As-built survey | CH 7+673 | 2026-07-08 | Eng. Mark Collins | Approved | 2026-07-11
CTP-WIR-SUR-0007 | 2026-07-07 | Survey | Setting-out check | CH 8+767 | 2026-07-08 | Eng. Pedro Alves | Approved | 2026-07-08
CTP-WIR-TUN-0006 | 2026-07-07 | Tunnelling | Tunnel invert cleaning | CH 1+931 | 2026-07-08 | Eng. Mark Collins | Approved with Comments | 2026-07-08 |  | Minor comments to close
CTP-WIR-TUN-0007 | 2026-07-07 | Tunnelling | Tunnel invert cleaning | CH 5+088 | 2026-07-09 | Eng. Pedro Alves | Approved with Comments | 2026-07-11 |  | Minor comments to close
CTP-WIR-TUN-0008 | 2026-07-07 | Tunnelling | TBM cutter change | CH 2+174 | 2026-07-09 | Eng. Ali Haddad | Approved with Comments | 2026-07-09 |  | Minor comments to close
CTP-WIR-GEO-0009 | 2026-07-08 | Geotechnical | Grout injection | CH 0+257 | 2026-07-09 | Eng. Sara Nasser | Approved with Comments | 2026-07-10 |  | Minor comments to close
CTP-WIR-GEO-0010 | 2026-07-08 | Geotechnical | Ground anchor installation | CH 4+557 | 2026-07-09 | Eng. Mark Collins | Approved with Comments | 2026-07-10 |  | Minor comments to close
CTP-WIR-GEO-0011 | 2026-07-08 | Geotechnical | Ground anchor installation | CH 7+678 | 2026-07-08 | Eng. Hana Saleh | Rejected | 2026-07-09 |  | Re-inspection required
CTP-WIR-MEP-0006 | 2026-07-08 | MEP | Ventilation duct alignment | CH 0+794 | 2026-07-10 | Eng. Mark Collins | Approved with Comments | 2026-07-13 |  | Minor comments to close
CTP-WIR-CIV-0008 | 2026-07-09 | Civil | Rebar inspection before concrete | CH 0+790 | 2026-07-09 | Eng. Hana Saleh | Approved | 2026-07-10
CTP-WIR-CIV-0009 | 2026-07-09 | Civil | Formwork inspection | CH 7+333 | 2026-07-11 | Eng. Sara Nasser | Approved | 2026-07-11
CTP-WIR-GEO-0012 | 2026-07-09 | Geotechnical | Ground anchor installation | CH 8+543 | 2026-07-09 | Eng. Ali Haddad | Approved | 2026-07-10
CTP-WIR-MEP-0007 | 2026-07-09 | MEP | Lighting installation | CH 6+124 | 2026-07-10 | Eng. Pedro Alves | Approved with Comments | 2026-07-11 |  | Minor comments to close
CTP-WIR-MEP-0008 | 2026-07-09 | MEP | Ventilation duct alignment | CH 6+074 | 2026-07-10 | Eng. Sara Nasser | Approved | 2026-07-11
CTP-WIR-SUR-0008 | 2026-07-09 | Survey | Setting-out check | CH 2+259 | 2026-07-10 | Eng. Pedro Alves | Rejected | 2026-07-11 |  | Re-inspection required
CTP-WIR-SUR-0009 | 2026-07-09 | Survey | Settlement monitoring | CH 6+906 | 2026-07-10 | Eng. Mark Collins | Approved with Comments | 2026-07-10 |  | Minor comments to close
CTP-WIR-TUN-0009 | 2026-07-09 | Tunnelling | Annulus grouting | CH 8+897 | 2026-07-11 | Eng. Hana Saleh | Approved | 2026-07-12
CTP-WIR-CIV-0010 | 2026-07-11 | Civil | Concrete pouring | CH 1+086 | 2026-07-11 | Eng. Sara Nasser | Rejected | 2026-07-12 |  | Re-inspection required
CTP-WIR-CIV-0011 | 2026-07-11 | Civil | Formwork inspection | CH 4+773 | 2026-07-11 | Eng. Pedro Alves | Rejected | 2026-07-12 |  | Re-inspection required
CTP-WIR-CIV-0012 | 2026-07-11 | Civil | Backfilling & compaction | CH 8+584 | 2026-07-12 | Eng. Sara Nasser | Approved | 2026-07-15
CTP-WIR-GEO-0013 | 2026-07-11 | Geotechnical | Rock bolt pull-out test | CH 8+413 | 2026-07-12 | Eng. Pedro Alves | Approved | 2026-07-14
CTP-WIR-GEO-0014 | 2026-07-11 | Geotechnical | Rock bolt pull-out test | CH 5+019 | 2026-07-12 | Eng. Hana Saleh | Approved | 2026-07-12
CTP-WIR-GEO-0015 | 2026-07-11 | Geotechnical | Rock bolt pull-out test | CH 6+339 | 2026-07-13 | Eng. Hana Saleh | Approved | 2026-07-13
CTP-WIR-SUR-0010 | 2026-07-11 | Survey | Tunnel alignment survey | CH 0+649 | 2026-07-13 | Eng. Sara Nasser | Approved with Comments | 2026-07-14 |  | Minor comments to close
CTP-WIR-SUR-0011 | 2026-07-11 | Survey | Tunnel alignment survey | CH 1+270 | 2026-07-11 | Eng. Pedro Alves | Approved | 2026-07-12
CTP-WIR-CIV-0013 | 2026-07-12 | Civil | Rebar inspection before concrete | CH 9+132 | 2026-07-14 | Eng. Hana Saleh | Rejected | 2026-07-15 |  | Re-inspection required
CTP-WIR-CIV-0014 | 2026-07-12 | Civil | Formwork inspection | CH 4+051 | 2026-07-13 | Eng. Mark Collins | Rejected | 2026-07-14 |  | Re-inspection required
CTP-WIR-CIV-0015 | 2026-07-12 | Civil | Backfilling & compaction | CH 3+296 | 2026-07-13 | Eng. Hana Saleh | Approved | 2026-07-16
CTP-WIR-MEP-0009 | 2026-07-12 | MEP | Pump station testing | CH 3+235 | 2026-07-14 | Eng. Mark Collins | Rejected | 2026-07-15 |  | Re-inspection required
CTP-WIR-SUR-0012 | 2026-07-12 | Survey | Setting-out check | CH 0+857 | 2026-07-13 | Eng. Ali Haddad | Approved | 2026-07-14
CTP-WIR-SUR-0013 | 2026-07-12 | Survey | Tunnel alignment survey | CH 6+167 | 2026-07-12 | Eng. Ali Haddad | Approved | 2026-07-13
CTP-WIR-TUN-0010 | 2026-07-12 | Tunnelling | Segment ring build | CH 4+037 | 2026-07-13 | Eng. Ali Haddad | Approved | 2026-07-13
CTP-WIR-TUN-0011 | 2026-07-12 | Tunnelling | Tunnel invert cleaning | CH 7+108 | 2026-07-13 | Eng. Pedro Alves | Approved | 2026-07-14
CTP-WIR-CIV-0016 | 2026-07-13 | Civil | Formwork inspection | CH 3+365 | 2026-07-14 | Eng. Ali Haddad | Approved | 2026-07-15
CTP-WIR-CIV-0017 | 2026-07-13 | Civil | Formwork inspection | CH 4+514 | 2026-07-14 | Eng. Mark Collins | Approved | 2026-07-16
CTP-WIR-CIV-0018 | 2026-07-13 | Civil | Rebar inspection before concrete | CH 2+409 | 2026-07-13 | Eng. Pedro Alves | Approved | 2026-07-13
CTP-WIR-GEO-0016 | 2026-07-13 | Geotechnical | Rock bolt pull-out test | CH 9+248 | 2026-07-15 | Eng. Ali Haddad | Approved with Comments | 2026-07-16 |  | Minor comments to close
CTP-WIR-GEO-0017 | 2026-07-13 | Geotechnical | Rock bolt pull-out test | CH 7+003 | 2026-07-15 | Eng. Sara Nasser | Approved | 2026-07-16
CTP-WIR-MEP-0010 | 2026-07-13 | MEP | Lighting installation | CH 2+673 | 2026-07-14 | Eng. Sara Nasser | Approved | 2026-07-17
CTP-WIR-SUR-0014 | 2026-07-13 | Survey | Settlement monitoring | CH 2+044 | 2026-07-15 | Eng. Hana Saleh | Approved | 2026-07-18
CTP-WIR-SUR-0015 | 2026-07-13 | Survey | Tunnel alignment survey | CH 9+854 | 2026-07-14 | Eng. Hana Saleh | Rejected | 2026-07-17 |  | Re-inspection required
CTP-WIR-CIV-0019 | 2026-07-14 | Civil | Rebar inspection before concrete | CH 1+766 | 2026-07-16 | Eng. Hana Saleh | Approved | 2026-07-18
CTP-WIR-CIV-0020 | 2026-07-14 | Civil | Rebar inspection before concrete | CH 4+828 | 2026-07-14 | Eng. Sara Nasser | Approved with Comments | 2026-07-16 |  | Minor comments to close
CTP-WIR-GEO-0018 | 2026-07-14 | Geotechnical | Rock bolt pull-out test | CH 2+652 | 2026-07-15 | Eng. Ali Haddad | Approved | 2026-07-15
CTP-WIR-GEO-0019 | 2026-07-14 | Geotechnical | Borehole drilling & logging | CH 0+642 | 2026-07-16 | Eng. Hana Saleh | Approved with Comments | 2026-07-19 |  | Minor comments to close
CTP-WIR-MEP-0011 | 2026-07-14 | MEP | Lighting installation | CH 7+865 | 2026-07-15 | Eng. Ali Haddad | Approved with Comments | 2026-07-17 |  | Minor comments to close
CTP-WIR-MEP-0012 | 2026-07-14 | MEP | Ventilation duct alignment | CH 0+631 | 2026-07-16 | Eng. Ali Haddad | Rejected | 2026-07-17 |  | Re-inspection required
CTP-WIR-SUR-0016 | 2026-07-14 | Survey | Setting-out check | CH 9+581 | 2026-07-15 | Eng. Ali Haddad | Approved | 2026-07-16
CTP-WIR-CIV-0021 | 2026-07-15 | Civil | Formwork inspection | CH 1+915 | 2026-07-16 | Eng. Sara Nasser | Approved | 2026-07-18
CTP-WIR-CIV-0022 | 2026-07-15 | Civil | Rebar inspection before concrete | CH 4+469 | 2026-07-15 | Eng. Hana Saleh | Rejected | 2026-07-15 |  | Re-inspection required
CTP-WIR-GEO-0020 | 2026-07-15 | Geotechnical | Ground anchor installation | CH 3+691 | 2026-07-17 | Eng. Sara Nasser | Approved | 2026-07-17
CTP-WIR-TUN-0012 | 2026-07-15 | Tunnelling | TBM cutter change | CH 3+938 | 2026-07-17 | Eng. Ali Haddad | Rejected | 2026-07-19 |  | Re-inspection required
CTP-WIR-TUN-0013 | 2026-07-15 | Tunnelling | Annulus grouting | CH 4+975 | 2026-07-15 | Eng. Mark Collins | Approved | 2026-07-18
CTP-WIR-TUN-0014 | 2026-07-15 | Tunnelling | Tunnel invert cleaning | CH 3+509 | 2026-07-16 | Eng. Pedro Alves | Approved with Comments | 2026-07-17 |  | Minor comments to close
CTP-WIR-GEO-0021 | 2026-07-16 | Geotechnical | Ground anchor installation | CH 6+352 | 2026-07-18 | Eng. Sara Nasser | Approved | 2026-07-19
CTP-WIR-MEP-0013 | 2026-07-16 | MEP | Cable tray installation | CH 6+399 | 2026-07-17 | Eng. Sara Nasser | Approved | 2026-07-17
CTP-WIR-MEP-0014 | 2026-07-16 | MEP | Cable tray installation | CH 4+104 | 2026-07-18 | Eng. Sara Nasser | Approved with Comments | 2026-07-18 |  | Minor comments to close
CTP-WIR-SUR-0017 | 2026-07-16 | Survey | As-built survey | CH 6+523 | 2026-07-17 | Eng. Mark Collins | Approved | 2026-07-18
CTP-WIR-TUN-0015 | 2026-07-16 | Tunnelling | TBM cutter change | CH 1+962 | 2026-07-17 | Eng. Ali Haddad | Approved with Comments | 2026-07-19 |  | Minor comments to close
CTP-WIR-CIV-0023 | 2026-07-18 | Civil | Concrete pouring | CH 5+288 | 2026-07-19 | Eng. Sara Nasser | Approved | 2026-07-21
CTP-WIR-GEO-0022 | 2026-07-18 | Geotechnical | Grout injection | CH 8+562 | 2026-07-20 | Eng. Ali Haddad | Approved with Comments | 2026-07-22 |  | Minor comments to close
CTP-WIR-GEO-0023 | 2026-07-18 | Geotechnical | Grout injection | CH 7+629 | 2026-07-18 | Eng. Sara Nasser | Rejected | 2026-07-20 |  | Re-inspection required
CTP-WIR-SUR-0018 | 2026-07-18 | Survey | Tunnel alignment survey | CH 3+249 | 2026-07-20 | Eng. Mark Collins | Approved | 2026-07-23
CTP-WIR-SUR-0019 | 2026-07-18 | Survey | As-built survey | CH 3+377 | 2026-07-19 | Eng. Hana Saleh | Approved | 2026-07-20
CTP-WIR-TUN-0016 | 2026-07-18 | Tunnelling | Tunnel invert cleaning | CH 4+494 | 2026-07-19 | Eng. Ali Haddad | Approved | 2026-07-20
CTP-WIR-TUN-0017 | 2026-07-18 | Tunnelling | Tunnel invert cleaning | CH 3+512 | 2026-07-19 | Eng. Hana Saleh | Approved | 2026-07-19
CTP-WIR-TUN-0018 | 2026-07-19 | Tunnelling | Annulus grouting | CH 3+385 | 2026-07-21 | Eng. Sara Nasser | Approved | 2026-07-24
CTP-WIR-TUN-0019 | 2026-07-19 | Tunnelling | TBM cutter change | CH 5+128 | 2026-07-19 | Eng. Ali Haddad | Approved | 2026-07-22
CTP-WIR-CIV-0024 | 2026-07-20 | Civil | Backfilling & compaction | CH 0+074 | 2026-07-22 | Eng. Hana Saleh | Rejected | 2026-07-24 |  | Re-inspection required
CTP-WIR-CIV-0025 | 2026-07-20 | Civil | Formwork inspection | CH 1+229 | 2026-07-22 | Eng. Mark Collins | Rejected | 2026-07-23 |  | Re-inspection required
CTP-WIR-GEO-0024 | 2026-07-20 | Geotechnical | Borehole drilling & logging | CH 0+130 | 2026-07-22 | Eng. Pedro Alves | Approved | 2026-07-23
CTP-WIR-MEP-0015 | 2026-07-20 | MEP | Ventilation duct alignment | CH 4+985 | 2026-07-21 | Eng. Sara Nasser | Approved | 2026-07-21
CTP-WIR-MEP-0016 | 2026-07-20 | MEP | Pump station testing | CH 1+072 | 2026-07-22 | Eng. Hana Saleh | Approved | 2026-07-22
CTP-WIR-SUR-0020 | 2026-07-20 | Survey | Tunnel alignment survey | CH 9+001 | 2026-07-21 | Eng. Hana Saleh | Approved | 2026-07-22
CTP-WIR-SUR-0021 | 2026-07-20 | Survey | Setting-out check | CH 5+660 | 2026-07-21 | Eng. Pedro Alves | Rejected | 2026-07-22 |  | Re-inspection required
CTP-WIR-SUR-0022 | 2026-07-20 | Survey | As-built survey | CH 6+721 | 2026-07-21 | Eng. Ali Haddad | Approved | 2026-07-21
CTP-WIR-TUN-0020 | 2026-07-20 | Tunnelling | Segment ring build | CH 1+564 | 2026-07-20 | Eng. Ali Haddad | Rejected | 2026-07-22 |  | Re-inspection required
CTP-WIR-CIV-0026 | 2026-07-21 | Civil | Concrete pouring | CH 6+947 | 2026-07-23 | Eng. Mark Collins | Approved | 2026-07-24
CTP-WIR-MEP-0017 | 2026-07-21 | MEP | Ventilation duct alignment | CH 4+784 | 2026-07-21 | Eng. Mark Collins | Approved | 2026-07-22
CTP-WIR-MEP-0018 | 2026-07-21 | MEP | Lighting installation | CH 1+974 | 2026-07-23 | Eng. Hana Saleh | Approved | 2026-07-24
CTP-WIR-TUN-0021 | 2026-07-21 | Tunnelling | Segment ring build | CH 6+202 | 2026-07-22 | Eng. Sara Nasser | Approved with Comments | 2026-07-23 |  | Minor comments to close
CTP-WIR-CIV-0027 | 2026-07-22 | Civil | Formwork inspection | CH 6+055 | 2026-07-22 | Eng. Ali Haddad | Rejected | 2026-07-23 |  | Re-inspection required
CTP-WIR-TUN-0022 | 2026-07-22 | Tunnelling | Tunnel invert cleaning | CH 2+402 | 2026-07-23 | Eng. Sara Nasser | Approved | 2026-07-23
CTP-WIR-TUN-0023 | 2026-07-22 | Tunnelling | TBM cutter change | CH 5+195 | 2026-07-22 | Eng. Hana Saleh | Rejected | 2026-07-23 |  | Re-inspection required
CTP-WIR-TUN-0024 | 2026-07-22 | Tunnelling | Tunnel invert cleaning | CH 5+339 | 2026-07-24 | Eng. Mark Collins | Approved | 2026-07-26
CTP-WIR-CIV-0028 | 2026-07-23 | Civil | Concrete pouring | CH 6+365 | 2026-07-23 | Eng. Pedro Alves | Approved | 2026-07-24
CTP-WIR-MEP-0019 | 2026-07-23 | MEP | Pump station testing | CH 3+331 | 2026-07-24 | Eng. Pedro Alves | Approved | 2026-07-26
CTP-WIR-MEP-0020 | 2026-07-23 | MEP | Lighting installation | CH 6+041 | 2026-07-23 | Eng. Ali Haddad | Approved | 2026-07-24
CTP-WIR-SUR-0023 | 2026-07-23 | Survey | As-built survey | CH 9+347 | 2026-07-23 | Eng. Sara Nasser | Approved | 2026-07-23
CTP-WIR-CIV-0029 | 2026-07-25 | Civil | Backfilling & compaction | CH 1+486 | 2026-07-25 | Eng. Pedro Alves | Approved | 2026-07-26
CTP-WIR-CIV-0030 | 2026-07-25 | Civil | Backfilling & compaction | CH 2+950 | 2026-07-26 | Eng. Mark Collins | Rejected | 2026-07-28 |  | Re-inspection required
CTP-WIR-CIV-0031 | 2026-07-25 | Civil | Formwork inspection | CH 2+621 | 2026-07-25 | Eng. Sara Nasser | Approved with Comments | 2026-07-26 |  | Minor comments to close
CTP-WIR-GEO-0025 | 2026-07-25 | Geotechnical | Borehole drilling & logging | CH 4+304 | 2026-07-25 | Eng. Hana Saleh | Approved | 2026-07-26
CTP-WIR-MEP-0021 | 2026-07-25 | MEP | Ventilation duct alignment | CH 9+086 | 2026-07-25 | Eng. Ali Haddad | Rejected | 2026-07-26 |  | Re-inspection required
CTP-WIR-MEP-0022 | 2026-07-25 | MEP | Ventilation duct alignment | CH 2+239 | 2026-07-27 | Eng. Pedro Alves | Approved | 2026-07-29
CTP-WIR-MEP-0023 | 2026-07-25 | MEP | Cable tray installation | CH 8+867 | 2026-07-27 | Eng. Sara Nasser | Approved | 2026-07-28
CTP-WIR-SUR-0024 | 2026-07-25 | Survey | Setting-out check | CH 3+449 | 2026-07-26 | Eng. Mark Collins | Approved | 2026-07-27
CTP-WIR-TUN-0025 | 2026-07-25 | Tunnelling | TBM cutter change | CH 1+524 | 2026-07-27 | Eng. Pedro Alves | Approved | 2026-07-30
CTP-WIR-TUN-0026 | 2026-07-25 | Tunnelling | Annulus grouting | CH 0+493 | 2026-07-26 | Eng. Mark Collins | Approved | 2026-07-26
CTP-WIR-MEP-0024 | 2026-07-26 | MEP | Ventilation duct alignment | CH 1+051 | 2026-07-26 | Eng. Hana Saleh | Approved with Comments | 2026-07-27 |  | Minor comments to close
CTP-WIR-MEP-0025 | 2026-07-26 | MEP | Ventilation duct alignment | CH 8+886 | 2026-07-27 | Eng. Pedro Alves | Rejected | 2026-07-28 |  | Re-inspection required
CTP-WIR-MEP-0026 | 2026-07-26 | MEP | Pump station testing | CH 1+652 | 2026-07-27 | Eng. Mark Collins | Approved with Comments | 2026-07-27 |  | Minor comments to close
CTP-WIR-TUN-0027 | 2026-07-26 | Tunnelling | TBM cutter change | CH 4+251 | 2026-07-27 | Eng. Ali Haddad | Approved | 2026-07-29
CTP-WIR-TUN-0028 | 2026-07-26 | Tunnelling | TBM cutter change | CH 0+486 | 2026-07-28 | Eng. Pedro Alves | Rejected | 2026-07-28 |  | Re-inspection required
CTP-WIR-CIV-0032 | 2026-07-27 | Civil | Rebar inspection before concrete | CH 9+319 | 2026-07-29 | Eng. Mark Collins | Approved | 2026-07-30
CTP-WIR-CIV-0033 | 2026-07-27 | Civil | Backfilling & compaction | CH 7+064 | 2026-07-27 | Eng. Ali Haddad | Approved with Comments | 2026-07-30 |  | Minor comments to close
CTP-WIR-GEO-0026 | 2026-07-27 | Geotechnical | Grout injection | CH 0+613 | 2026-07-27 | Eng. Ali Haddad | Approved | 2026-07-28
CTP-WIR-MEP-0027 | 2026-07-27 | MEP | Cable tray installation | CH 6+208 | 2026-07-28 | Eng. Pedro Alves | Approved | 2026-07-30
CTP-WIR-SUR-0025 | 2026-07-27 | Survey | As-built survey | CH 6+591 | 2026-07-29 | Eng. Pedro Alves | Approved | 2026-07-29
CTP-WIR-SUR-0026 | 2026-07-27 | Survey | Settlement monitoring | CH 8+145 | 2026-07-28 | Eng. Ali Haddad | Approved | 2026-07-28
CTP-WIR-TUN-0029 | 2026-07-27 | Tunnelling | Annulus grouting | CH 2+407 | 2026-07-28 | Eng. Pedro Alves | Approved | 2026-07-28
CTP-WIR-TUN-0030 | 2026-07-27 | Tunnelling | Annulus grouting | CH 0+319 | 2026-07-28 | Eng. Pedro Alves | Approved | 2026-07-30
CTP-WIR-CIV-0034 | 2026-07-28 | Civil | Formwork inspection | CH 3+308 | 2026-07-28 | Eng. Ali Haddad | Approved | 2026-07-30
CTP-WIR-GEO-0027 | 2026-07-28 | Geotechnical | Rock bolt pull-out test | CH 2+356 | 2026-07-29 | Eng. Mark Collins | Approved with Comments | 2026-07-30 |  | Minor comments to close
CTP-WIR-SUR-0027 | 2026-07-28 | Survey | As-built survey | CH 0+683 | 2026-07-29 | Eng. Ali Haddad | Approved | 2026-08-01
CTP-WIR-SUR-0028 | 2026-07-28 | Survey | Settlement monitoring | CH 4+664 | 2026-07-30 | Eng. Sara Nasser | Approved | 2026-08-02
CTP-WIR-TUN-0031 | 2026-07-28 | Tunnelling | TBM cutter change | CH 6+088 | 2026-07-30 | Eng. Mark Collins | Approved | 2026-08-02
CTP-WIR-TUN-0032 | 2026-07-28 | Tunnelling | TBM cutter change | CH 7+187 | 2026-07-30 | Eng. Ali Haddad | Approved | 2026-07-31
CTP-WIR-TUN-0033 | 2026-07-28 | Tunnelling | Segment ring build | CH 6+367 | 2026-07-30 | Eng. Mark Collins | Rejected | 2026-07-31 |  | Re-inspection required
CTP-WIR-GEO-0028 | 2026-07-29 | Geotechnical | Ground anchor installation | CH 7+515 | 2026-07-31 | Eng. Mark Collins | Approved | 2026-08-01
CTP-WIR-MEP-0028 | 2026-07-29 | MEP | Pump station testing | CH 5+440 | 2026-07-31 | Eng. Ali Haddad | Approved | 2026-08-01
CTP-WIR-MEP-0029 | 2026-07-29 | MEP | Ventilation duct alignment | CH 0+651 | 2026-07-31 | Eng. Ali Haddad | Approved | 2026-07-31
CTP-WIR-SUR-0029 | 2026-07-29 | Survey | Settlement monitoring | CH 1+055 | 2026-07-30 | Eng. Mark Collins | Approved with Comments | 2026-08-02 |  | Minor comments to close
CTP-WIR-SUR-0030 | 2026-07-29 | Survey | Setting-out check | CH 1+198 | 2026-07-29 | Eng. Pedro Alves | Approved with Comments | 2026-08-01 |  | Minor comments to close
CTP-WIR-SUR-0031 | 2026-07-29 | Survey | As-built survey | CH 3+067 | 2026-07-30 | Eng. Hana Saleh | Rejected | 2026-07-31 |  | Re-inspection required
CTP-WIR-TUN-0034 | 2026-07-29 | Tunnelling | Tunnel invert cleaning | CH 9+798 | 2026-07-31 | Eng. Mark Collins | Approved | 2026-08-02
CTP-WIR-CIV-0035 | 2026-07-30 | Civil | Formwork inspection | CH 2+413 | 2026-07-31 | Eng. Sara Nasser | Approved | 2026-08-01
CTP-WIR-GEO-0029 | 2026-07-30 | Geotechnical | Ground anchor installation | CH 4+926 | 2026-07-31 | Eng. Mark Collins | Approved | 2026-08-03
CTP-WIR-GEO-0030 | 2026-07-30 | Geotechnical | Rock bolt pull-out test | CH 3+606 | 2026-07-31 | Eng. Hana Saleh | Approved | 2026-08-02
CTP-WIR-SUR-0032 | 2026-07-30 | Survey | Setting-out check | CH 7+235 | 2026-07-31 | Eng. Hana Saleh | Approved | 2026-07-31
CTP-WIR-SUR-0033 | 2026-07-30 | Survey | As-built survey | CH 4+317 | 2026-07-30 | Eng. Ali Haddad | Approved | 2026-08-02
CTP-WIR-SUR-0034 | 2026-07-30 | Survey | Settlement monitoring | CH 9+640 | 2026-07-30 | Eng. Pedro Alves | Approved | 2026-07-31
CTP-WIR-TUN-0035 | 2026-07-30 | Tunnelling | Segment ring build | CH 1+786 | 2026-08-01 | Eng. Sara Nasser | Approved | 2026-08-02
CTP-WIR-TUN-0036 | 2026-07-30 | Tunnelling | Tunnel invert cleaning | CH 1+258 | 2026-08-01 | Eng. Sara Nasser | Approved | 2026-08-04
CTP-WIR-GEO-0031 | 2026-08-01 | Geotechnical | Borehole drilling & logging | CH 9+668 | 2026-08-01 | Eng. Ali Haddad | Approved | 2026-08-02
CTP-WIR-MEP-0030 | 2026-08-01 | MEP | Ventilation duct alignment | CH 7+162 | 2026-08-02 | Eng. Ali Haddad | Approved | 2026-08-05
CTP-WIR-SUR-0035 | 2026-08-01 | Survey | Setting-out check | CH 1+065 | 2026-08-02 | Eng. Sara Nasser | Approved with Comments | 2026-08-04 |  | Minor comments to close
CTP-WIR-SUR-0036 | 2026-08-01 | Survey | As-built survey | CH 0+660 | 2026-08-03 | Eng. Hana Saleh | Approved with Comments | 2026-08-03 |  | Minor comments to close
CTP-WIR-SUR-0037 | 2026-08-01 | Survey | Setting-out check | CH 7+254 | 2026-08-03 | Eng. Ali Haddad | Approved | 2026-08-06
CTP-WIR-TUN-0037 | 2026-08-01 | Tunnelling | Tunnel invert cleaning | CH 8+229 | 2026-08-02 | Eng. Hana Saleh | Approved | 2026-08-03
CTP-WIR-CIV-0036 | 2026-08-02 | Civil | Rebar inspection before concrete | CH 0+933 | 2026-08-04 | Eng. Ali Haddad | Approved | 2026-08-05
CTP-WIR-SUR-0038 | 2026-08-02 | Survey | Settlement monitoring | CH 8+006 | 2026-08-03 | Eng. Pedro Alves | Approved | 2026-08-05
CTP-WIR-TUN-0038 | 2026-08-02 | Tunnelling | Tunnel invert cleaning | CH 8+622 | 2026-08-03 | Eng. Hana Saleh | Approved | 2026-08-04
CTP-WIR-GEO-0032 | 2026-08-03 | Geotechnical | Borehole drilling & logging | CH 2+231 | 2026-08-05 | Eng. Sara Nasser | Approved | 2026-08-07
CTP-WIR-GEO-0033 | 2026-08-03 | Geotechnical | Rock bolt pull-out test | CH 5+912 | 2026-08-04 | Eng. Ali Haddad | Approved | 2026-08-04
CTP-WIR-MEP-0031 | 2026-08-03 | MEP | Ventilation duct alignment | CH 3+967 | 2026-08-03 | Eng. Sara Nasser | Approved | 2026-08-04
CTP-WIR-MEP-0032 | 2026-08-03 | MEP | Lighting installation | CH 9+244 | 2026-08-04 | Eng. Hana Saleh | Approved with Comments | 2026-08-05 |  | Minor comments to close
CTP-WIR-SUR-0039 | 2026-08-03 | Survey | As-built survey | CH 3+584 | 2026-08-03 | Eng. Mark Collins | Approved with Comments | 2026-08-05 |  | Minor comments to close
CTP-WIR-TUN-0039 | 2026-08-03 | Tunnelling | TBM cutter change | CH 4+302 | 2026-08-05 | Eng. Ali Haddad | Approved | 2026-08-08
CTP-WIR-GEO-0034 | 2026-08-04 | Geotechnical | Borehole drilling & logging | CH 2+033 | 2026-08-04 | Eng. Ali Haddad | Approved | 2026-08-05
CTP-WIR-TUN-0040 | 2026-08-04 | Tunnelling | TBM cutter change | CH 0+042 | 2026-08-05 | Eng. Ali Haddad | Rejected | 2026-08-05 |  | Re-inspection required
CTP-WIR-TUN-0041 | 2026-08-04 | Tunnelling | Annulus grouting | CH 9+780 | 2026-08-04 | Eng. Mark Collins | Approved with Comments | 2026-08-04 |  | Minor comments to close
CTP-WIR-TUN-0042 | 2026-08-04 | Tunnelling | TBM cutter change | CH 1+252 | 2026-08-04 | Eng. Mark Collins | Approved with Comments | 2026-08-06 |  | Minor comments to close
CTP-WIR-GEO-0035 | 2026-08-05 | Geotechnical | Grout injection | CH 7+102 | 2026-08-05 | Eng. Ali Haddad | Approved with Comments | 2026-08-06 |  | Minor comments to close
CTP-WIR-GEO-0036 | 2026-08-05 | Geotechnical | Borehole drilling & logging | CH 6+267 | 2026-08-06 | Eng. Sara Nasser | Approved | 2026-08-07
CTP-WIR-MEP-0033 | 2026-08-05 | MEP | Lighting installation | CH 1+355 | 2026-08-07 | Eng. Ali Haddad | Approved | 2026-08-10
CTP-WIR-MEP-0034 | 2026-08-05 | MEP | Pump station testing | CH 9+839 | 2026-08-06 | Eng. Mark Collins | Approved with Comments | 2026-08-06 |  | Minor comments to close
CTP-WIR-SUR-0040 | 2026-08-05 | Survey | Settlement monitoring | CH 0+356 | 2026-08-06 | Eng. Ali Haddad | Approved | 2026-08-06
CTP-WIR-TUN-0043 | 2026-08-05 | Tunnelling | Annulus grouting | CH 8+487 | 2026-08-06 | Eng. Hana Saleh | Rejected | 2026-08-09 |  | Re-inspection required
CTP-WIR-CIV-0037 | 2026-08-06 | Civil | Rebar inspection before concrete | CH 7+169 | 2026-08-07 | Eng. Ali Haddad | Approved with Comments | 2026-08-08 |  | Minor comments to close
CTP-WIR-CIV-0038 | 2026-08-06 | Civil | Concrete pouring | CH 1+643 | 2026-08-08 | Eng. Sara Nasser | Approved with Comments | 2026-08-11 |  | Minor comments to close
CTP-WIR-CIV-0039 | 2026-08-06 | Civil | Rebar inspection before concrete | CH 1+432 | 2026-08-06 | Eng. Sara Nasser | Approved | 2026-08-08
CTP-WIR-GEO-0037 | 2026-08-06 | Geotechnical | Rock bolt pull-out test | CH 5+980 | 2026-08-07 | Eng. Hana Saleh | Rejected | 2026-08-10 |  | Re-inspection required
CTP-WIR-SUR-0041 | 2026-08-06 | Survey | Tunnel alignment survey | CH 7+129 | 2026-08-07 | Eng. Sara Nasser | Approved | 2026-08-08
CTP-WIR-SUR-0042 | 2026-08-06 | Survey | As-built survey | CH 8+759 | 2026-08-07 | Eng. Mark Collins | Approved | 2026-08-09
CTP-WIR-GEO-0038 | 2026-08-08 | Geotechnical | Grout injection | CH 5+473 | 2026-08-09 | Eng. Hana Saleh | Approved | 2026-08-10
CTP-WIR-SUR-0043 | 2026-08-08 | Survey | Tunnel alignment survey | CH 2+985 | 2026-08-09 | Eng. Mark Collins | Rejected | 2026-08-09 |  | Re-inspection required
CTP-WIR-SUR-0044 | 2026-08-08 | Survey | As-built survey | CH 4+750 | 2026-08-10 | Eng. Pedro Alves | Approved | 2026-08-11
CTP-WIR-SUR-0045 | 2026-08-08 | Survey | Settlement monitoring | CH 4+211 | 2026-08-09 | Eng. Pedro Alves | Approved | 2026-08-09
CTP-WIR-TUN-0044 | 2026-08-08 | Tunnelling | Annulus grouting | CH 5+617 | 2026-08-09 | Eng. Mark Collins | Approved with Comments | 2026-08-10 |  | Minor comments to close
CTP-WIR-CIV-0040 | 2026-08-09 | Civil | Rebar inspection before concrete | CH 4+474 | 2026-08-11 | Eng. Mark Collins | Approved | 2026-08-14
CTP-WIR-MEP-0035 | 2026-08-09 | MEP | Lighting installation | CH 9+601 | 2026-08-09 | Eng. Mark Collins | Approved with Comments | 2026-08-11 |  | Minor comments to close
CTP-WIR-MEP-0036 | 2026-08-09 | MEP | Pump station testing | CH 7+442 | 2026-08-10 | Eng. Sara Nasser | Approved | 2026-08-10
CTP-WIR-SUR-0046 | 2026-08-09 | Survey | Setting-out check | CH 6+730 | 2026-08-09 | Eng. Sara Nasser | Approved with Comments | 2026-08-10 |  | Minor comments to close
CTP-WIR-GEO-0039 | 2026-08-10 | Geotechnical | Grout injection | CH 6+530 | 2026-08-12 | Eng. Sara Nasser | Approved | 2026-08-15
CTP-WIR-GEO-0040 | 2026-08-10 | Geotechnical | Rock bolt pull-out test | CH 1+039 | 2026-08-10 | Eng. Hana Saleh | Approved | 2026-08-12
CTP-WIR-SUR-0047 | 2026-08-10 | Survey | Tunnel alignment survey | CH 9+364 | 2026-08-12 | Eng. Sara Nasser | Approved | 2026-08-12
CTP-WIR-SUR-0048 | 2026-08-10 | Survey | Settlement monitoring | CH 0+076 | 2026-08-11 | Eng. Pedro Alves | Approved | 2026-08-11
CTP-WIR-TUN-0045 | 2026-08-10 | Tunnelling | TBM cutter change | CH 9+467 | 2026-08-11 | Eng. Pedro Alves | Approved | 2026-08-11
CTP-WIR-TUN-0046 | 2026-08-10 | Tunnelling | Tunnel invert cleaning | CH 8+351 | 2026-08-10 | Eng. Pedro Alves | Approved | 2026-08-11
CTP-WIR-CIV-0041 | 2026-08-11 | Civil | Rebar inspection before concrete | CH 2+951 | 2026-08-13 | Eng. Mark Collins | Approved | 2026-08-14
CTP-WIR-CIV-0042 | 2026-08-11 | Civil | Backfilling & compaction | CH 2+361 | 2026-08-13 | Eng. Pedro Alves | Approved | 2026-08-14
CTP-WIR-CIV-0043 | 2026-08-11 | Civil | Formwork inspection | CH 7+363 | 2026-08-12 | Eng. Sara Nasser | Approved with Comments | 2026-08-13 |  | Minor comments to close
CTP-WIR-GEO-0041 | 2026-08-11 | Geotechnical | Ground anchor installation | CH 3+310 | 2026-08-12 | Eng. Hana Saleh | Approved | 2026-08-12
CTP-WIR-MEP-0037 | 2026-08-11 | MEP | Cable tray installation | CH 6+058 | 2026-08-12 | Eng. Hana Saleh | Approved | 2026-08-13
CTP-WIR-MEP-0038 | 2026-08-11 | MEP | Pump station testing | CH 8+851 | 2026-08-12 | Eng. Hana Saleh | Approved with Comments | 2026-08-13 |  | Minor comments to close
CTP-WIR-TUN-0047 | 2026-08-11 | Tunnelling | Annulus grouting | CH 7+002 | 2026-08-12 | Eng. Sara Nasser | Rejected | 2026-08-13 |  | Re-inspection required
CTP-WIR-TUN-0048 | 2026-08-11 | Tunnelling | Tunnel invert cleaning | CH 7+496 | 2026-08-12 | Eng. Hana Saleh | Approved | 2026-08-13
CTP-WIR-CIV-0044 | 2026-08-12 | Civil | Formwork inspection | CH 9+146 | 2026-08-13 | Eng. Mark Collins | Approved | 2026-08-13
CTP-WIR-CIV-0045 | 2026-08-12 | Civil | Backfilling & compaction | CH 3+925 | 2026-08-14 | Eng. Hana Saleh | Approved | 2026-08-15
CTP-WIR-CIV-0046 | 2026-08-12 | Civil | Concrete pouring | CH 1+684 | 2026-08-13 | Eng. Mark Collins | Approved | 2026-08-16
CTP-WIR-MEP-0039 | 2026-08-12 | MEP | Lighting installation | CH 0+495 | 2026-08-13 | Eng. Mark Collins | Approved | 2026-08-16
CTP-WIR-SUR-0049 | 2026-08-12 | Survey | Tunnel alignment survey | CH 9+883 | 2026-08-13 | Eng. Mark Collins | Approved | 2026-08-16
CTP-WIR-SUR-0050 | 2026-08-12 | Survey | As-built survey | CH 7+681 | 2026-08-13 | Eng. Pedro Alves | Approved | 2026-08-16
CTP-WIR-TUN-0049 | 2026-08-12 | Tunnelling | Segment ring build | CH 1+568 | 2026-08-13 | Eng. Sara Nasser | Approved | 2026-08-15
CTP-WIR-GEO-0042 | 2026-08-13 | Geotechnical | Rock bolt pull-out test | CH 2+652 | 2026-08-15 | Eng. Ali Haddad | Rejected | 2026-08-15 |  | Re-inspection required
CTP-WIR-MEP-0040 | 2026-08-13 | MEP | Lighting installation | CH 8+495 | 2026-08-14 | Eng. Mark Collins | Approved with Comments | 2026-08-14 |  | Minor comments to close
CTP-WIR-MEP-0041 | 2026-08-13 | MEP | Cable tray installation | CH 2+346 | 2026-08-13 | Eng. Sara Nasser | Approved | 2026-08-15
CTP-WIR-SUR-0051 | 2026-08-13 | Survey | Tunnel alignment survey | CH 6+257 | 2026-08-14 | Eng. Sara Nasser | Approved | 2026-08-15
CTP-WIR-CIV-0047 | 2026-08-15 | Civil | Rebar inspection before concrete | CH 4+130 | 2026-08-15 | Eng. Ali Haddad | Approved | 2026-08-16
CTP-WIR-CIV-0048 | 2026-08-15 | Civil | Rebar inspection before concrete | CH 8+587 | 2026-08-17 | Eng. Pedro Alves | Approved with Comments | 2026-08-19 |  | Minor comments to close
CTP-WIR-GEO-0043 | 2026-08-15 | Geotechnical | Rock bolt pull-out test | CH 4+893 | 2026-08-17 | Eng. Mark Collins | Approved | 2026-08-20
CTP-WIR-MEP-0042 | 2026-08-15 | MEP | Cable tray installation | CH 1+217 | 2026-08-17 | Eng. Pedro Alves | Approved | 2026-08-20
CTP-WIR-MEP-0043 | 2026-08-15 | MEP | Cable tray installation | CH 0+431 | 2026-08-16 | Eng. Ali Haddad | Approved | 2026-08-17
CTP-WIR-MEP-0044 | 2026-08-15 | MEP | Pump station testing | CH 4+575 | 2026-08-16 | Eng. Sara Nasser | Approved with Comments | 2026-08-17 |  | Minor comments to close
CTP-WIR-TUN-0050 | 2026-08-15 | Tunnelling | Segment ring build | CH 9+784 | 2026-08-15 | Eng. Hana Saleh | Approved | 2026-08-17
CTP-WIR-MEP-0045 | 2026-08-16 | MEP | Ventilation duct alignment | CH 6+608 | 2026-08-18 | Eng. Pedro Alves | Approved | 2026-08-18
CTP-WIR-SUR-0052 | 2026-08-16 | Survey | Setting-out check | CH 3+917 | 2026-08-16 | Eng. Ali Haddad | Approved | 2026-08-18
CTP-WIR-SUR-0053 | 2026-08-16 | Survey | Tunnel alignment survey | CH 1+223 | 2026-08-18 | Eng. Mark Collins | Approved | 2026-08-18
CTP-WIR-TUN-0051 | 2026-08-16 | Tunnelling | Segment ring build | CH 0+844 | 2026-08-16 | Eng. Pedro Alves | Approved | 2026-08-19
CTP-WIR-CIV-0049 | 2026-08-17 | Civil | Backfilling & compaction | CH 4+643 | 2026-08-18 | Eng. Pedro Alves | Approved with Comments | 2026-08-18 |  | Minor comments to close
CTP-WIR-GEO-0044 | 2026-08-17 | Geotechnical | Grout injection | CH 7+751 | 2026-08-18 | Eng. Ali Haddad | Approved with Comments | 2026-08-19 |  | Minor comments to close
CTP-WIR-SUR-0054 | 2026-08-17 | Survey | Tunnel alignment survey | CH 2+989 | 2026-08-19 | Eng. Sara Nasser | Approved | 2026-08-20
CTP-WIR-TUN-0052 | 2026-08-17 | Tunnelling | Segment ring build | CH 0+011 | 2026-08-18 | Eng. Ali Haddad | Rejected | 2026-08-18 |  | Re-inspection required
CTP-WIR-TUN-0053 | 2026-08-17 | Tunnelling | Tunnel invert cleaning | CH 9+169 | 2026-08-17 | Eng. Hana Saleh | Approved | 2026-08-18
CTP-WIR-CIV-0050 | 2026-08-18 | Civil | Rebar inspection before concrete | CH 7+290 | 2026-08-20 | Eng. Sara Nasser | Approved | 2026-08-21
CTP-WIR-GEO-0045 | 2026-08-18 | Geotechnical | Ground anchor installation | CH 7+394 | 2026-08-19 | Eng. Sara Nasser | Approved | 2026-08-21
CTP-WIR-GEO-0046 | 2026-08-18 | Geotechnical | Rock bolt pull-out test | CH 9+997 | 2026-08-19 | Eng. Hana Saleh | Approved | 2026-08-19
CTP-WIR-GEO-0047 | 2026-08-18 | Geotechnical | Ground anchor installation | CH 4+598 | 2026-08-18 | Eng. Mark Collins | Approved with Comments | 2026-08-21 |  | Minor comments to close
CTP-WIR-MEP-0046 | 2026-08-18 | MEP | Pump station testing | CH 9+150 | 2026-08-18 | Eng. Hana Saleh | Approved | 2026-08-19
CTP-WIR-SUR-0055 | 2026-08-18 | Survey | Settlement monitoring | CH 8+566 | 2026-08-20 | Eng. Pedro Alves | Approved | 2026-08-20
CTP-WIR-SUR-0056 | 2026-08-18 | Survey | Tunnel alignment survey | CH 4+621 | 2026-08-19 | Eng. Pedro Alves | Approved with Comments | 2026-08-20 |  | Minor comments to close
CTP-WIR-CIV-0051 | 2026-08-19 | Civil | Concrete pouring | CH 6+593 | 2026-08-20 | Eng. Hana Saleh | Approved with Comments | 2026-08-21 |  | Minor comments to close
CTP-WIR-GEO-0048 | 2026-08-19 | Geotechnical | Ground anchor installation | CH 0+810 | 2026-08-20 | Eng. Pedro Alves | Rejected | 2026-08-23 |  | Re-inspection required
CTP-WIR-MEP-0047 | 2026-08-19 | MEP | Cable tray installation | CH 2+252 | 2026-08-20 | Eng. Pedro Alves | Approved | 2026-08-23
CTP-WIR-SUR-0057 | 2026-08-19 | Survey | As-built survey | CH 1+159 | 2026-08-19 | Eng. Hana Saleh | Approved | 2026-08-21
CTP-WIR-TUN-0054 | 2026-08-19 | Tunnelling | Annulus grouting | CH 1+185 | 2026-08-20 | Eng. Sara Nasser | Approved | 2026-08-21
CTP-WIR-CIV-0052 | 2026-08-20 | Civil | Formwork inspection | CH 9+497 | 2026-08-20 | Eng. Sara Nasser | Approved | 2026-08-21
CTP-WIR-MEP-0048 | 2026-08-20 | MEP | Ventilation duct alignment | CH 4+326 | 2026-08-20 | Eng. Ali Haddad | Approved with Comments | 2026-08-20 |  | Minor comments to close
CTP-WIR-MEP-0049 | 2026-08-20 | MEP | Ventilation duct alignment | CH 5+988 | 2026-08-22 | Eng. Mark Collins | Approved | 2026-08-23
CTP-WIR-TUN-0055 | 2026-08-20 | Tunnelling | TBM cutter change | CH 9+838 | 2026-08-21 | Eng. Sara Nasser | Approved | 2026-08-23
CTP-WIR-TUN-0056 | 2026-08-20 | Tunnelling | Segment ring build | CH 6+085 | 2026-08-20 | Eng. Ali Haddad | Approved | 2026-08-21
CTP-WIR-TUN-0057 | 2026-08-20 | Tunnelling | Segment ring build | CH 7+969 | 2026-08-20 | Eng. Hana Saleh | Approved | 2026-08-22
CTP-WIR-GEO-0049 | 2026-08-22 | Geotechnical | Borehole drilling & logging | CH 0+857 | 2026-08-23 | Eng. Sara Nasser | Approved | 2026-08-26
CTP-WIR-GEO-0050 | 2026-08-22 | Geotechnical | Borehole drilling & logging | CH 5+773 | 2026-08-24 | Eng. Mark Collins | Approved | 2026-08-25
CTP-WIR-GEO-0051 | 2026-08-22 | Geotechnical | Rock bolt pull-out test | CH 1+482 | 2026-08-23 | Eng. Sara Nasser | Approved | 2026-08-25
CTP-WIR-MEP-0050 | 2026-08-22 | MEP | Ventilation duct alignment | CH 0+479 | 2026-08-23 | Eng. Ali Haddad | Approved | 2026-08-24
CTP-WIR-CIV-0053 | 2026-08-23 | Civil | Formwork inspection | CH 2+339 | 2026-08-25 | Eng. Ali Haddad | Approved | 2026-08-26
CTP-WIR-CIV-0054 | 2026-08-23 | Civil | Formwork inspection | CH 2+449 | 2026-08-24 | Eng. Sara Nasser | Approved with Comments | 2026-08-27 |  | Minor comments to close
CTP-WIR-GEO-0052 | 2026-08-23 | Geotechnical | Ground anchor installation | CH 2+796 | 2026-08-23 | Eng. Ali Haddad | Rejected | 2026-08-24 |  | Re-inspection required
CTP-WIR-GEO-0053 | 2026-08-23 | Geotechnical | Rock bolt pull-out test | CH 7+995 | 2026-08-25 | Eng. Sara Nasser | Approved with Comments | 2026-08-25 |  | Minor comments to close
CTP-WIR-MEP-0051 | 2026-08-23 | MEP | Lighting installation | CH 7+924 | 2026-08-24 | Eng. Ali Haddad | Approved | 2026-08-25
CTP-WIR-MEP-0052 | 2026-08-23 | MEP | Lighting installation | CH 3+573 | 2026-08-24 | Eng. Sara Nasser | Rejected | 2026-08-24 |  | Re-inspection required
CTP-WIR-TUN-0058 | 2026-08-23 | Tunnelling | Annulus grouting | CH 9+859 | 2026-08-24 | Eng. Sara Nasser | Approved | 2026-08-25
CTP-WIR-CIV-0055 | 2026-08-24 | Civil | Formwork inspection | CH 5+523 | 2026-08-24 | Eng. Pedro Alves | Approved | 2026-08-27
CTP-WIR-CIV-0056 | 2026-08-24 | Civil | Concrete pouring | CH 4+190 | 2026-08-24 | Eng. Pedro Alves | Approved with Comments | 2026-08-27 |  | Minor comments to close
CTP-WIR-CIV-0057 | 2026-08-24 | Civil | Formwork inspection | CH 4+585 | 2026-08-24 | Eng. Mark Collins | Rejected | 2026-08-25 |  | Re-inspection required
CTP-WIR-GEO-0054 | 2026-08-24 | Geotechnical | Grout injection | CH 3+947 | 2026-08-25 | Eng. Ali Haddad | Approved | 2026-08-26
CTP-WIR-GEO-0055 | 2026-08-24 | Geotechnical | Rock bolt pull-out test | CH 0+852 | 2026-08-26 | Eng. Mark Collins | Approved | 2026-08-27
CTP-WIR-MEP-0053 | 2026-08-24 | MEP | Cable tray installation | CH 6+861 | 2026-08-24 | Eng. Hana Saleh | Approved | 2026-08-27
CTP-WIR-SUR-0058 | 2026-08-24 | Survey | Settlement monitoring | CH 1+015 | 2026-08-25 | Eng. Pedro Alves | Approved | 2026-08-27
CTP-WIR-SUR-0059 | 2026-08-24 | Survey | As-built survey | CH 3+190 | 2026-08-25 | Eng. Ali Haddad | Approved with Comments | 2026-08-26 |  | Minor comments to close
CTP-WIR-TUN-0059 | 2026-08-24 | Tunnelling | Segment ring build | CH 9+081 | 2026-08-25 | Eng. Hana Saleh | Approved with Comments | 2026-08-26 |  | Minor comments to close
CTP-WIR-TUN-0060 | 2026-08-24 | Tunnelling | TBM cutter change | CH 3+140 | 2026-08-26 | Eng. Hana Saleh | Approved with Comments | 2026-08-27 |  | Minor comments to close
CTP-WIR-CIV-0058 | 2026-08-25 | Civil | Rebar inspection before concrete | CH 8+073 | 2026-08-25 | Eng. Sara Nasser | Approved | 2026-08-27
CTP-WIR-MEP-0054 | 2026-08-25 | MEP | Ventilation duct alignment | CH 3+633 | 2026-08-26 | Eng. Mark Collins | Approved | 2026-08-26
CTP-WIR-MEP-0055 | 2026-08-25 | MEP | Cable tray installation | CH 0+019 | 2026-08-25 | Eng. Mark Collins | Approved | 2026-08-28
CTP-WIR-TUN-0061 | 2026-08-25 | Tunnelling | Segment ring build | CH 9+769 | 2026-08-26 | Eng. Sara Nasser | Approved with Comments | 2026-08-28 |  | Minor comments to close
CTP-WIR-TUN-0062 | 2026-08-25 | Tunnelling | Segment ring build | CH 7+525 | 2026-08-25 | Eng. Hana Saleh | Rejected | 2026-08-27 |  | Re-inspection required
CTP-WIR-GEO-0056 | 2026-08-26 | Geotechnical | Borehole drilling & logging | CH 1+359 | 2026-08-28 | Eng. Mark Collins | Approved | 2026-08-30
CTP-WIR-GEO-0057 | 2026-08-26 | Geotechnical | Rock bolt pull-out test | CH 7+599 | 2026-08-26 | Eng. Ali Haddad | Approved | 2026-08-28
CTP-WIR-SUR-0060 | 2026-08-26 | Survey | Tunnel alignment survey | CH 9+538 | 2026-08-28 | Eng. Pedro Alves | Approved | 2026-08-31
CTP-WIR-SUR-0061 | 2026-08-26 | Survey | As-built survey | CH 6+246 | 2026-08-26 | Eng. Pedro Alves | Approved with Comments | 2026-08-27 |  | Minor comments to close
CTP-WIR-TUN-0063 | 2026-08-26 | Tunnelling | Tunnel invert cleaning | CH 3+150 | 2026-08-27 | Eng. Pedro Alves | Approved | 2026-08-28
CTP-WIR-CIV-0059 | 2026-08-27 | Civil | Backfilling & compaction | CH 3+142 | 2026-08-28 | Eng. Pedro Alves | Approved | 2026-08-28
CTP-WIR-GEO-0058 | 2026-08-27 | Geotechnical | Grout injection | CH 0+332 | 2026-08-28 | Eng. Sara Nasser | Approved with Comments | 2026-08-31 |  | Minor comments to close
CTP-WIR-GEO-0059 | 2026-08-27 | Geotechnical | Grout injection | CH 5+111 | 2026-08-28 | Eng. Ali Haddad | Approved with Comments | 2026-08-28 |  | Minor comments to close
CTP-WIR-MEP-0056 | 2026-08-27 | MEP | Pump station testing | CH 4+115 | 2026-08-29 | Eng. Sara Nasser | Approved | 2026-08-29
CTP-WIR-SUR-0062 | 2026-08-27 | Survey | Settlement monitoring | CH 4+086 | 2026-08-27 | Eng. Hana Saleh | Approved | 2026-08-30
CTP-WIR-SUR-0063 | 2026-08-27 | Survey | As-built survey | CH 2+906 | 2026-08-28 | Eng. Pedro Alves | Approved | 2026-08-31
CTP-WIR-TUN-0064 | 2026-08-27 | Tunnelling | Annulus grouting | CH 0+886 | 2026-08-29 | Eng. Hana Saleh | Approved | 2026-08-29
CTP-WIR-TUN-0065 | 2026-08-27 | Tunnelling | Annulus grouting | CH 9+102 | 2026-08-28 | Eng. Ali Haddad | Approved | 2026-08-28
CTP-WIR-CIV-0060 | 2026-08-29 | Civil | Concrete pouring | CH 8+727 | 2026-08-30 | Eng. Pedro Alves | Approved | 2026-08-31
CTP-WIR-CIV-0061 | 2026-08-29 | Civil | Formwork inspection | CH 4+031 | 2026-08-30 | Eng. Sara Nasser | Approved | 2026-09-01
CTP-WIR-GEO-0060 | 2026-08-29 | Geotechnical | Ground anchor installation | CH 8+294 | 2026-08-30 | Eng. Hana Saleh | Approved | 2026-08-30
CTP-WIR-MEP-0057 | 2026-08-29 | MEP | Pump station testing | CH 0+946 | 2026-08-31 | Eng. Mark Collins | Rejected | 2026-09-02 |  | Re-inspection required
CTP-WIR-SUR-0064 | 2026-08-29 | Survey | As-built survey | CH 7+276 | 2026-08-30 | Eng. Mark Collins | Approved | 2026-08-31
CTP-WIR-SUR-0065 | 2026-08-29 | Survey | Tunnel alignment survey | CH 2+564 | 2026-08-30 | Eng. Hana Saleh | Approved | 2026-08-30
CTP-WIR-CIV-0062 | 2026-08-30 | Civil | Backfilling & compaction | CH 1+756 | 2026-08-31 | Eng. Sara Nasser | Approved with Comments | 2026-09-03 |  | Minor comments to close
CTP-WIR-CIV-0063 | 2026-08-30 | Civil | Rebar inspection before concrete | CH 0+420 | 2026-08-31 | Eng. Pedro Alves | Approved | 2026-08-31
CTP-WIR-GEO-0061 | 2026-08-30 | Geotechnical | Ground anchor installation | CH 6+854 | 2026-09-01 | Eng. Sara Nasser | Approved | 2026-09-04
CTP-WIR-GEO-0062 | 2026-08-30 | Geotechnical | Rock bolt pull-out test | CH 6+345 | 2026-08-30 | Eng. Mark Collins | Approved | 2026-08-31
CTP-WIR-MEP-0058 | 2026-08-30 | MEP | Lighting installation | CH 4+361 | 2026-09-01 | Eng. Hana Saleh | Approved | 2026-09-02
CTP-WIR-MEP-0059 | 2026-08-30 | MEP | Lighting installation | CH 7+389 | 2026-09-01 | Eng. Sara Nasser | Approved | 2026-09-01
CTP-WIR-TUN-0066 | 2026-08-30 | Tunnelling | Segment ring build | CH 9+621 | 2026-08-31 | Eng. Pedro Alves | Approved | 2026-09-01
CTP-WIR-CIV-0064 | 2026-08-31 | Civil | Rebar inspection before concrete | CH 6+912 | 2026-09-01 | Eng. Ali Haddad | Rejected | 2026-09-02 |  | Re-inspection required
CTP-WIR-GEO-0063 | 2026-08-31 | Geotechnical | Borehole drilling & logging | CH 9+237 | 2026-09-01 | Eng. Sara Nasser | Approved | 2026-09-03
CTP-WIR-MEP-0060 | 2026-08-31 | MEP | Lighting installation | CH 4+551 | 2026-09-02 | Eng. Hana Saleh | Approved | 2026-09-05
CTP-WIR-SUR-0066 | 2026-08-31 | Survey | As-built survey | CH 0+608 | 2026-09-02 | Eng. Pedro Alves | Approved | 2026-09-03
CTP-WIR-SUR-0067 | 2026-08-31 | Survey | Settlement monitoring | CH 3+101 | 2026-08-31 | Eng. Sara Nasser | Approved | 2026-09-03
CTP-WIR-CIV-0065 | 2026-09-01 | Civil | Concrete pouring | CH 2+371 | 2026-09-02 | Eng. Sara Nasser | Approved | 2026-09-02
CTP-WIR-CIV-0066 | 2026-09-01 | Civil | Concrete pouring | CH 2+113 | 2026-09-01 | Eng. Sara Nasser | Approved with Comments | 2026-09-04 |  | Minor comments to close
CTP-WIR-GEO-0064 | 2026-09-01 | Geotechnical | Ground anchor installation | CH 7+411 | 2026-09-02 | Eng. Hana Saleh | Approved with Comments | 2026-09-04 |  | Minor comments to close
CTP-WIR-MEP-0061 | 2026-09-01 | MEP | Cable tray installation | CH 0+314 | 2026-09-01 | Eng. Sara Nasser | Approved | 2026-09-01
CTP-WIR-SUR-0068 | 2026-09-01 | Survey | Settlement monitoring | CH 3+179 | 2026-09-01 | Eng. Hana Saleh | Approved | 2026-09-01
CTP-WIR-TUN-0067 | 2026-09-01 | Tunnelling | TBM cutter change | CH 4+835 | 2026-09-03 | Eng. Hana Saleh | Approved | 2026-09-06
CTP-WIR-TUN-0068 | 2026-09-01 | Tunnelling | Segment ring build | CH 9+617 | 2026-09-02 | Eng. Sara Nasser | Approved | 2026-09-02
CTP-WIR-CIV-0067 | 2026-09-02 | Civil | Backfilling & compaction | CH 2+970 | 2026-09-02 | Eng. Pedro Alves | Approved | 2026-09-02
CTP-WIR-GEO-0065 | 2026-09-02 | Geotechnical | Grout injection | CH 9+124 | 2026-09-03 | Eng. Mark Collins | Approved | 2026-09-05
CTP-WIR-MEP-0062 | 2026-09-02 | MEP | Pump station testing | CH 9+064 | 2026-09-02 | Eng. Mark Collins | Approved | 2026-09-02
CTP-WIR-SUR-0069 | 2026-09-02 | Survey | Tunnel alignment survey | CH 6+596 | 2026-09-04 | Eng. Pedro Alves | Approved | 2026-09-05
CTP-WIR-TUN-0069 | 2026-09-02 | Tunnelling | TBM cutter change | CH 5+147 | 2026-09-02 | Eng. Sara Nasser | Approved | 2026-09-05
CTP-WIR-SUR-0070 | 2026-09-03 | Survey | As-built survey | CH 4+428 | 2026-09-04 | Eng. Pedro Alves | Approved | 2026-09-06
CTP-WIR-CIV-0068 | 2026-09-05 | Civil | Rebar inspection before concrete | CH 5+412 | 2026-09-05 | Eng. Ali Haddad | Approved | 2026-09-07
CTP-WIR-GEO-0066 | 2026-09-05 | Geotechnical | Ground anchor installation | CH 9+226 | 2026-09-05 | Eng. Sara Nasser | Approved | 2026-09-07
CTP-WIR-GEO-0067 | 2026-09-05 | Geotechnical | Grout injection | CH 0+811 | 2026-09-07 | Eng. Ali Haddad | Approved with Comments | 2026-09-09 |  | Minor comments to close
CTP-WIR-GEO-0068 | 2026-09-05 | Geotechnical | Rock bolt pull-out test | CH 2+007 | 2026-09-06 | Eng. Pedro Alves | Approved | 2026-09-08
CTP-WIR-TUN-0070 | 2026-09-05 | Tunnelling | Annulus grouting | CH 3+478 | 2026-09-06 | Eng. Sara Nasser | Approved | 2026-09-08
CTP-WIR-GEO-0069 | 2026-09-06 | Geotechnical | Grout injection | CH 2+094 | 2026-09-07 | Eng. Sara Nasser | Approved with Comments | 2026-09-08 |  | Minor comments to close
CTP-WIR-GEO-0070 | 2026-09-06 | Geotechnical | Rock bolt pull-out test | CH 3+163 | 2026-09-07 | Eng. Sara Nasser | Approved | 2026-09-09
CTP-WIR-MEP-0063 | 2026-09-06 | MEP | Ventilation duct alignment | CH 9+376 | 2026-09-07 | Eng. Pedro Alves | Approved | 2026-09-09
CTP-WIR-MEP-0064 | 2026-09-06 | MEP | Pump station testing | CH 8+093 | 2026-09-07 | Eng. Pedro Alves | Approved | 2026-09-07
CTP-WIR-TUN-0071 | 2026-09-06 | Tunnelling | TBM cutter change | CH 8+209 | 2026-09-07 | Eng. Pedro Alves | Approved | 2026-09-09
CTP-WIR-CIV-0069 | 2026-09-07 | Civil | Concrete pouring | CH 1+231 | 2026-09-08 | Eng. Mark Collins | Approved | 2026-09-09
CTP-WIR-CIV-0070 | 2026-09-07 | Civil | Formwork inspection | CH 7+793 | 2026-09-09 | Eng. Sara Nasser | Approved | 2026-09-11
CTP-WIR-GEO-0071 | 2026-09-07 | Geotechnical | Grout injection | CH 1+711 | 2026-09-08 | Eng. Mark Collins | Approved | 2026-09-10
CTP-WIR-GEO-0072 | 2026-09-07 | Geotechnical | Rock bolt pull-out test | CH 1+575 | 2026-09-08 | Eng. Hana Saleh | Approved | 2026-09-08
CTP-WIR-MEP-0065 | 2026-09-07 | MEP | Lighting installation | CH 7+254 | 2026-09-08 | Eng. Sara Nasser | Approved with Comments | 2026-09-08 |  | Minor comments to close
CTP-WIR-SUR-0071 | 2026-09-07 | Survey | Setting-out check | CH 4+934 | 2026-09-07 | Eng. Ali Haddad | Approved | 2026-09-07
CTP-WIR-SUR-0072 | 2026-09-07 | Survey | As-built survey | CH 6+202 | 2026-09-09 | Eng. Mark Collins | Approved | 2026-09-10
CTP-WIR-CIV-0071 | 2026-09-08 | Civil | Rebar inspection before concrete | CH 5+958 | 2026-09-09 | Eng. Ali Haddad | Rejected | 2026-09-12 |  | Re-inspection required
CTP-WIR-GEO-0073 | 2026-09-08 | Geotechnical | Grout injection | CH 9+859 | 2026-09-08 | Eng. Hana Saleh | Approved | 2026-09-09
CTP-WIR-MEP-0066 | 2026-09-08 | MEP | Cable tray installation | CH 3+287 | 2026-09-10 | Eng. Sara Nasser | Rejected | 2026-09-13 |  | Re-inspection required
CTP-WIR-SUR-0073 | 2026-09-08 | Survey | Settlement monitoring | CH 8+756 | 2026-09-10 | Eng. Hana Saleh | Approved | 2026-09-11
CTP-WIR-SUR-0074 | 2026-09-08 | Survey | Setting-out check | CH 6+689 | 2026-09-08 | Eng. Pedro Alves | Approved | 2026-09-09
CTP-WIR-SUR-0075 | 2026-09-08 | Survey | Setting-out check | CH 4+178 | 2026-09-09 | Eng. Mark Collins | Approved | 2026-09-12
CTP-WIR-TUN-0072 | 2026-09-08 | Tunnelling | Segment ring build | CH 9+712 | 2026-09-09 | Eng. Mark Collins | Rejected | 2026-09-12 |  | Re-inspection required
CTP-WIR-TUN-0073 | 2026-09-08 | Tunnelling | Annulus grouting | CH 3+795 | 2026-09-08 | Eng. Ali Haddad | Approved | 2026-09-09
CTP-WIR-GEO-0074 | 2026-09-09 | Geotechnical | Ground anchor installation | CH 5+355 | 2026-09-10 | Eng. Ali Haddad | Rejected | 2026-09-11 |  | Re-inspection required
CTP-WIR-MEP-0067 | 2026-09-09 | MEP | Ventilation duct alignment | CH 4+136 | 2026-09-11 | Eng. Hana Saleh | Approved | 2026-09-12
CTP-WIR-SUR-0076 | 2026-09-09 | Survey | Setting-out check | CH 8+434 | 2026-09-10 | Eng. Mark Collins | Approved | 2026-09-10
CTP-WIR-TUN-0074 | 2026-09-09 | Tunnelling | TBM cutter change | CH 7+243 | 2026-09-10 | Eng. Ali Haddad | Approved | 2026-09-12
CTP-WIR-CIV-0072 | 2026-09-10 | Civil | Rebar inspection before concrete | CH 4+201 | 2026-09-11 | Eng. Sara Nasser | Approved | 2026-09-12
CTP-WIR-GEO-0075 | 2026-09-10 | Geotechnical | Rock bolt pull-out test | CH 3+117 | 2026-09-12 | Eng. Ali Haddad | Approved with Comments | 2026-09-14 |  | Minor comments to close
CTP-WIR-TUN-0075 | 2026-09-10 | Tunnelling | Annulus grouting | CH 7+582 | 2026-09-10 | Eng. Sara Nasser | Approved | 2026-09-12
CTP-WIR-CIV-0073 | 2026-09-12 | Civil | Rebar inspection before concrete | CH 9+270 | 2026-09-14 | Eng. Pedro Alves | Approved | 2026-09-15
CTP-WIR-CIV-0074 | 2026-09-12 | Civil | Concrete pouring | CH 5+008 | 2026-09-14 | Eng. Ali Haddad | Approved | 2026-09-17
CTP-WIR-CIV-0075 | 2026-09-12 | Civil | Formwork inspection | CH 3+080 | 2026-09-13 | Eng. Ali Haddad | Approved | 2026-09-14
CTP-WIR-MEP-0068 | 2026-09-12 | MEP | Ventilation duct alignment | CH 8+866 | 2026-09-13 | Eng. Ali Haddad | Approved | 2026-09-14
CTP-WIR-SUR-0077 | 2026-09-12 | Survey | As-built survey | CH 6+188 | 2026-09-13 | Eng. Sara Nasser | Approved with Comments | 2026-09-14 |  | Minor comments to close
CTP-WIR-SUR-0078 | 2026-09-12 | Survey | As-built survey | CH 5+857 | 2026-09-13 | Eng. Mark Collins | Approved | 2026-09-16
CTP-WIR-SUR-0079 | 2026-09-13 | Survey | Setting-out check | CH 7+490 | 2026-09-15 | Eng. Mark Collins | Approved | 2026-09-15
CTP-WIR-SUR-0080 | 2026-09-13 | Survey | Setting-out check | CH 8+435 | 2026-09-14 | Eng. Sara Nasser | Approved | 2026-09-17
CTP-WIR-TUN-0076 | 2026-09-13 | Tunnelling | Tunnel invert cleaning | CH 7+433 | 2026-09-15 | Eng. Mark Collins | Rejected | 2026-09-16 |  | Re-inspection required
CTP-WIR-TUN-0077 | 2026-09-13 | Tunnelling | TBM cutter change | CH 2+704 | 2026-09-14 | Eng. Mark Collins | Approved | 2026-09-14
CTP-WIR-SUR-0081 | 2026-09-14 | Survey | Settlement monitoring | CH 2+997 | 2026-09-16 | Eng. Hana Saleh | Approved | 2026-09-19
CTP-WIR-TUN-0078 | 2026-09-14 | Tunnelling | TBM cutter change | CH 2+925 | 2026-09-15 | Eng. Pedro Alves | Approved | 2026-09-15
CTP-WIR-TUN-0079 | 2026-09-14 | Tunnelling | TBM cutter change | CH 5+581 | 2026-09-15 | Eng. Pedro Alves | Approved | 2026-09-18
CTP-WIR-CIV-0076 | 2026-09-15 | Civil | Concrete pouring | CH 4+886 | 2026-09-16 | Eng. Hana Saleh | Approved | 2026-09-17
CTP-WIR-GEO-0076 | 2026-09-15 | Geotechnical | Rock bolt pull-out test | CH 9+674 | 2026-09-15 | Eng. Hana Saleh | Approved with Comments | 2026-09-16 |  | Minor comments to close
CTP-WIR-MEP-0069 | 2026-09-15 | MEP | Cable tray installation | CH 3+561 | 2026-09-16 | Eng. Mark Collins | Approved | 2026-09-17
CTP-WIR-SUR-0082 | 2026-09-15 | Survey | As-built survey | CH 8+686 | 2026-09-16 | Eng. Pedro Alves | Approved | 2026-09-17
CTP-WIR-SUR-0083 | 2026-09-15 | Survey | Tunnel alignment survey | CH 8+586 | 2026-09-16 | Eng. Hana Saleh | Approved | 2026-09-17
CTP-WIR-TUN-0080 | 2026-09-15 | Tunnelling | Segment ring build | CH 7+707 | 2026-09-15 | Eng. Mark Collins | Approved with Comments | 2026-09-16 |  | Minor comments to close
CTP-WIR-TUN-0081 | 2026-09-15 | Tunnelling | TBM cutter change | CH 5+542 | 2026-09-16 | Eng. Hana Saleh | Approved | 2026-09-18
CTP-WIR-GEO-0077 | 2026-09-16 | Geotechnical | Borehole drilling & logging | CH 7+137 | 2026-09-16 | Eng. Hana Saleh | Approved with Comments | 2026-09-16 |  | Minor comments to close
CTP-WIR-GEO-0078 | 2026-09-16 | Geotechnical | Grout injection | CH 8+175 | 2026-09-16 | Eng. Hana Saleh | Approved | 2026-09-18
CTP-WIR-GEO-0079 | 2026-09-16 | Geotechnical | Borehole drilling & logging | CH 5+794 | 2026-09-18 | Eng. Pedro Alves | Approved with Comments | 2026-09-19 |  | Minor comments to close
CTP-WIR-MEP-0070 | 2026-09-16 | MEP | Pump station testing | CH 9+117 | 2026-09-16 | Eng. Mark Collins | Approved | 2026-09-17
CTP-WIR-SUR-0084 | 2026-09-16 | Survey | Setting-out check | CH 4+125 | 2026-09-17 | Eng. Sara Nasser | Approved with Comments | 2026-09-17 |  | Minor comments to close
CTP-WIR-TUN-0082 | 2026-09-16 | Tunnelling | Segment ring build | CH 7+307 | 2026-09-16 | Eng. Mark Collins | Approved with Comments | 2026-09-17 |  | Minor comments to close
CTP-WIR-CIV-0077 | 2026-09-17 | Civil | Formwork inspection | CH 4+362 | 2026-09-17 | Eng. Pedro Alves | Approved | 2026-09-18
CTP-WIR-GEO-0080 | 2026-09-17 | Geotechnical | Borehole drilling & logging | CH 9+361 | 2026-09-18 | Eng. Sara Nasser | Approved with Comments | 2026-09-18 |  | Minor comments to close
CTP-WIR-MEP-0071 | 2026-09-17 | MEP | Cable tray installation | CH 7+113 | 2026-09-19 | Eng. Sara Nasser | Approved | 2026-09-19
CTP-WIR-MEP-0072 | 2026-09-17 | MEP | Ventilation duct alignment | CH 6+856 | 2026-09-18 | Eng. Hana Saleh | Approved | 2026-09-19
CTP-WIR-MEP-0073 | 2026-09-17 | MEP | Cable tray installation | CH 7+014 | 2026-09-18 | Eng. Sara Nasser | Approved | 2026-09-19
CTP-WIR-SUR-0085 | 2026-09-17 | Survey | Setting-out check | CH 0+076 | 2026-09-19 | Eng. Hana Saleh | Approved | 2026-09-19
CTP-WIR-SUR-0086 | 2026-09-17 | Survey | Setting-out check | CH 7+402 | 2026-09-19 | Eng. Hana Saleh | Approved with Comments | 2026-09-20 |  | Minor comments to close
CTP-WIR-SUR-0087 | 2026-09-17 | Survey | Setting-out check | CH 3+318 | 2026-09-17 | Eng. Hana Saleh | Approved | 2026-09-20
CTP-WIR-CIV-0078 | 2026-09-19 | Civil | Formwork inspection | CH 7+341 | 2026-09-20 | Eng. Ali Haddad | Approved | 2026-09-23
CTP-WIR-CIV-0079 | 2026-09-19 | Civil | Formwork inspection | CH 0+646 | 2026-09-20 | Eng. Mark Collins | Approved | 2026-09-23
CTP-WIR-CIV-0080 | 2026-09-19 | Civil | Concrete pouring | CH 8+268 | 2026-09-20 | Eng. Hana Saleh | Approved | 2026-09-20
CTP-WIR-GEO-0081 | 2026-09-19 | Geotechnical | Ground anchor installation | CH 7+339 | 2026-09-20 | Eng. Pedro Alves | Approved | 2026-09-21
CTP-WIR-MEP-0074 | 2026-09-19 | MEP | Ventilation duct alignment | CH 3+893 | 2026-09-19 | Eng. Ali Haddad | Approved | 2026-09-20
CTP-WIR-MEP-0075 | 2026-09-19 | MEP | Ventilation duct alignment | CH 5+521 | 2026-09-20 | Eng. Sara Nasser | Rejected | 2026-09-21 |  | Re-inspection required
CTP-WIR-SUR-0088 | 2026-09-19 | Survey | Settlement monitoring | CH 5+904 | 2026-09-21 | Eng. Hana Saleh | Approved | 2026-09-22
CTP-WIR-SUR-0089 | 2026-09-19 | Survey | Setting-out check | CH 5+154 | 2026-09-20 | Eng. Mark Collins | Approved with Comments | 2026-09-21 |  | Minor comments to close
CTP-WIR-TUN-0083 | 2026-09-19 | Tunnelling | Segment ring build | CH 8+924 | 2026-09-20 | Eng. Mark Collins | Rejected | 2026-09-20 |  | Re-inspection required
CTP-WIR-CIV-0081 | 2026-09-20 | Civil | Concrete pouring | CH 9+790 | 2026-09-22 | Eng. Mark Collins | Approved | 2026-09-24
CTP-WIR-CIV-0082 | 2026-09-20 | Civil | Concrete pouring | CH 4+744 | 2026-09-20 | Eng. Ali Haddad | Approved | 2026-09-21
CTP-WIR-SUR-0090 | 2026-09-20 | Survey | Tunnel alignment survey | CH 3+247 | 2026-09-21 | Eng. Mark Collins | Approved with Comments | 2026-09-21 |  | Minor comments to close
CTP-WIR-TUN-0084 | 2026-09-20 | Tunnelling | Tunnel invert cleaning | CH 9+361 | 2026-09-20 | Eng. Sara Nasser | Approved | 2026-09-21
CTP-WIR-TUN-0085 | 2026-09-20 | Tunnelling | TBM cutter change | CH 7+326 | 2026-09-22 | Eng. Sara Nasser | Approved with Comments | 2026-09-22 |  | Minor comments to close
CTP-WIR-TUN-0086 | 2026-09-20 | Tunnelling | Segment ring build | CH 4+242 | 2026-09-21 | Eng. Mark Collins | Approved | 2026-09-22
CTP-WIR-GEO-0082 | 2026-09-21 | Geotechnical | Grout injection | CH 5+736 | 2026-09-21 | Eng. Ali Haddad | Approved | 2026-09-24
CTP-WIR-MEP-0076 | 2026-09-21 | MEP | Lighting installation | CH 2+058 | 2026-09-23 | Eng. Ali Haddad | Approved | 2026-09-24
CTP-WIR-MEP-0077 | 2026-09-21 | MEP | Lighting installation | CH 7+612 | 2026-09-21 | Eng. Sara Nasser | Approved | 2026-09-22
CTP-WIR-SUR-0091 | 2026-09-21 | Survey | As-built survey | CH 9+669 | 2026-09-21 | Eng. Ali Haddad | Approved | 2026-09-22
CTP-WIR-SUR-0092 | 2026-09-21 | Survey | Tunnel alignment survey | CH 2+095 | 2026-09-23 | Eng. Mark Collins | Approved | 2026-09-24
CTP-WIR-SUR-0093 | 2026-09-21 | Survey | As-built survey | CH 5+833 | 2026-09-22 | Eng. Pedro Alves | Approved | 2026-09-22
CTP-WIR-TUN-0087 | 2026-09-21 | Tunnelling | Annulus grouting | CH 3+329 | 2026-09-21 | Eng. Ali Haddad | Approved | 2026-09-21
CTP-WIR-GEO-0083 | 2026-09-22 | Geotechnical | Grout injection | CH 9+338 | 2026-09-23 | Eng. Hana Saleh | Approved | 2026-09-26
CTP-WIR-MEP-0078 | 2026-09-22 | MEP | Ventilation duct alignment | CH 2+643 | 2026-09-22 | Eng. Pedro Alves | Approved | 2026-09-23
CTP-WIR-SUR-0094 | 2026-09-22 | Survey | Tunnel alignment survey | CH 2+125 | 2026-09-22 | Eng. Hana Saleh | Rejected | 2026-09-25 |  | Re-inspection required
CTP-WIR-SUR-0095 | 2026-09-22 | Survey | As-built survey | CH 4+962 | 2026-09-23 | Eng. Mark Collins | Approved | 2026-09-24
CTP-WIR-TUN-0088 | 2026-09-22 | Tunnelling | Tunnel invert cleaning | CH 8+723 | 2026-09-22 | Eng. Hana Saleh | Approved with Comments | 2026-09-23 |  | Minor comments to close
CTP-WIR-TUN-0089 | 2026-09-22 | Tunnelling | Annulus grouting | CH 4+135 | 2026-09-23 | Eng. Ali Haddad | Approved | 2026-09-26
CTP-WIR-GEO-0084 | 2026-09-23 | Geotechnical | Ground anchor installation | CH 3+452 | 2026-09-24 | Eng. Mark Collins | Approved | 2026-09-25
CTP-WIR-GEO-0085 | 2026-09-23 | Geotechnical | Rock bolt pull-out test | CH 7+217 | 2026-09-24 | Eng. Ali Haddad | Rejected | 2026-09-26 |  | Re-inspection required
CTP-WIR-SUR-0096 | 2026-09-23 | Survey | As-built survey | CH 6+658 | 2026-09-24 | Eng. Sara Nasser | Approved | 2026-09-25
CTP-WIR-TUN-0090 | 2026-09-23 | Tunnelling | TBM cutter change | CH 5+061 | 2026-09-23 | Eng. Hana Saleh | Approved with Comments | 2026-09-25 |  | Minor comments to close
CTP-WIR-TUN-0091 | 2026-09-23 | Tunnelling | Annulus grouting | CH 3+031 | 2026-09-25 | Eng. Ali Haddad | Approved | 2026-09-27
CTP-WIR-CIV-0083 | 2026-09-24 | Civil | Concrete pouring | CH 3+871 | 2026-09-26 | Eng. Ali Haddad | Approved | 2026-09-26
CTP-WIR-GEO-0086 | 2026-09-24 | Geotechnical | Rock bolt pull-out test | CH 2+488 | 2026-09-26 | Eng. Mark Collins | Approved | 2026-09-29
CTP-WIR-GEO-0087 | 2026-09-24 | Geotechnical | Grout injection | CH 0+497 | 2026-09-25 | Eng. Mark Collins | Approved | 2026-09-26
CTP-WIR-MEP-0079 | 2026-09-24 | MEP | Lighting installation | CH 7+699 | 2026-09-25 | Eng. Ali Haddad | Approved | 2026-09-26
CTP-WIR-SUR-0097 | 2026-09-24 | Survey | Setting-out check | CH 9+240 | 2026-09-26 | Eng. Ali Haddad | Approved with Comments | 2026-09-26 |  | Minor comments to close
CTP-WIR-TUN-0092 | 2026-09-24 | Tunnelling | Segment ring build | CH 4+701 | 2026-09-26 | Eng. Ali Haddad | Approved | 2026-09-27
CTP-WIR-TUN-0093 | 2026-09-24 | Tunnelling | Annulus grouting | CH 2+933 | 2026-09-25 | Eng. Mark Collins | Rejected | 2026-09-25 |  | Re-inspection required
CTP-WIR-CIV-0084 | 2026-09-26 | Civil | Concrete pouring | CH 0+049 | 2026-09-27 | Eng. Ali Haddad | Approved | 2026-09-27
CTP-WIR-MEP-0080 | 2026-09-26 | MEP | Ventilation duct alignment | CH 5+993 | 2026-09-28 | Eng. Mark Collins | Rejected | 2026-09-28 |  | Re-inspection required
CTP-WIR-SUR-0098 | 2026-09-26 | Survey | Tunnel alignment survey | CH 4+275 | 2026-09-27 | Eng. Ali Haddad | Approved with Comments | 2026-09-27 |  | Minor comments to close
CTP-WIR-SUR-0099 | 2026-09-26 | Survey | As-built survey | CH 8+974 | 2026-09-27 | Eng. Sara Nasser | Approved | 2026-09-29
CTP-WIR-TUN-0094 | 2026-09-26 | Tunnelling | Segment ring build | CH 8+438 | 2026-09-26 | Eng. Mark Collins | Rejected | 2026-09-27 |  | Re-inspection required
CTP-WIR-TUN-0095 | 2026-09-26 | Tunnelling | Segment ring build | CH 8+512 | 2026-09-27 | Eng. Hana Saleh | Approved | 2026-09-28
CTP-WIR-CIV-0085 | 2026-09-27 | Civil | Backfilling & compaction | CH 5+706 | 2026-09-29 | Eng. Sara Nasser | Approved | 2026-10-02
CTP-WIR-CIV-0086 | 2026-09-27 | Civil | Formwork inspection | CH 6+392 | 2026-09-29 | Eng. Pedro Alves | Approved | 2026-10-02
CTP-WIR-MEP-0081 | 2026-09-27 | MEP | Pump station testing | CH 8+684 | 2026-09-28 | Eng. Pedro Alves | Approved | 2026-09-30
CTP-WIR-SUR-0100 | 2026-09-27 | Survey | Settlement monitoring | CH 8+350 | 2026-09-27 | Eng. Mark Collins | Approved | 2026-09-29
CTP-WIR-SUR-0101 | 2026-09-27 | Survey | As-built survey | CH 6+999 | 2026-09-29 | Eng. Hana Saleh | Approved | 2026-09-29
CTP-WIR-SUR-0102 | 2026-09-27 | Survey | As-built survey | CH 3+946 | 2026-09-28 | Eng. Sara Nasser | Approved | 2026-10-01
CTP-WIR-TUN-0096 | 2026-09-27 | Tunnelling | Annulus grouting | CH 3+622 | 2026-09-29 | Eng. Hana Saleh | Approved with Comments | 2026-09-29 |  | Minor comments to close
CTP-WIR-TUN-0097 | 2026-09-27 | Tunnelling | Segment ring build | CH 1+088 | 2026-09-29 | Eng. Ali Haddad | Rejected | 2026-09-30 |  | Re-inspection required
CTP-WIR-GEO-0088 | 2026-09-28 | Geotechnical | Ground anchor installation | CH 8+603 | 2026-09-30 | Eng. Hana Saleh | Approved with Comments | 2026-10-01 |  | Minor comments to close
CTP-WIR-GEO-0089 | 2026-09-28 | Geotechnical | Grout injection | CH 8+372 | 2026-09-29 | Eng. Hana Saleh | Rejected | 2026-09-29 |  | Re-inspection required
CTP-WIR-MEP-0082 | 2026-09-28 | MEP | Cable tray installation | CH 4+384 | 2026-09-30 | Eng. Sara Nasser | Approved | 2026-10-01
CTP-WIR-SUR-0103 | 2026-09-28 | Survey | As-built survey | CH 4+405 | 2026-09-29 | Eng. Pedro Alves | Approved | 2026-09-29
CTP-WIR-TUN-0098 | 2026-09-28 | Tunnelling | Segment ring build | CH 2+655 | 2026-09-29 | Eng. Sara Nasser | Approved | 2026-10-01
CTP-WIR-GEO-0090 | 2026-09-29 | Geotechnical | Borehole drilling & logging | CH 8+153 | 2026-10-01 | Eng. Mark Collins | Approved | 2026-10-02
CTP-WIR-GEO-0091 | 2026-09-29 | Geotechnical | Rock bolt pull-out test | CH 9+379 | 2026-09-30 | Eng. Pedro Alves | Approved | 2026-10-01
CTP-WIR-MEP-0083 | 2026-09-29 | MEP | Lighting installation | CH 7+093 | 2026-09-30 | Eng. Ali Haddad | Approved | 2026-10-01
CTP-WIR-TUN-0099 | 2026-09-29 | Tunnelling | Annulus grouting | CH 9+182 | 2026-09-29 | Eng. Hana Saleh | Approved | 2026-09-29
CTP-WIR-CIV-0087 | 2026-09-30 | Civil | Concrete pouring | CH 9+830 | 2026-10-01 | Eng. Sara Nasser | Rejected | 2026-10-03 |  | Re-inspection required
CTP-WIR-GEO-0092 | 2026-09-30 | Geotechnical | Ground anchor installation | CH 0+734 | 2026-10-01 | Eng. Pedro Alves | Approved | 2026-10-02
CTP-WIR-MEP-0084 | 2026-09-30 | MEP | Cable tray installation | CH 9+381 | 2026-10-01 | Eng. Mark Collins | Rejected | 2026-10-02 |  | Re-inspection required
CTP-WIR-MEP-0085 | 2026-09-30 | MEP | Lighting installation | CH 7+388 | 2026-10-01 | Eng. Hana Saleh | Approved with Comments | 2026-10-01 |  | Minor comments to close
CTP-WIR-SUR-0104 | 2026-09-30 | Survey | Settlement monitoring | CH 7+957 | 2026-09-30 | Eng. Pedro Alves | Approved | 2026-10-03
CTP-WIR-CIV-0088 | 2026-10-01 | Civil | Rebar inspection before concrete | CH 6+554 | 2026-10-01 | Eng. Sara Nasser | Approved | 2026-10-02
CTP-WIR-GEO-0093 | 2026-10-01 | Geotechnical | Ground anchor installation | CH 7+407 | 2026-10-03 | Eng. Mark Collins | Approved | 2026-10-03
CTP-WIR-MEP-0086 | 2026-10-01 | MEP | Cable tray installation | CH 9+465 | 2026-10-01 | Eng. Mark Collins | Approved | 2026-10-02
CTP-WIR-MEP-0087 | 2026-10-01 | MEP | Lighting installation | CH 8+707 | 2026-10-02 | Eng. Hana Saleh | Approved | 2026-10-02
CTP-WIR-TUN-0100 | 2026-10-01 | Tunnelling | Segment ring build | CH 1+226 | 2026-10-03 | Eng. Hana Saleh | Approved with Comments | 2026-10-03 |  | Minor comments to close
CTP-WIR-CIV-0089 | 2026-10-03 | Civil | Rebar inspection before concrete | CH 8+268 | 2026-10-04 | Eng. Sara Nasser | Rejected | 2026-10-05 |  | Re-inspection required
CTP-WIR-CIV-0090 | 2026-10-03 | Civil | Backfilling & compaction | CH 8+404 | 2026-10-05 | Eng. Ali Haddad | Approved | 2026-10-06
CTP-WIR-CIV-0091 | 2026-10-03 | Civil | Concrete pouring | CH 6+877 | 2026-10-04 | Eng. Sara Nasser | Approved | 2026-10-06
CTP-WIR-GEO-0094 | 2026-10-03 | Geotechnical | Grout injection | CH 5+342 | 2026-10-03 | Eng. Hana Saleh | Approved with Comments | 2026-10-04 |  | Minor comments to close
CTP-WIR-SUR-0105 | 2026-10-03 | Survey | As-built survey | CH 9+144 | 2026-10-04 | Eng. Sara Nasser | Rejected | 2026-10-06 |  | Re-inspection required
CTP-WIR-CIV-0092 | 2026-10-04 | Civil | Backfilling & compaction | CH 8+069 | 2026-10-04 | Eng. Hana Saleh | Approved with Comments | 2026-10-04 |  | Minor comments to close
CTP-WIR-CIV-0093 | 2026-10-04 | Civil | Formwork inspection | CH 7+298 | 2026-10-05 | Eng. Mark Collins | Approved | 2026-10-06
CTP-WIR-CIV-0094 | 2026-10-04 | Civil | Formwork inspection | CH 3+899 | 2026-10-06 | Eng. Ali Haddad | Approved | 2026-10-08
CTP-WIR-MEP-0088 | 2026-10-04 | MEP | Ventilation duct alignment | CH 9+509 | 2026-10-04 | Eng. Ali Haddad | Approved | 2026-10-04
CTP-WIR-MEP-0089 | 2026-10-04 | MEP | Ventilation duct alignment | CH 3+547 | 2026-10-05 | Eng. Mark Collins | Approved | 2026-10-06
CTP-WIR-SUR-0106 | 2026-10-04 | Survey | Tunnel alignment survey | CH 1+206 | 2026-10-05 | Eng. Ali Haddad | Approved | 2026-10-07
CTP-WIR-SUR-0107 | 2026-10-04 | Survey | Settlement monitoring | CH 7+702 | 2026-10-06 | Eng. Mark Collins | Approved | 2026-10-07
CTP-WIR-CIV-0095 | 2026-10-05 | Civil | Rebar inspection before concrete | CH 6+997 | 2026-10-06 | Eng. Sara Nasser | Approved | 2026-10-07
CTP-WIR-GEO-0095 | 2026-10-05 | Geotechnical | Grout injection | CH 4+776 | 2026-10-06 | Eng. Hana Saleh | Approved | 2026-10-08
CTP-WIR-GEO-0096 | 2026-10-05 | Geotechnical | Rock bolt pull-out test | CH 4+933 | 2026-10-06 | Eng. Sara Nasser | Approved with Comments | 2026-10-07 |  | Minor comments to close
CTP-WIR-MEP-0090 | 2026-10-05 | MEP | Pump station testing | CH 1+039 | 2026-10-07 | Eng. Ali Haddad | Approved | 2026-10-09
CTP-WIR-MEP-0091 | 2026-10-05 | MEP | Pump station testing | CH 8+074 | 2026-10-06 | Eng. Pedro Alves | Rejected | 2026-10-09 |  | Re-inspection required
CTP-WIR-SUR-0108 | 2026-10-05 | Survey | As-built survey | CH 3+496 | 2026-10-07 | Eng. Sara Nasser | Approved with Comments | 2026-10-07 |  | Minor comments to close
CTP-WIR-TUN-0101 | 2026-10-05 | Tunnelling | Tunnel invert cleaning | CH 1+202 | 2026-10-06 | Eng. Mark Collins | Approved | 2026-10-09
CTP-WIR-CIV-0096 | 2026-10-06 | Civil | Formwork inspection | CH 4+051 | 2026-10-06 | Eng. Sara Nasser | Approved | 2026-10-07
CTP-WIR-GEO-0097 | 2026-10-06 | Geotechnical | Rock bolt pull-out test | CH 9+946 | 2026-10-06 | Eng. Ali Haddad | Approved | 2026-10-07
CTP-WIR-MEP-0092 | 2026-10-06 | MEP | Ventilation duct alignment | CH 8+115 | 2026-10-08 | Eng. Hana Saleh | Pending
CTP-WIR-MEP-0093 | 2026-10-06 | MEP | Lighting installation | CH 9+099 | 2026-10-08 | Eng. Mark Collins | Approved | 2026-10-11
CTP-WIR-SUR-0109 | 2026-10-06 | Survey | Setting-out check | CH 2+368 | 2026-10-07 | Eng. Ali Haddad | Pending
CTP-WIR-TUN-0102 | 2026-10-06 | Tunnelling | Annulus grouting | CH 1+806 | 2026-10-08 | Eng. Ali Haddad | Approved with Comments | 2026-10-09 |  | Minor comments to close
CTP-WIR-GEO-0098 | 2026-10-07 | Geotechnical | Grout injection | CH 3+119 | 2026-10-09 | Eng. Pedro Alves | Approved | 2026-10-09
CTP-WIR-MEP-0094 | 2026-10-07 | MEP | Ventilation duct alignment | CH 3+744 | 2026-10-08 | Eng. Ali Haddad | Approved | 2026-10-09
CTP-WIR-MEP-0095 | 2026-10-07 | MEP | Ventilation duct alignment | CH 0+500 | 2026-10-07 | Eng. Mark Collins | Pending
CTP-WIR-MEP-0096 | 2026-10-07 | MEP | Lighting installation | CH 0+434 | 2026-10-07 | Eng. Hana Saleh | Approved | 2026-10-08
CTP-WIR-SUR-0110 | 2026-10-07 | Survey | Setting-out check | CH 3+239 | 2026-10-08 | Eng. Hana Saleh | Approved | 2026-10-11
CTP-WIR-TUN-0103 | 2026-10-07 | Tunnelling | Annulus grouting | CH 0+518 | 2026-10-08 | Eng. Sara Nasser | Approved | 2026-10-11
CTP-WIR-CIV-0097 | 2026-10-08 | Civil | Formwork inspection | CH 2+751 | 2026-10-10 | Eng. Mark Collins | Approved | 2026-10-11
CTP-WIR-GEO-0099 | 2026-10-08 | Geotechnical | Grout injection | CH 1+042 | 2026-10-08 | Eng. Hana Saleh | Approved | 2026-10-09
CTP-WIR-GEO-0100 | 2026-10-08 | Geotechnical | Grout injection | CH 9+942 | 2026-10-09 | Eng. Ali Haddad | Approved | 2026-10-11
CTP-WIR-MEP-0097 | 2026-10-08 | MEP | Ventilation duct alignment | CH 5+596 | 2026-10-08 | Eng. Pedro Alves | Approved with Comments | 2026-10-08 |  | Minor comments to close
CTP-WIR-MEP-0098 | 2026-10-08 | MEP | Cable tray installation | CH 4+926 | 2026-10-10 | Eng. Pedro Alves | Pending
CTP-WIR-SUR-0111 | 2026-10-08 | Survey | Tunnel alignment survey | CH 4+765 | 2026-10-09 | Eng. Ali Haddad | Approved with Comments | 2026-10-12 |  | Minor comments to close
CTP-WIR-SUR-0112 | 2026-10-08 | Survey | Settlement monitoring | CH 3+601 | 2026-10-09 | Eng. Hana Saleh | Approved with Comments | 2026-10-10 |  | Minor comments to close
CTP-WIR-TUN-0104 | 2026-10-08 | Tunnelling | Tunnel invert cleaning | CH 1+002 | 2026-10-09 | Eng. Ali Haddad | Rejected | 2026-10-10 |  | Re-inspection required
CTP-WIR-TUN-0105 | 2026-10-08 | Tunnelling | Segment ring build | CH 9+651 | 2026-10-10 | Eng. Mark Collins | Approved | 2026-10-10
CTP-WIR-CIV-0098 | 2026-10-10 | Civil | Rebar inspection before concrete | CH 6+415 | 2026-10-10 | Eng. Mark Collins | Approved with Comments | 2026-10-11 |  | Minor comments to close
CTP-WIR-SUR-0113 | 2026-10-10 | Survey | As-built survey | CH 0+299 | 2026-10-10 | Eng. Ali Haddad | Approved with Comments | 2026-10-13 |  | Minor comments to close
CTP-WIR-TUN-0106 | 2026-10-10 | Tunnelling | Annulus grouting | CH 4+004 | 2026-10-11 | Eng. Pedro Alves | Rejected | 2026-10-13 |  | Re-inspection required
CTP-WIR-TUN-0107 | 2026-10-10 | Tunnelling | Annulus grouting | CH 6+420 | 2026-10-10 | Eng. Pedro Alves | Approved with Comments | 2026-10-12 |  | Minor comments to close
CTP-WIR-CIV-0099 | 2026-10-11 | Civil | Rebar inspection before concrete | CH 8+009 | 2026-10-12 | Eng. Mark Collins | Rejected | 2026-10-14 |  | Re-inspection required
CTP-WIR-CIV-0100 | 2026-10-11 | Civil | Rebar inspection before concrete | CH 5+692 | 2026-10-11 | Eng. Hana Saleh | Approved | 2026-10-12
CTP-WIR-CIV-0101 | 2026-10-11 | Civil | Backfilling & compaction | CH 4+682 | 2026-10-13 | Eng. Ali Haddad | Pending
CTP-WIR-GEO-0101 | 2026-10-11 | Geotechnical | Grout injection | CH 3+123 | 2026-10-12 | Eng. Ali Haddad | Approved | 2026-10-14
CTP-WIR-GEO-0102 | 2026-10-11 | Geotechnical | Grout injection | CH 5+980 | 2026-10-13 | Eng. Sara Nasser | Approved | 2026-10-14
CTP-WIR-GEO-0103 | 2026-10-11 | Geotechnical | Ground anchor installation | CH 6+315 | 2026-10-12 | Eng. Sara Nasser | Approved with Comments | 2026-10-14 |  | Minor comments to close
CTP-WIR-MEP-0099 | 2026-10-11 | MEP | Cable tray installation | CH 0+058 | 2026-10-11 | Eng. Hana Saleh | Approved | 2026-10-12
CTP-WIR-MEP-0100 | 2026-10-11 | MEP | Lighting installation | CH 9+767 | 2026-10-13 | Eng. Ali Haddad | Approved with Comments | 2026-10-14 |  | Minor comments to close
CTP-WIR-SUR-0114 | 2026-10-11 | Survey | Setting-out check | CH 4+147 | 2026-10-13 | Eng. Hana Saleh | Pending
CTP-WIR-SUR-0115 | 2026-10-11 | Survey | Setting-out check | CH 4+642 | 2026-10-11 | Eng. Sara Nasser | Approved | 2026-10-14
CTP-WIR-SUR-0116 | 2026-10-11 | Survey | As-built survey | CH 6+504 | 2026-10-11 | Eng. Sara Nasser | Rejected | 2026-10-11 |  | Re-inspection required
CTP-WIR-TUN-0108 | 2026-10-11 | Tunnelling | Tunnel invert cleaning | CH 4+677 | 2026-10-12 | Eng. Hana Saleh | Rejected | 2026-10-13 |  | Re-inspection required
CTP-WIR-CIV-0102 | 2026-10-12 | Civil | Concrete pouring | CH 0+601 | 2026-10-13 | Eng. Pedro Alves | Pending
CTP-WIR-GEO-0104 | 2026-10-12 | Geotechnical | Borehole drilling & logging | CH 3+528 | 2026-10-14 | Eng. Mark Collins | Approved | 2026-10-14
CTP-WIR-MEP-0101 | 2026-10-12 | MEP | Lighting installation | CH 3+948 | 2026-10-14 | Eng. Hana Saleh | Pending
CTP-WIR-SUR-0117 | 2026-10-12 | Survey | Settlement monitoring | CH 7+677 | 2026-10-13 | Eng. Ali Haddad | Approved | 2026-10-14
CTP-WIR-SUR-0118 | 2026-10-12 | Survey | As-built survey | CH 6+542 | 2026-10-13 | Eng. Ali Haddad | Pending
CTP-WIR-TUN-0109 | 2026-10-12 | Tunnelling | Annulus grouting | CH 3+635 | 2026-10-13 | Eng. Pedro Alves | Approved | 2026-10-14
CTP-WIR-TUN-0110 | 2026-10-12 | Tunnelling | Tunnel invert cleaning | CH 4+370 | 2026-10-14 | Eng. Sara Nasser | Pending
CTP-WIR-CIV-0103 | 2026-10-13 | Civil | Concrete pouring | CH 9+312 | 2026-10-13 | Eng. Hana Saleh | Pending
CTP-WIR-CIV-0104 | 2026-10-13 | Civil | Rebar inspection before concrete | CH 3+907 | 2026-10-14 | Eng. Hana Saleh | Pending
CTP-WIR-MEP-0102 | 2026-10-13 | MEP | Cable tray installation | CH 2+990 | 2026-10-15 | Eng. Pedro Alves | Rejected | 2026-10-14 |  | Re-inspection required
CTP-WIR-SUR-0119 | 2026-10-13 | Survey | As-built survey | CH 7+825 | 2026-10-14 | Eng. Sara Nasser | Pending
CTP-WIR-CIV-0105 | 2026-10-14 | Civil | Concrete pouring | CH 6+219 | 2026-10-15 | Eng. Mark Collins | Pending
CTP-WIR-GEO-0105 | 2026-10-14 | Geotechnical | Rock bolt pull-out test | CH 8+423 | 2026-10-15 | Eng. Mark Collins | Pending
CTP-WIR-GEO-0106 | 2026-10-14 | Geotechnical | Ground anchor installation | CH 1+946 | 2026-10-15 | Eng. Ali Haddad | Pending
CTP-WIR-MEP-0103 | 2026-10-14 | MEP | Cable tray installation | CH 4+920 | 2026-10-15 | Eng. Pedro Alves | Pending
CTP-WIR-MEP-0104 | 2026-10-14 | MEP | Pump station testing | CH 6+627 | 2026-10-15 | Eng. Ali Haddad | Pending
CTP-WIR-SUR-0120 | 2026-10-14 | Survey | Tunnel alignment survey | CH 3+316 | 2026-10-15 | Eng. Sara Nasser | Pending
CTP-WIR-SUR-0121 | 2026-10-14 | Survey | Tunnel alignment survey | CH 8+073 | 2026-10-14 | Eng. Sara Nasser | Pending
Formulas:
Days Open = IF([Status]="Pending",TODAY()-[Submitted],IF([Response Date]="","",[Response Date]-[Submitted]))

## Daily Log
Daily WIR Submission Log
Submitted per discipline per working day (Friday off) • Formulas count directly from the WIR Register
Date | Day | Geotechnical | Civil | Tunnelling | MEP | Survey | Total
2026-10-14
2026-10-13
2026-10-12
2026-10-11
2026-10-10
2026-10-08
2026-10-07
2026-10-06
2026-10-05
2026-10-04
2026-10-03
2026-10-01
2026-09-30
2026-09-29
2026-09-28
2026-09-27
2026-09-26
2026-09-24
2026-09-23
2026-09-22
2026-09-21
2026-09-20
2026-09-19
2026-09-17
2026-09-16
2026-09-15
2026-09-14
2026-09-13
2026-09-12
2026-09-10
2026-09-09
2026-09-08
2026-09-07
2026-09-06
2026-09-05
2026-09-03
2026-09-02
2026-09-01
2026-08-31
2026-08-30
2026-08-29
2026-08-27
2026-08-26
2026-08-25
2026-08-24
2026-08-23
2026-08-22
2026-08-20
2026-08-19
2026-08-18
2026-08-17
2026-08-16
2026-08-15
2026-08-13
2026-08-12
2026-08-11
2026-08-10
2026-08-09
2026-08-08
2026-08-06
2026-08-05
2026-08-04
2026-08-03
2026-08-02
2026-08-01
2026-07-30
2026-07-29
2026-07-28
2026-07-27
2026-07-26
2026-07-25
2026-07-23
2026-07-22
2026-07-21
2026-07-20
2026-07-19
2026-07-18
2026-07-16
2026-07-15
2026-07-14
2026-07-13
2026-07-12
2026-07-11
2026-07-09
2026-07-08
2026-07-07
2026-07-06
2026-07-05
2026-07-04
2026-07-02
2026-07-01