## Executive Dashboard
MANAGEMENT ACTION TRACKER — EXECUTIVE KPI DASHBOARD
Executive Action Control ¦ Priority • Aging • Department Follow-up ¦ Portfolio Demonstration
TOTAL ACTIONS |  | OPEN ACTIONS |  | OVERDUE ACTIONS | HIGH PRIORITY | AVG COMPLETION
12 |  | 9 |  | 2 | 5 | 68.33%
1. ACTION STATUS OVERVIEW
Status | Actions
Pending | 2
In Progress | 5
Completed | 3
Overdue | 2
Priority | Actions
High | 5
Medium | 5
Low | 2
2. DEPARTMENT FOLLOW-UP & OPEN ACTION EXPOSURE
Department | Total | Open | Overdue
Finance | 2 | 2 | 1
HR / Admin | 2 | 2 | 0
Logistics | 2 | 1 | 0
Procurement | 2 | 2 | 1
Executive Office | 2 | 1 | 0
Facilities | 1 | 0 | 0
Operations | 1 | 1 | 0
3. MANAGEMENT CONTROL NOTES
• High-priority and overdue actions should be reviewed first during management follow-up.
• The Action Tracker sheet is the operational source; dashboard KPIs update from the tracker formulas.
• Days Remaining and Aging are dynamic and recalculate using TODAY().
• Sample data is fictional/anonymized for portfolio demonstration and contains no confidential project information.

## Action Tracker
Action ID | Action / Deliverable | Department | Responsible Person | Priority | Status | Date Raised | Due Date | Days Remaining | Aging (Days) | Completion % | Risk / Impact | Management Remarks
ACT-001 | Close pending subcontractor payment reconciliation | Finance | A. Rahman | High | In Progress | 2026-07-01 | 2026-07-28 | 1 | 26 | 75% | High | Final supporting documents under review
ACT-002 | Finalize July manpower demobilization list | HR / Admin | S. Ahmed | High | Pending | 2026-07-05 | 2026-07-30 | 3 | 22 | 40% | High | Management confirmation required
ACT-003 | Submit equipment release schedule | Logistics | M. Khan | Medium | In Progress | 2026-07-07 | 2026-08-03 | 7 | 20 | 60% | Medium | Coordinate with site teams
ACT-004 | Resolve received-not-invoiced items | Procurement | T. Hassan | High | Overdue | 2026-06-18 | 2026-07-20 | -7 | 39 | 55% | High | Supplier invoices pending
ACT-005 | Update executive weekly KPI pack | Executive Office | S. Ahmed | Medium | Completed | 2026-07-15 | 2026-07-22 | -5 | 12 | 100% | Low | Issued for management review
ACT-006 | Close outstanding PO receiving | Procurement | G. Ali | Medium | In Progress | 2026-07-09 | 2026-07-31 | 4 | 18 | 70% | Medium | Receiving verification ongoing
ACT-007 | Confirm August release dates | HR / Admin | R. Celik | High | Pending | 2026-07-10 | 2026-07-27 | 0 | 17 | 25% | High | Awaiting department heads
ACT-008 | Prepare accommodation occupancy forecast | Facilities | M. Albalwi | Low | Completed | 2026-07-12 | 2026-07-24 | -3 | 15 | 100% | Low | Forecast completed
ACT-009 | Verify Friday workforce attendance | Operations | D. Rathour | Medium | In Progress | 2026-07-18 | 2026-07-29 | 2 | 9 | 80% | Medium | Final exceptions under review
ACT-010 | Close advance payment reconciliation | Finance | A. Ramzi | High | Overdue | 2026-06-25 | 2026-07-18 | -9 | 32 | 50% | High | Escalated for closure
ACT-011 | Issue monthly fleet maintenance summary | Logistics | M. Khan | Low | Completed | 2026-07-10 | 2026-07-25 | -2 | 17 | 100% | Low | Submitted
ACT-012 | Finalize management action log | Executive Office | S. Ahmed | Medium | In Progress | 2026-07-20 | 2026-08-01 | 5 | 7 | 65% | Medium | Open actions being consolidated
Formulas:
Days Remaining = [Due Date]-TODAY()
Aging (Days) = TODAY()-[Date Raised]