## Executive Dashboard
DOCUMENT CONTROL & CORRESPONDENCE COMMAND CENTER
Executive Document Control ¦ Correspondence • Aging • Actions • Approvals • Portfolio Demonstration
TOTAL CORRESPONDENCE |  | ACTIVE ITEMS |  | OVERDUE >14 DAYS |  | CLOSED | DOCUMENTS
60 |  | 40 |  | 32 |  | 20 | 40
1. CORRESPONDENCE STATUS & PRIORITY |  |  |  | 2. ACTIVE EXPOSURE BY DEPARTMENT
STATUS | COUNT | PRIORITY | COUNT | DEPARTMENT | ACTIVE
Open | 17 | Critical | 5 | Management | 5
Under Review | 14 | High | 16 | Engineering | 5
Action Required | 9 | Medium | 23 | Contracts | 6
Closed | 20 | Low | 16 | Procurement | 4
|  |  |  | Construction | 2
|  |  |  | Document Control | 10
|  |  |  | Finance | 3
|  |  |  | HSE | 5
3. MANAGEMENT CONTROL NOTES
• Prioritize overdue and critical correspondence during management follow-up.
• Correspondence Register is the operational source; dashboard KPIs update automatically.
• Days Open and Aging Band recalculate dynamically using TODAY().
• Document Register provides revision, approval-status and next-action visibility.
• Hyperlink fields demonstrate direct document access; sample links/data are fictional for portfolio use.

## Correspondence Register
Ref No. | Direction | Date | Type | Subject | From / To | Department | Responsible | Priority | Response Due | Days Open | Status | Aging Band | Document Link | Remarks
COR-2026-0001 | Incoming | 2026-07-10 | Letter | Procurement technical clarification | External Stakeholder | HSE | HSE Lead | High | 2026-07-17 | 17 | Open | 15-30 Days | documents/COR-2026-0001.pdf | Synthetic portfolio sample
COR-2026-0002 | Outgoing | 2026-06-13 | Memo | Material approval package | Project Team | Management | Project Controls | High | 2026-06-18 | 44 | Open | 31+ Days | documents/COR-2026-0002.pdf | Synthetic portfolio sample
COR-2026-0003 | Incoming | 2026-05-18 | Letter | Management instruction and action follow-up | External Stakeholder | Management | Project Controls | Medium | 2026-06-01 | 0 | Closed | Closed | documents/COR-2026-0003.pdf | Synthetic portfolio sample
COR-2026-0004 | Outgoing | 2026-06-24 | Memo | Method statement review | Project Team | Contracts | Contracts Team | Low | 2026-07-04 | 33 | Under Review | 31+ Days | documents/COR-2026-0004.pdf | Synthetic portfolio sample
COR-2026-0005 | Incoming | 2026-05-16 | Submittal | Technical drawing transmittal | External Stakeholder | Document Control | Document Controller | High | 2026-05-21 | 72 | Action Required | 31+ Days | documents/COR-2026-0005.pdf | Synthetic portfolio sample
COR-2026-0006 | Outgoing | 2026-05-23 | Transmittal | Site access coordination | Project Team | Construction | Construction Manager | Medium | 2026-05-30 | 65 | Under Review | 31+ Days | documents/COR-2026-0006.pdf | Synthetic portfolio sample
COR-2026-0007 | Incoming | 2026-07-21 | RFI | Method statement review | External Stakeholder | Management | Project Controls | Medium | 2026-07-31 | 6 | Action Required | 0-7 Days | documents/COR-2026-0007.pdf | Synthetic portfolio sample
COR-2026-0008 | Outgoing | 2026-06-21 | Transmittal | Technical drawing transmittal | Project Team | Finance | Finance Team | Medium | 2026-07-12 | 0 | Closed | Closed | documents/COR-2026-0008.pdf | Synthetic portfolio sample
COR-2026-0009 | Incoming | 2026-05-16 | Memo | Method statement review | External Stakeholder | Management | Project Controls | High | 2026-05-26 | 72 | Under Review | 31+ Days | documents/COR-2026-0009.pdf | Synthetic portfolio sample
COR-2026-0010 | Outgoing | 2026-05-19 | Submittal | Payment documentation follow-up | Project Team | Finance | Finance Team | Critical | 2026-06-09 | 69 | Under Review | 31+ Days | documents/COR-2026-0010.pdf | Synthetic portfolio sample
COR-2026-0011 | Incoming | 2026-07-15 | Transmittal | Method statement review | External Stakeholder | Management | Project Controls | Low | 2026-07-29 | 0 | Closed | Closed | documents/COR-2026-0011.pdf | Synthetic portfolio sample
COR-2026-0012 | Outgoing | 2026-06-27 | Transmittal | Design clarification and response required | Project Team | HSE | HSE Lead | Low | 2026-07-11 | 30 | Open | 15-30 Days | documents/COR-2026-0012.pdf | Synthetic portfolio sample
COR-2026-0013 | Incoming | 2026-05-19 | Transmittal | Variation supporting documents | External Stakeholder | Document Control | Document Controller | Low | 2026-06-02 | 69 | Under Review | 31+ Days | documents/COR-2026-0013.pdf | Synthetic portfolio sample
COR-2026-0014 | Outgoing | 2026-07-23 | Letter | Design clarification and response required | Project Team | Procurement | Procurement Lead | Medium | 2026-07-28 | 4 | Action Required | 0-7 Days | documents/COR-2026-0014.pdf | Synthetic portfolio sample
COR-2026-0015 | Incoming | 2026-07-03 | Submittal | Design clarification and response required | External Stakeholder | Contracts | Contracts Team | Low | 2026-07-17 | 24 | Open | 15-30 Days | documents/COR-2026-0015.pdf | Synthetic portfolio sample
COR-2026-0016 | Outgoing | 2026-07-12 | Submittal | Variation supporting documents | Project Team | Contracts | Contracts Team | Medium | 2026-07-26 | 0 | Closed | Closed | documents/COR-2026-0016.pdf | Synthetic portfolio sample
COR-2026-0017 | Incoming | 2026-07-19 | Memo | Technical drawing transmittal | External Stakeholder | Engineering | Engineering Lead | Low | 2026-07-29 | 0 | Closed | Closed | documents/COR-2026-0017.pdf | Synthetic portfolio sample
COR-2026-0018 | Outgoing | 2026-07-12 | RFI | Commercial submission for review | Project Team | Document Control | Document Controller | Medium | 2026-07-17 | 15 | Open | 15-30 Days | documents/COR-2026-0018.pdf | Synthetic portfolio sample
COR-2026-0019 | Incoming | 2026-07-06 | Letter | Interface coordination response | External Stakeholder | Construction | Construction Manager | High | 2026-07-27 | 21 | Under Review | 15-30 Days | documents/COR-2026-0019.pdf | Synthetic portfolio sample
COR-2026-0020 | Outgoing | 2026-06-12 | Letter | Material approval package | Project Team | Construction | Construction Manager | Medium | 2026-06-17 | 0 | Closed | Closed | documents/COR-2026-0020.pdf | Synthetic portfolio sample
COR-2026-0021 | Incoming | 2026-07-25 | Submittal | Payment documentation follow-up | External Stakeholder | HSE | HSE Lead | Medium | 2026-08-04 | 0 | Closed | Closed | documents/COR-2026-0021.pdf | Synthetic portfolio sample
COR-2026-0022 | Outgoing | 2026-07-12 | Memo | Design clarification and response required | Project Team | Management | Project Controls | High | 2026-08-02 | 0 | Closed | Closed | documents/COR-2026-0022.pdf | Synthetic portfolio sample
COR-2026-0023 | Incoming | 2026-07-01 | Submittal | Variation supporting documents | External Stakeholder | Finance | Finance Team | Critical | 2026-07-08 | 0 | Closed | Closed | documents/COR-2026-0023.pdf | Synthetic portfolio sample
COR-2026-0024 | Outgoing | 2026-06-25 | Letter | Document revision submission | Project Team | Engineering | Engineering Lead | High | 2026-07-02 | 0 | Closed | Closed | documents/COR-2026-0024.pdf | Synthetic portfolio sample
COR-2026-0025 | Incoming | 2026-05-16 | Submittal | Material approval package | External Stakeholder | Document Control | Document Controller | Critical | 2026-05-23 | 72 | Open | 31+ Days | documents/COR-2026-0025.pdf | Synthetic portfolio sample
COR-2026-0026 | Outgoing | 2026-06-22 | Letter | Interface coordination response | Project Team | Management | Project Controls | High | 2026-06-27 | 0 | Closed | Closed | documents/COR-2026-0026.pdf | Synthetic portfolio sample
COR-2026-0027 | Incoming | 2026-05-31 | RFI | Technical drawing transmittal | External Stakeholder | Finance | Finance Team | High | 2026-06-07 | 57 | Under Review | 31+ Days | documents/COR-2026-0027.pdf | Synthetic portfolio sample
COR-2026-0028 | Outgoing | 2026-07-26 | Memo | Method statement review | Project Team | Engineering | Engineering Lead | High | 2026-08-09 | 1 | Action Required | 0-7 Days | documents/COR-2026-0028.pdf | Synthetic portfolio sample
COR-2026-0029 | Incoming | 2026-06-11 | RFI | Method statement review | External Stakeholder | Construction | Construction Manager | High | 2026-06-21 | 0 | Closed | Closed | documents/COR-2026-0029.pdf | Synthetic portfolio sample
COR-2026-0030 | Outgoing | 2026-07-07 | Transmittal | Method statement review | Project Team | HSE | HSE Lead | Medium | 2026-07-17 | 0 | Closed | Closed | documents/COR-2026-0030.pdf | Synthetic portfolio sample
COR-2026-0031 | Incoming | 2026-07-03 | Memo | Interface coordination response | External Stakeholder | Engineering | Engineering Lead | Medium | 2026-07-17 | 24 | Under Review | 15-30 Days | documents/COR-2026-0031.pdf | Synthetic portfolio sample
COR-2026-0032 | Outgoing | 2026-07-07 | Letter | Method statement review | Project Team | Finance | Finance Team | High | 2026-07-12 | 20 | Open | 15-30 Days | documents/COR-2026-0032.pdf | Synthetic portfolio sample
COR-2026-0033 | Incoming | 2026-05-21 | Memo | Design clarification and response required | External Stakeholder | Document Control | Document Controller | Low | 2026-05-28 | 67 | Open | 31+ Days | documents/COR-2026-0033.pdf | Synthetic portfolio sample
COR-2026-0034 | Outgoing | 2026-05-21 | Memo | Document revision submission | Project Team | Management | Project Controls | High | 2026-05-31 | 0 | Closed | Closed | documents/COR-2026-0034.pdf | Synthetic portfolio sample
COR-2026-0035 | Incoming | 2026-07-21 | RFI | Method statement review | External Stakeholder | Engineering | Engineering Lead | Low | 2026-07-26 | 6 | Open | 0-7 Days | documents/COR-2026-0035.pdf | Synthetic portfolio sample
COR-2026-0036 | Outgoing | 2026-06-19 | Memo | Procurement technical clarification | Project Team | Finance | Finance Team | Medium | 2026-06-29 | 0 | Closed | Closed | documents/COR-2026-0036.pdf | Synthetic portfolio sample
COR-2026-0037 | Incoming | 2026-05-18 | Memo | Document revision submission | External Stakeholder | Management | Project Controls | Low | 2026-05-28 | 70 | Under Review | 31+ Days | documents/COR-2026-0037.pdf | Synthetic portfolio sample
COR-2026-0038 | Outgoing | 2026-06-16 | RFI | Technical drawing transmittal | Project Team | Procurement | Procurement Lead | Critical | 2026-06-26 | 41 | Open | 31+ Days | documents/COR-2026-0038.pdf | Synthetic portfolio sample
COR-2026-0039 | Incoming | 2026-07-24 | Transmittal | Material approval package | External Stakeholder | HSE | HSE Lead | Low | 2026-08-03 | 3 | Open | 0-7 Days | documents/COR-2026-0039.pdf | Synthetic portfolio sample
COR-2026-0040 | Outgoing | 2026-05-27 | Submittal | Technical drawing transmittal | Project Team | Document Control | Document Controller | High | 2026-06-06 | 61 | Under Review | 31+ Days | documents/COR-2026-0040.pdf | Synthetic portfolio sample
COR-2026-0041 | Incoming | 2026-06-27 | Submittal | Technical drawing transmittal | External Stakeholder | Document Control | Document Controller | Low | 2026-07-18 | 30 | Open | 15-30 Days | documents/COR-2026-0041.pdf | Synthetic portfolio sample
COR-2026-0042 | Outgoing | 2026-05-23 | RFI | Method statement review | Project Team | Contracts | Contracts Team | Low | 2026-06-13 | 65 | Open | 31+ Days | documents/COR-2026-0042.pdf | Synthetic portfolio sample
COR-2026-0043 | Incoming | 2026-07-10 | Letter | Method statement review | External Stakeholder | Procurement | Procurement Lead | Low | 2026-07-24 | 17 | Open | 15-30 Days | documents/COR-2026-0043.pdf | Synthetic portfolio sample
COR-2026-0044 | Outgoing | 2026-05-27 | RFI | Interface coordination response | Project Team | Finance | Finance Team | Critical | 2026-06-06 | 0 | Closed | Closed | documents/COR-2026-0044.pdf | Synthetic portfolio sample
COR-2026-0045 | Incoming | 2026-06-09 | Memo | Design clarification and response required | External Stakeholder | HSE | HSE Lead | Medium | 2026-06-16 | 0 | Closed | Closed | documents/COR-2026-0045.pdf | Synthetic portfolio sample
COR-2026-0046 | Outgoing | 2026-06-07 | RFI | Procurement technical clarification | Project Team | HSE | HSE Lead | Medium | 2026-06-21 | 0 | Closed | Closed | documents/COR-2026-0046.pdf | Synthetic portfolio sample
COR-2026-0047 | Incoming | 2026-07-26 | Letter | Interface coordination response | External Stakeholder | HSE | HSE Lead | Medium | 2026-07-31 | 1 | Open | 0-7 Days | documents/COR-2026-0047.pdf | Synthetic portfolio sample
COR-2026-0048 | Outgoing | 2026-05-16 | Letter | Material approval package | Project Team | Construction | Construction Manager | Medium | 2026-05-30 | 0 | Closed | Closed | documents/COR-2026-0048.pdf | Synthetic portfolio sample
COR-2026-0049 | Incoming | 2026-05-14 | RFI | Procurement technical clarification | External Stakeholder | Procurement | Procurement Lead | Low | 2026-05-24 | 74 | Action Required | 31+ Days | documents/COR-2026-0049.pdf | Synthetic portfolio sample
COR-2026-0050 | Outgoing | 2026-06-07 | Submittal | Method statement review | Project Team | Contracts | Contracts Team | Medium | 2026-06-21 | 50 | Action Required | 31+ Days | documents/COR-2026-0050.pdf | Synthetic portfolio sample
COR-2026-0051 | Incoming | 2026-06-03 | Transmittal | Document revision submission | External Stakeholder | Procurement | Procurement Lead | Medium | 2026-06-13 | 0 | Closed | Closed | documents/COR-2026-0051.pdf | Synthetic portfolio sample
COR-2026-0052 | Outgoing | 2026-05-21 | Transmittal | Management instruction and action follow-up | Project Team | Management | Project Controls | Medium | 2026-05-31 | 67 | Action Required | 31+ Days | documents/COR-2026-0052.pdf | Synthetic portfolio sample
COR-2026-0053 | Incoming | 2026-05-18 | Letter | Management instruction and action follow-up | External Stakeholder | Document Control | Document Controller | Low | 2026-05-25 | 70 | Under Review | 31+ Days | documents/COR-2026-0053.pdf | Synthetic portfolio sample
COR-2026-0054 | Outgoing | 2026-06-28 | Transmittal | Design clarification and response required | Project Team | Contracts | Contracts Team | Low | 2026-07-08 | 29 | Under Review | 15-30 Days | documents/COR-2026-0054.pdf | Synthetic portfolio sample
COR-2026-0055 | Incoming | 2026-05-18 | Memo | Procurement technical clarification | External Stakeholder | Engineering | Engineering Lead | High | 2026-06-08 | 70 | Action Required | 31+ Days | documents/COR-2026-0055.pdf | Synthetic portfolio sample
COR-2026-0056 | Outgoing | 2026-06-28 | RFI | Design clarification and response required | Project Team | Document Control | Document Controller | Medium | 2026-07-12 | 29 | Open | 15-30 Days | documents/COR-2026-0056.pdf | Synthetic portfolio sample
COR-2026-0057 | Incoming | 2026-07-26 | Transmittal | Method statement review | External Stakeholder | Document Control | Document Controller | High | 2026-08-02 | 1 | Under Review | 0-7 Days | documents/COR-2026-0057.pdf | Synthetic portfolio sample
COR-2026-0058 | Outgoing | 2026-07-07 | Transmittal | Procurement technical clarification | Project Team | Engineering | Engineering Lead | Medium | 2026-07-12 | 20 | Under Review | 15-30 Days | documents/COR-2026-0058.pdf | Synthetic portfolio sample
COR-2026-0059 | Incoming | 2026-07-17 | RFI | Procurement technical clarification | External Stakeholder | HSE | HSE Lead | Medium | 2026-08-07 | 10 | Action Required | 8-14 Days | documents/COR-2026-0059.pdf | Synthetic portfolio sample
COR-2026-0060 | Outgoing | 2026-05-15 | Letter | Management instruction and action follow-up | Project Team | Contracts | Contracts Team | Medium | 2026-05-25 | 73 | Open | 31+ Days | documents/COR-2026-0060.pdf | Synthetic portfolio sample
Formulas:
Days Open = IF([Status]="Closed",0,MAX(0,TODAY()-[Date]))

## Document Register
Document No. | Title | Discipline | Revision | Document Type | Submitted Date | Current Status | Responsible | Next Action Due | Days to Due | Hyperlink
DOC-0001 | Commercial submission for review | Civil | B | Procedure | 2026-07-20 | For Information | Document Controller | 2026-08-03 | 7 | documents/DOC-0001.pdf
DOC-0002 | Procurement technical clarification | Civil | 01 | Report | 2026-05-28 | Approved | Project Controls | 2026-06-18 | -39 | documents/DOC-0002.pdf
DOC-0003 | Management instruction and action follow-up | Commercial | 02 | Method Statement | 2026-06-21 | Approved | Finance Team | 2026-07-05 | -22 | documents/DOC-0003.pdf
DOC-0004 | Design clarification and response required | HSE | 02 | Procedure | 2026-06-25 | For Review | Contracts Team | 2026-07-02 | -25 | documents/DOC-0004.pdf
DOC-0005 | Variation supporting documents | HSE | A | Report | 2026-06-29 | For Review | Document Controller | 2026-07-06 | -21 | documents/DOC-0005.pdf
DOC-0006 | Variation supporting documents | Architecture | 01 | Technical Submittal | 2026-06-18 | For Review | Contracts Team | 2026-06-25 | -32 | documents/DOC-0006.pdf
DOC-0007 | Document revision submission | Civil | 00 | Report | 2026-05-29 | Revise & Resubmit | Document Controller | 2026-06-12 | -45 | documents/DOC-0007.pdf
DOC-0008 | Variation supporting documents | Structural | 01 | Drawing | 2026-07-02 | For Review | Engineering Lead | 2026-07-12 | -15 | documents/DOC-0008.pdf
DOC-0009 | Site access coordination | HSE | A | Technical Submittal | 2026-07-15 | Approved | Document Controller | 2026-07-29 | 2 | documents/DOC-0009.pdf
DOC-0010 | Payment documentation follow-up | MEP | 00 | Procedure | 2026-06-11 | For Information | Procurement Lead | 2026-06-25 | -32 | documents/DOC-0010.pdf
DOC-0011 | Site access coordination | Architecture | 01 | Drawing | 2026-07-18 | Approved | Document Controller | 2026-07-28 | 1 | documents/DOC-0011.pdf
DOC-0012 | Variation supporting documents | Commercial | B | Procedure | 2026-06-10 | For Information | Procurement Lead | 2026-06-17 | -40 | documents/DOC-0012.pdf
DOC-0013 | Material approval package | HSE | 02 | Drawing | 2026-07-26 | For Review | HSE Lead | 2026-08-05 | 9 | documents/DOC-0013.pdf
DOC-0014 | Interface coordination response | Civil | 01 | Technical Submittal | 2026-07-20 | For Information | Contracts Team | 2026-08-03 | 7 | documents/DOC-0014.pdf
DOC-0015 | Document revision submission | Structural | B | Report | 2026-07-18 | For Information | Engineering Lead | 2026-08-01 | 5 | documents/DOC-0015.pdf
DOC-0016 | Material approval package | MEP | 01 | Drawing | 2026-06-08 | Approved | Procurement Lead | 2026-06-22 | -35 | documents/DOC-0016.pdf
DOC-0017 | Payment documentation follow-up | HSE | 02 | Procedure | 2026-05-30 | For Review | Construction Manager | 2026-06-13 | -44 | documents/DOC-0017.pdf
DOC-0018 | Method statement review | Structural | 01 | Method Statement | 2026-06-14 | Revise & Resubmit | Contracts Team | 2026-07-05 | -22 | documents/DOC-0018.pdf
DOC-0019 | Material approval package | Civil | 01 | Drawing | 2026-07-07 | For Information | Construction Manager | 2026-07-21 | -6 | documents/DOC-0019.pdf
DOC-0020 | Site access coordination | Civil | 00 | Drawing | 2026-07-20 | For Information | HSE Lead | 2026-07-27 | 0 | documents/DOC-0020.pdf
DOC-0021 | Method statement review | Structural | 01 | Technical Submittal | 2026-07-01 | Approved | Project Controls | 2026-07-11 | -16 | documents/DOC-0021.pdf
DOC-0022 | Commercial submission for review | Civil | B | Report | 2026-07-07 | Revise & Resubmit | Document Controller | 2026-07-17 | -10 | documents/DOC-0022.pdf
DOC-0023 | Technical drawing transmittal | Commercial | 02 | Drawing | 2026-07-13 | For Review | Project Controls | 2026-07-23 | -4 | documents/DOC-0023.pdf
DOC-0024 | Method statement review | Architecture | A | Drawing | 2026-07-26 | Approved | Finance Team | 2026-08-09 | 13 | documents/DOC-0024.pdf
DOC-0025 | Payment documentation follow-up | Civil | A | Procedure | 2026-06-25 | Approved | Finance Team | 2026-07-02 | -25 | documents/DOC-0025.pdf
DOC-0026 | Management instruction and action follow-up | Structural | 00 | Technical Submittal | 2026-07-14 | For Review | Finance Team | 2026-07-24 | -3 | documents/DOC-0026.pdf
DOC-0027 | Payment documentation follow-up | HSE | 00 | Technical Submittal | 2026-07-07 | Approved | Document Controller | 2026-07-21 | -6 | documents/DOC-0027.pdf
DOC-0028 | Technical drawing transmittal | HSE | 02 | Technical Submittal | 2026-07-10 | Approved | Finance Team | 2026-07-17 | -10 | documents/DOC-0028.pdf
DOC-0029 | Procurement technical clarification | Civil | A | Method Statement | 2026-06-22 | Revise & Resubmit | Contracts Team | 2026-07-02 | -25 | documents/DOC-0029.pdf
DOC-0030 | Document revision submission | Civil | 02 | Report | 2026-07-12 | For Information | HSE Lead | 2026-08-02 | 6 | documents/DOC-0030.pdf
DOC-0031 | Commercial submission for review | MEP | A | Drawing | 2026-06-24 | For Information | Construction Manager | 2026-07-15 | -12 | documents/DOC-0031.pdf
DOC-0032 | Material approval package | Commercial | B | Report | 2026-06-14 | Approved | HSE Lead | 2026-06-28 | -29 | documents/DOC-0032.pdf
DOC-0033 | Site access coordination | Architecture | 01 | Report | 2026-06-19 | Approved | HSE Lead | 2026-07-10 | -17 | documents/DOC-0033.pdf
DOC-0034 | Procurement technical clarification | Architecture | 02 | Procedure | 2026-05-31 | For Review | Document Controller | 2026-06-07 | -50 | documents/DOC-0034.pdf
DOC-0035 | Procurement technical clarification | Civil | A | Technical Submittal | 2026-07-26 | For Information | Project Controls | 2026-08-09 | 13 | documents/DOC-0035.pdf
DOC-0036 | Site access coordination | MEP | A | Method Statement | 2026-06-02 | For Review | Finance Team | 2026-06-12 | -45 | documents/DOC-0036.pdf
DOC-0037 | Payment documentation follow-up | Structural | 00 | Procedure | 2026-07-16 | Approved | Project Controls | 2026-07-26 | -1 | documents/DOC-0037.pdf
DOC-0038 | Design clarification and response required | Civil | A | Procedure | 2026-07-04 | Revise & Resubmit | Contracts Team | 2026-07-11 | -16 | documents/DOC-0038.pdf
DOC-0039 | Management instruction and action follow-up | Commercial | 00 | Procedure | 2026-06-25 | Approved | Project Controls | 2026-07-02 | -25 | documents/DOC-0039.pdf
DOC-0040 | Payment documentation follow-up | Structural | 00 | Drawing | 2026-06-02 | For Review | Procurement Lead | 2026-06-23 | -34 | documents/DOC-0040.pdf
Formulas:
Days to Due = [Next Action Due]-TODAY()

## Lists (hidden)
Direction | Type | Status | Priority | Department
Incoming | Letter | Open | Critical | Management
Outgoing | Transmittal | Under Review | High | Engineering
| RFI | Action Required | Medium | Contracts
| Submittal | Closed | Low | Procurement
| Memo |  |  | Construction
Document Control
Finance
HSE