## Executive Dashboard
EXECUTIVE PROJECT OPERATIONS CONTROL CENTER
Management Overview ¦ Actions • Workforce • Attendance • Procurement • KPI Performance
Report Date | 2026-07-27 |  | ACTION TRACKER |  | WORKFORCE REPORT |  | PROCUREMENT |  | KPI SCORECARD
68 |  |  | 61 |  |  | 126 |  |  | 91.28% |  |  | 46
Open / In Progress |  |  | Past Due |  |  | Active Employees |  |  | Average Attendance |  |  | Priority Actions
21.1868 |  |  | 9.6787 |  |  | 1 |  |  | 10 |  |  | 150
Outstanding Commitments | Outstanding Commitments | Outstanding Commitments | Paid Value | Paid Value | Paid Value | KPIs On Track |  |  | OT Exceptions |  |  | Employees
Executive Insight: 61 actions are overdue; 91.3% average attendance; 21,186,817 SAR outstanding commitments. Review critical actions and procurement exposure.
Department | Open Actions | Overdue | Active Workforce | Avg Attendance | Outstanding SAR |  | KPI | Target | Actual | Achievement | Status | Comment | Department | Outstanding M SAR
Construction | 7 | 5 | 27 | 91.87% | 1425213.35 |  | Attendance Rate | 96% | 91.28% | 95.09% | Watch | Monitor closely | Construction | 1.4252
Logistics | 6 | 4 | 19 | 89.46% | 2716925.12 |  | Active Workforce % | 90% | 84% | 93.33% | Watch | Monitor closely | Logistics | 2.7169
Fleet & Transportation | 9 | 8 | 16 | 90.97% | 1907607.26 |  | Open Action Closure % | 80% | 38.33% | 47.92% | Critical | Management action required | Fleet & Transportation | 1.9076
Project Administration | 4 | 3 | 19 | 92.19% | 2694405.14 |  | Overdue Action Rate | 10% | 50.83% | 19.67% | Critical | Management action required | Project Administration | 2.6944
Warehouse | 7 | 5 | 11 | 92.9% | 2124066.01 |  | Procurement Paid % | 75% | 31.36% | 41.81% | Critical | Management action required | Warehouse | 2.1241
Procurement | 9 | 9 | 5 | 91.58% | 1122956.66 |  | OT Exception Rate | 15% | 6.667% | 225% | On Track | Within target | Procurement | 1.123
Document Control | 10 | 8 | 9 | 91.95% | 1213026.69 | [7 empty] | Document Control | 1.213
Finance | 3 | 3 | 8 | 89.36% | 3260233.31 | [7 empty] | Finance | 3.2602
Human Resources | 9 | 7 | 9 | 91.33% | 2098604.72 | [7 empty] | Human Resources | 2.0986
Executive Office | 10 | 9 | 3 | 89.66% | 2623779.01 | [7 empty] | Executive Office | 2.6238

## Action Tracker
MANAGEMENT ACTION & FOLLOW-UP TRACKER
Executive follow-up register ¦ Priorities • Owners • Due dates • Progress • Overdue visibility
Action ID | Action / Deliverable | Department | Owner | Priority | Status | Created Date | Due Date | Completed Date | Progress % | Category | Days Overdue
ACT-001 | Warehouse operational follow-up item 001 | Warehouse | Admin Manager | Medium | In Progress | 2026-07-12 | 2026-07-26 |  | 75% | Management review | 1
ACT-002 | Finance operational follow-up item 002 | Finance | Document Controller | Medium | Open | 2026-05-26 | 2026-06-26 |  | 20% | Site action | 31
ACT-003 | Construction operational follow-up item 003 | Construction | Document Controller | High | In Progress | 2026-06-24 | 2026-07-28 |  | 60% | Vendor follow-up | 0
ACT-004 | Construction operational follow-up item 004 | Construction | Procurement Lead | Medium | In Progress | 2026-05-26 | 2026-06-03 |  | 50% | Internal coordination | 54
ACT-005 | Fleet & Transportation operational follow-up item 005 | Fleet & Transportation | HR Manager | Critical | Completed | 2026-06-04 | 2026-06-24 | 2026-06-24 | 100% | Commercial follow-up | 0
ACT-006 | Fleet & Transportation operational follow-up item 006 | Fleet & Transportation | Executive Office | Medium | Completed | 2026-05-11 | 2026-05-19 | 2026-05-18 | 100% | Vendor follow-up | 0
ACT-007 | Human Resources operational follow-up item 007 | Human Resources | Logistics Manager | Medium | In Progress | 2026-07-02 | 2026-07-20 |  | 50% | Vendor follow-up | 7
ACT-008 | Construction operational follow-up item 008 | Construction | Document Controller | High | Completed | 2026-06-24 | 2026-07-22 | 2026-07-17 | 100% | Internal coordination | 0
ACT-009 | Document Control operational follow-up item 009 | Document Control | Logistics Manager | High | Open | 2026-07-02 | 2026-07-10 |  | 0% | Commercial follow-up | 17
ACT-010 | Warehouse operational follow-up item 010 | Warehouse | Document Controller | Medium | In Progress | 2026-06-22 | 2026-06-30 |  | 85% | Management review | 27
ACT-011 | Logistics operational follow-up item 011 | Logistics | Procurement Lead | Medium | Completed | 2026-07-10 | 2026-07-18 | 2026-07-21 | 100% | Management review | 0
ACT-012 | Project Administration operational follow-up item 012 | Project Administration | Admin Manager | Critical | Completed | 2026-06-07 | 2026-06-22 | 2026-06-19 | 100% | Site action | 0
ACT-013 | Construction operational follow-up item 013 | Construction | Executive Office | Medium | Open | 2026-06-21 | 2026-07-03 |  | 10% | Vendor follow-up | 24
ACT-014 | Human Resources operational follow-up item 014 | Human Resources | HR Manager | Low | Open | 2026-07-24 | 2026-08-20 |  | 30% | Management review | 0
ACT-015 | Logistics operational follow-up item 015 | Logistics | Executive Office | Medium | Open | 2026-07-12 | 2026-08-08 |  | 20% | Site action | 0
ACT-016 | Procurement operational follow-up item 016 | Procurement | Logistics Manager | Medium | In Progress | 2026-06-22 | 2026-07-25 |  | 60% | Internal coordination | 2
ACT-017 | Procurement operational follow-up item 017 | Procurement | Site Administrator | Medium | In Progress | 2026-05-09 | 2026-05-29 |  | 25% | Management review | 59
ACT-018 | Executive Office operational follow-up item 018 | Executive Office | Site Administrator | Medium | In Progress | 2026-07-20 | 2026-08-15 |  | 85% | Internal coordination | 0
ACT-019 | Human Resources operational follow-up item 019 | Human Resources | Document Controller | Medium | Completed | 2026-06-29 | 2026-07-28 | 2026-07-22 | 100% | Vendor follow-up | 0
ACT-020 | Executive Office operational follow-up item 020 | Executive Office | Admin Manager | Critical | In Progress | 2026-05-28 | 2026-06-17 |  | 85% | Internal coordination | 40
ACT-021 | Logistics operational follow-up item 021 | Logistics | Project Manager | Medium | Completed | 2026-06-16 | 2026-07-19 | 2026-07-12 | 100% | Management review | 0
ACT-022 | Procurement operational follow-up item 022 | Procurement | Site Administrator | Medium | Completed | 2026-05-25 | 2026-06-25 | 2026-06-30 | 100% | Vendor follow-up | 0
ACT-023 | Fleet & Transportation operational follow-up item 023 | Fleet & Transportation | Executive Office | Critical | Completed | 2026-05-01 | 2026-05-27 | 2026-06-06 | 100% | Site action | 0
ACT-024 | Project Administration operational follow-up item 024 | Project Administration | Admin Manager | Medium | Completed | 2026-05-12 | 2026-06-15 | 2026-06-23 | 100% | Vendor follow-up | 0
ACT-025 | Fleet & Transportation operational follow-up item 025 | Fleet & Transportation | Finance Lead | High | Open | 2026-06-02 | 2026-06-18 |  | 0% | Commercial follow-up | 39
ACT-026 | Document Control operational follow-up item 026 | Document Control | HR Manager | Medium | Completed | 2026-06-20 | 2026-07-06 | 2026-07-14 | 100% | Site action | 0
ACT-027 | Warehouse operational follow-up item 027 | Warehouse | HR Manager | Medium | Open | 2026-05-03 | 2026-05-13 |  | 10% | Management review | 75
ACT-028 | Procurement operational follow-up item 028 | Procurement | HR Manager | Medium | Completed | 2026-05-09 | 2026-05-30 | 2026-05-28 | 100% | Vendor follow-up | 0
ACT-029 | Executive Office operational follow-up item 029 | Executive Office | Site Administrator | Medium | In Progress | 2026-05-14 | 2026-06-13 |  | 85% | Site action | 44
ACT-030 | Procurement operational follow-up item 030 | Procurement | Procurement Lead | Medium | In Progress | 2026-05-22 | 2026-06-09 |  | 25% | Vendor follow-up | 48
ACT-031 | Document Control operational follow-up item 031 | Document Control | Fleet Supervisor | Medium | In Progress | 2026-07-17 | 2026-08-16 |  | 25% | Management review | 0
ACT-032 | Human Resources operational follow-up item 032 | Human Resources | HR Manager | Low | Open | 2026-05-04 | 2026-05-13 |  | 10% | Internal coordination | 75
ACT-033 | Warehouse operational follow-up item 033 | Warehouse | Project Manager | Medium | In Progress | 2026-07-12 | 2026-08-05 |  | 25% | Site action | 0
ACT-034 | Warehouse operational follow-up item 034 | Warehouse | Finance Lead | Medium | Completed | 2026-06-07 | 2026-06-30 | 2026-06-23 | 100% | Commercial follow-up | 0
ACT-035 | Procurement operational follow-up item 035 | Procurement | Admin Manager | High | Completed | 2026-06-06 | 2026-06-18 | 2026-06-16 | 100% | Site action | 0
ACT-036 | Document Control operational follow-up item 036 | Document Control | Project Manager | Medium | On Hold | 2026-06-02 | 2026-07-07 |  | 30% | Internal coordination | 20
ACT-037 | Construction operational follow-up item 037 | Construction | Logistics Manager | High | Open | 2026-07-20 | 2026-08-15 |  | 30% | Site action | 0
ACT-038 | Fleet & Transportation operational follow-up item 038 | Fleet & Transportation | Project Manager | Critical | Completed | 2026-06-04 | 2026-07-09 | 2026-07-14 | 100% | Internal coordination | 0
ACT-039 | Human Resources operational follow-up item 039 | Human Resources | Executive Office | Low | Completed | 2026-07-05 | 2026-07-27 | 2026-07-27 | 100% | Site action | 0
ACT-040 | Document Control operational follow-up item 040 | Document Control | Logistics Manager | Critical | Open | 2026-05-14 | 2026-06-04 |  | 30% | Management review | 53
ACT-041 | Fleet & Transportation operational follow-up item 041 | Fleet & Transportation | Document Controller | Medium | Open | 2026-05-29 | 2026-06-20 |  | 10% | Internal coordination | 37
ACT-042 | Human Resources operational follow-up item 042 | Human Resources | Finance Lead | Medium | In Progress | 2026-06-08 | 2026-06-19 |  | 85% | Internal coordination | 38
ACT-043 | Document Control operational follow-up item 043 | Document Control | HR Manager | High | In Progress | 2026-06-10 | 2026-06-15 |  | 85% | Site action | 42
ACT-044 | Executive Office operational follow-up item 044 | Executive Office | Finance Lead | Medium | Completed | 2026-06-09 | 2026-06-25 | 2026-07-03 | 100% | Commercial follow-up | 0
ACT-045 | Executive Office operational follow-up item 045 | Executive Office | Finance Lead | High | Open | 2026-06-02 | 2026-06-06 |  | 20% | Vendor follow-up | 51
ACT-046 | Fleet & Transportation operational follow-up item 046 | Fleet & Transportation | Site Administrator | High | Completed | 2026-05-30 | 2026-06-23 | 2026-06-30 | 100% | Site action | 0
ACT-047 | Human Resources operational follow-up item 047 | Human Resources | Fleet Supervisor | Critical | In Progress | 2026-05-18 | 2026-05-30 |  | 40% | Internal coordination | 58
ACT-048 | Document Control operational follow-up item 048 | Document Control | Fleet Supervisor | Critical | Open | 2026-07-06 | 2026-07-26 |  | 20% | Commercial follow-up | 1
ACT-049 | Fleet & Transportation operational follow-up item 049 | Fleet & Transportation | Executive Office | Medium | In Progress | 2026-06-22 | 2026-07-26 |  | 50% | Internal coordination | 1
ACT-050 | Executive Office operational follow-up item 050 | Executive Office | Admin Manager | Medium | In Progress | 2026-05-16 | 2026-06-09 |  | 60% | Vendor follow-up | 48
ACT-051 | Executive Office operational follow-up item 051 | Executive Office | Logistics Manager | High | In Progress | 2026-07-07 | 2026-07-21 |  | 85% | Management review | 6
ACT-052 | Finance operational follow-up item 052 | Finance | HR Manager | Low | Completed | 2026-06-20 | 2026-06-28 | 2026-06-30 | 100% | Commercial follow-up | 0
ACT-053 | Document Control operational follow-up item 053 | Document Control | Fleet Supervisor | High | Completed | 2026-07-05 | 2026-07-21 | 2026-07-27 | 100% | Site action | 0
ACT-054 | Logistics operational follow-up item 054 | Logistics | Site Administrator | High | Open | 2026-05-09 | 2026-05-18 |  | 30% | Site action | 70
ACT-055 | Procurement operational follow-up item 055 | Procurement | Site Administrator | Medium | Completed | 2026-05-23 | 2026-06-27 | 2026-07-06 | 100% | Vendor follow-up | 0
ACT-056 | Human Resources operational follow-up item 056 | Human Resources | Document Controller | Medium | Open | 2026-05-16 | 2026-06-20 |  | 20% | Site action | 37
ACT-057 | Fleet & Transportation operational follow-up item 057 | Fleet & Transportation | Document Controller | High | Completed | 2026-05-12 | 2026-06-15 | 2026-06-20 | 100% | Site action | 0
ACT-058 | Document Control operational follow-up item 058 | Document Control | Project Manager | High | Completed | 2026-05-01 | 2026-06-04 | 2026-06-09 | 100% | Commercial follow-up | 0
ACT-059 | Procurement operational follow-up item 059 | Procurement | Project Manager | Medium | Completed | 2026-07-25 | 2026-07-29 | 2026-07-23 | 100% | Management review | 0
ACT-060 | Warehouse operational follow-up item 060 | Warehouse | Site Administrator | Critical | Open | 2026-05-03 | 2026-05-25 |  | 30% | Site action | 63
ACT-061 | Finance operational follow-up item 061 | Finance | HR Manager | High | Completed | 2026-06-01 | 2026-06-09 | 2026-06-05 | 100% | Vendor follow-up | 0
ACT-062 | Human Resources operational follow-up item 062 | Human Resources | Document Controller | Medium | In Progress | 2026-05-11 | 2026-05-31 |  | 40% | Management review | 57
ACT-063 | Finance operational follow-up item 063 | Finance | Site Administrator | Low | On Hold | 2026-07-22 | 2026-07-25 |  | 20% | Vendor follow-up | 2
ACT-064 | Document Control operational follow-up item 064 | Document Control | HR Manager | High | Open | 2026-07-09 | 2026-08-10 |  | 10% | Commercial follow-up | 0
ACT-065 | Document Control operational follow-up item 065 | Document Control | Fleet Supervisor | Medium | Open | 2026-06-22 | 2026-07-24 |  | 0% | Vendor follow-up | 3
ACT-066 | Procurement operational follow-up item 066 | Procurement | Admin Manager | Medium | Open | 2026-05-31 | 2026-06-14 |  | 30% | Internal coordination | 43
ACT-067 | Finance operational follow-up item 067 | Finance | Document Controller | High | In Progress | 2026-06-16 | 2026-06-19 |  | 75% | Internal coordination | 38
ACT-068 | Warehouse operational follow-up item 068 | Warehouse | Procurement Lead | Medium | Completed | 2026-07-22 | 2026-08-07 | 2026-08-05 | 100% | Management review | 0
ACT-069 | Human Resources operational follow-up item 069 | Human Resources | Executive Office | Medium | Completed | 2026-05-16 | 2026-06-12 | 2026-06-05 | 100% | Site action | 0
ACT-070 | Construction operational follow-up item 070 | Construction | Document Controller | High | Completed | 2026-07-14 | 2026-08-05 | 2026-07-30 | 100% | Commercial follow-up | 0
ACT-071 | Procurement operational follow-up item 071 | Procurement | Site Administrator | Medium | Completed | 2026-05-15 | 2026-05-18 | 2026-05-21 | 100% | Vendor follow-up | 0
ACT-072 | Fleet & Transportation operational follow-up item 072 | Fleet & Transportation | HR Manager | Medium | Open | 2026-07-01 | 2026-07-17 |  | 20% | Commercial follow-up | 10
ACT-073 | Fleet & Transportation operational follow-up item 073 | Fleet & Transportation | Project Manager | High | Completed | 2026-06-07 | 2026-06-14 | 2026-06-20 | 100% | Internal coordination | 0
ACT-074 | Logistics operational follow-up item 074 | Logistics | Document Controller | Medium | Open | 2026-05-09 | 2026-06-05 |  | 20% | Commercial follow-up | 52
ACT-075 | Construction operational follow-up item 075 | Construction | Finance Lead | Critical | In Progress | 2026-06-16 | 2026-06-26 |  | 25% | Management review | 31
ACT-076 | Fleet & Transportation operational follow-up item 076 | Fleet & Transportation | HR Manager | Medium | Open | 2026-07-24 | 2026-07-31 |  | 0% | Vendor follow-up | 0
ACT-077 | Procurement operational follow-up item 077 | Procurement | Fleet Supervisor | Medium | Completed | 2026-07-21 | 2026-08-21 | 2026-08-18 | 100% | Commercial follow-up | 0
ACT-078 | Procurement operational follow-up item 078 | Procurement | Document Controller | High | In Progress | 2026-07-15 | 2026-07-20 |  | 25% | Internal coordination | 7
ACT-079 | Procurement operational follow-up item 079 | Procurement | Finance Lead | Medium | Open | 2026-06-08 | 2026-06-12 |  | 0% | Management review | 45
ACT-080 | Human Resources operational follow-up item 080 | Human Resources | Executive Office | High | In Progress | 2026-06-18 | 2026-07-22 |  | 40% | Commercial follow-up | 5
ACT-081 | Procurement operational follow-up item 081 | Procurement | HR Manager | High | Open | 2026-07-18 | 2026-07-22 |  | 30% | Commercial follow-up | 5
ACT-082 | Procurement operational follow-up item 082 | Procurement | Fleet Supervisor | Medium | In Progress | 2026-06-28 | 2026-07-23 |  | 40% | Vendor follow-up | 4
ACT-083 | Document Control operational follow-up item 083 | Document Control | Procurement Lead | Medium | Completed | 2026-06-30 | 2026-07-23 | 2026-07-23 | 100% | Management review | 0
ACT-084 | Procurement operational follow-up item 084 | Procurement | Fleet Supervisor | Medium | Completed | 2026-05-09 | 2026-06-10 | 2026-06-20 | 100% | Internal coordination | 0
ACT-085 | Executive Office operational follow-up item 085 | Executive Office | Finance Lead | Medium | On Hold | 2026-05-01 | 2026-05-12 |  | 10% | Management review | 76
ACT-086 | Construction operational follow-up item 086 | Construction | Finance Lead | Medium | On Hold | 2026-05-07 | 2026-05-10 |  | 20% | Vendor follow-up | 78
ACT-087 | Document Control operational follow-up item 087 | Document Control | Logistics Manager | High | Completed | 2026-05-17 | 2026-05-22 | 2026-05-26 | 100% | Vendor follow-up | 0
ACT-088 | Human Resources operational follow-up item 088 | Human Resources | Admin Manager | High | Completed | 2026-07-04 | 2026-07-16 | 2026-07-14 | 100% | Internal coordination | 0
ACT-089 | Project Administration operational follow-up item 089 | Project Administration | HR Manager | Medium | In Progress | 2026-07-05 | 2026-08-05 |  | 60% | Site action | 0
ACT-090 | Warehouse operational follow-up item 090 | Warehouse | Logistics Manager | Critical | In Progress | 2026-05-21 | 2026-06-01 |  | 25% | Internal coordination | 56
ACT-091 | Finance operational follow-up item 091 | Finance | Finance Lead | High | Completed | 2026-07-09 | 2026-07-21 | 2026-07-14 | 100% | Vendor follow-up | 0
ACT-092 | Project Administration operational follow-up item 092 | Project Administration | Document Controller | Medium | In Progress | 2026-06-23 | 2026-07-13 |  | 25% | Vendor follow-up | 14
ACT-093 | Logistics operational follow-up item 093 | Logistics | Document Controller | Medium | Open | 2026-07-07 | 2026-08-08 |  | 20% | Vendor follow-up | 0
ACT-094 | Executive Office operational follow-up item 094 | Executive Office | Project Manager | Low | In Progress | 2026-05-13 | 2026-06-07 |  | 60% | Site action | 50
ACT-095 | Logistics operational follow-up item 095 | Logistics | Logistics Manager | High | Open | 2026-06-14 | 2026-07-01 |  | 30% | Vendor follow-up | 26
ACT-096 | Logistics operational follow-up item 096 | Logistics | Site Administrator | Medium | Completed | 2026-06-03 | 2026-06-30 | 2026-07-01 | 100% | Vendor follow-up | 0
ACT-097 | Procurement operational follow-up item 097 | Procurement | Site Administrator | Critical | Completed | 2026-06-03 | 2026-06-26 | 2026-06-28 | 100% | Internal coordination | 0
ACT-098 | Fleet & Transportation operational follow-up item 098 | Fleet & Transportation | Fleet Supervisor | Critical | Completed | 2026-05-22 | 2026-06-18 | 2026-06-23 | 100% | Internal coordination | 0
ACT-099 | Document Control operational follow-up item 099 | Document Control | Site Administrator | High | Completed | 2026-06-02 | 2026-06-09 | 2026-06-09 | 100% | Commercial follow-up | 0
ACT-100 | Logistics operational follow-up item 100 | Logistics | Finance Lead | Medium | In Progress | 2026-05-27 | 2026-06-15 |  | 25% | Commercial follow-up | 42
ACT-101 | Warehouse operational follow-up item 101 | Warehouse | Finance Lead | Medium | Completed | 2026-05-13 | 2026-05-26 | 2026-05-27 | 100% | Internal coordination | 0
ACT-102 | Finance operational follow-up item 102 | Finance | Site Administrator | Medium | Completed | 2026-05-30 | 2026-06-13 | 2026-06-17 | 100% | Site action | 0
ACT-103 | Executive Office operational follow-up item 103 | Executive Office | Admin Manager | Medium | Completed | 2026-07-08 | 2026-07-21 | 2026-07-26 | 100% | Internal coordination | 0
ACT-104 | Executive Office operational follow-up item 104 | Executive Office | Executive Office | Critical | Completed | 2026-07-09 | 2026-07-25 | 2026-07-18 | 100% | Management review | 0
ACT-105 | Document Control operational follow-up item 105 | Document Control | Finance Lead | Medium | In Progress | 2026-06-16 | 2026-06-29 |  | 50% | Management review | 28
ACT-106 | Procurement operational follow-up item 106 | Procurement | Document Controller | Medium | In Progress | 2026-05-04 | 2026-06-01 |  | 85% | Vendor follow-up | 56
ACT-107 | Project Administration operational follow-up item 107 | Project Administration | Site Administrator | Medium | In Progress | 2026-05-09 | 2026-06-07 |  | 50% | Commercial follow-up | 50
ACT-108 | Warehouse operational follow-up item 108 | Warehouse | Fleet Supervisor | Medium | On Hold | 2026-07-19 | 2026-08-06 |  | 10% | Internal coordination | 0
ACT-109 | Project Administration operational follow-up item 109 | Project Administration | Logistics Manager | Low | In Progress | 2026-05-11 | 2026-06-06 |  | 40% | Site action | 51
ACT-110 | Fleet & Transportation operational follow-up item 110 | Fleet & Transportation | Site Administrator | Medium | Open | 2026-06-24 | 2026-07-10 |  | 0% | Site action | 17
ACT-111 | Fleet & Transportation operational follow-up item 111 | Fleet & Transportation | Document Controller | Critical | Open | 2026-06-21 | 2026-06-30 |  | 10% | Vendor follow-up | 27
ACT-112 | Executive Office operational follow-up item 112 | Executive Office | Document Controller | Medium | Open | 2026-05-09 | 2026-05-19 |  | 10% | Commercial follow-up | 69
ACT-113 | Document Control operational follow-up item 113 | Document Control | Logistics Manager | Medium | Open | 2026-05-12 | 2026-06-02 |  | 10% | Management review | 55
ACT-114 | Fleet & Transportation operational follow-up item 114 | Fleet & Transportation | HR Manager | High | Open | 2026-07-05 | 2026-07-25 |  | 0% | Site action | 2
ACT-115 | Fleet & Transportation operational follow-up item 115 | Fleet & Transportation | Document Controller | Medium | In Progress | 2026-06-23 | 2026-07-08 |  | 50% | Site action | 19
ACT-116 | Fleet & Transportation operational follow-up item 116 | Fleet & Transportation | HR Manager | Critical | Completed | 2026-07-17 | 2026-07-20 | 2026-07-29 | 100% | Commercial follow-up | 0
ACT-117 | Executive Office operational follow-up item 117 | Executive Office | HR Manager | Low | Completed | 2026-06-22 | 2026-06-30 | 2026-07-08 | 100% | Vendor follow-up | 0
ACT-118 | Executive Office operational follow-up item 118 | Executive Office | Executive Office | High | On Hold | 2026-05-25 | 2026-06-19 |  | 10% | Site action | 38
ACT-119 | Construction operational follow-up item 119 | Construction | Logistics Manager | Medium | Open | 2026-07-07 | 2026-07-18 |  | 10% | Internal coordination | 9
ACT-120 | Human Resources operational follow-up item 120 | Human Resources | Finance Lead | High | Open | 2026-07-19 | 2026-08-18 |  | 30% | Commercial follow-up | 0

## Workforce & Attendance
WORKFORCE & ATTENDANCE MANAGEMENT REPORT
Synthetic monthly workforce sample ¦ Attendance • Worked hours • Absence • Late incidents • Overtime
Employee ID | Employee Name | Department | Site | Employment Status | Scheduled Hrs | Worked Hrs | Absent Days | Late Incidents | OT Hours | Attendance %
EMP0001 | Employee 001 | Construction | Base Camp | Active | 184 | 173 | 1.4 | 0 | 39.7 | 94.02%
EMP0002 | Employee 002 | Finance | Head Office | On Leave | 192 | 188 | 0.5 | 4 | 35.1 | 97.92%
EMP0003 | Employee 003 | Finance | Head Office | Active | 200 | 169 | 3.9 | 4 | 32.6 | 84.5%
EMP0004 | Employee 004 | Construction | Head Office | Active | 200 | 186 | 1.8 | 1 | 8.6 | 93%
EMP0005 | Employee 005 | Procurement | West Site | Active | 192 | 162 | 3.8 | 5 | 36.6 | 84.38%
EMP0006 | Employee 006 | Fleet & Transportation | Base Camp | Active | 192 | 173 | 2.4 | 2 | 4.9 | 90.1%
EMP0007 | Employee 007 | Logistics | East Site | Active | 200 | 191 | 1.1 | 4 | 21.9 | 95.5%
EMP0008 | Employee 008 | Fleet & Transportation | Warehouse | Active | 192 | 186 | 0.8 | 2 | 49.7 | 96.88%
EMP0009 | Employee 009 | Logistics | Base Camp | Active | 184 | 155 | 3.6 | 0 | 8.4 | 84.24%
EMP0010 | Employee 010 | Project Administration | Head Office | Active | 176 | 145 | 3.9 | 5 | 22.9 | 82.39%
EMP0011 | Employee 011 | Logistics | Base Camp | Active | 208 | 176 | 4 | 0 | 52.3 | 84.62%
EMP0012 | Employee 012 | Document Control | Base Camp | Active | 192 | 181 | 1.4 | 2 | 21.2 | 94.27%
EMP0013 | Employee 013 | Construction | East Site | Inactive | 176 | 168 | 1 | 4 | 36.1 | 95.45%
EMP0014 | Employee 014 | Document Control | Warehouse | On Leave | 208 | 197 | 1.4 | 1 | 45.3 | 94.71%
EMP0015 | Employee 015 | Project Administration | Segment Factory | Active | 192 | 182 | 1.2 | 5 | 15.6 | 94.79%
EMP0016 | Employee 016 | Human Resources | Segment Factory | Active | 208 | 192 | 2 | 2 | 0.8 | 92.31%
EMP0017 | Employee 017 | Fleet & Transportation | Warehouse | Active | 184 | 157 | 3.4 | 4 | 33 | 85.33%
EMP0018 | Employee 018 | Fleet & Transportation | Base Camp | Active | 184 | 180 | 0.5 | 0 | 27.3 | 97.83%
EMP0019 | Employee 019 | Project Administration | East Site | Active | 176 | 176 | 0 | 2 | 16.6 | 100%
EMP0020 | Employee 020 | Project Administration | East Site | Active | 192 | 170 | 2.8 | 0 | 24.3 | 88.54%
EMP0021 | Employee 021 | Fleet & Transportation | Segment Factory | Active | 176 | 176 | 0 | 3 | 12.3 | 100%
EMP0022 | Employee 022 | Construction | West Site | Active | 208 | 204 | 0.5 | 4 | 2.7 | 98.08%
EMP0023 | Employee 023 | Project Administration | Head Office | Active | 208 | 199 | 1.1 | 3 | 30.5 | 95.67%
EMP0024 | Employee 024 | Fleet & Transportation | Base Camp | Active | 208 | 176 | 4 | 0 | 36.5 | 84.62%
EMP0025 | Employee 025 | Project Administration | Segment Factory | Active | 208 | 188 | 2.5 | 1 | 22.1 | 90.38%
EMP0026 | Employee 026 | Logistics | Head Office | Active | 192 | 169 | 2.9 | 5 | 18.9 | 88.02%
EMP0027 | Employee 027 | Procurement | Segment Factory | On Leave | 200 | 179 | 2.6 | 5 | 9.1 | 89.5%
EMP0028 | Employee 028 | Fleet & Transportation | Warehouse | Active | 208 | 179 | 3.6 | 4 | 1.5 | 86.06%
EMP0029 | Employee 029 | Project Administration | Head Office | Active | 200 | 178 | 2.8 | 4 | 43.7 | 89%
EMP0030 | Employee 030 | Project Administration | Warehouse | Active | 208 | 204 | 0.5 | 3 | 30.9 | 98.08%
EMP0031 | Employee 031 | Document Control | Warehouse | Active | 208 | 191 | 2.1 | 2 | 4.7 | 91.83%
EMP0032 | Employee 032 | Fleet & Transportation | Head Office | Active | 192 | 165 | 3.4 | 1 | 25 | 85.94%
EMP0033 | Employee 033 | Project Administration | Head Office | Active | 176 | 156 | 2.5 | 5 | 34.4 | 88.64%
EMP0034 | Employee 034 | Procurement | East Site | Active | 208 | 201 | 0.9 | 2 | 48.2 | 96.63%
EMP0035 | Employee 035 | Human Resources | Head Office | Active | 208 | 203 | 0.6 | 4 | 42.5 | 97.6%
EMP0036 | Employee 036 | Document Control | Warehouse | Active | 192 | 163 | 3.6 | 0 | 22.3 | 84.9%
EMP0037 | Employee 037 | Logistics | Warehouse | Active | 208 | 177 | 3.9 | 3 | 28.9 | 85.1%
EMP0038 | Employee 038 | Finance | West Site | Active | 184 | 153 | 3.9 | 4 | 14 | 83.15%
EMP0039 | Employee 039 | Construction | Head Office | Active | 192 | 175 | 2.1 | 0 | 17.1 | 91.15%
EMP0040 | Employee 040 | Fleet & Transportation | West Site | Active | 176 | 165 | 1.4 | 4 | 14.8 | 93.75%
EMP0041 | Employee 041 | Logistics | West Site | Active | 192 | 170 | 2.8 | 1 | 1.3 | 88.54%
EMP0042 | Employee 042 | Logistics | Head Office | On Leave | 184 | 156 | 3.5 | 0 | 9.9 | 84.78%
EMP0043 | Employee 043 | Construction | Base Camp | Inactive | 192 | 164 | 3.5 | 3 | 15.3 | 85.42%
EMP0044 | Employee 044 | Human Resources | Segment Factory | Active | 200 | 169 | 3.9 | 5 | 29.3 | 84.5%
EMP0045 | Employee 045 | Construction | Segment Factory | Active | 184 | 167 | 2.1 | 3 | 54.1 | 90.76%
EMP0046 | Employee 046 | Logistics | Warehouse | Active | 176 | 165 | 1.4 | 4 | 29.3 | 93.75%
EMP0047 | Employee 047 | Procurement | West Site | Inactive | 176 | 160 | 2 | 0 | 26.4 | 90.91%
EMP0048 | Employee 048 | Construction | West Site | Active | 192 | 168 | 3 | 1 | 27.7 | 87.5%
EMP0049 | Employee 049 | Logistics | Base Camp | Active | 208 | 177 | 3.9 | 5 | 20.1 | 85.1%
EMP0050 | Employee 050 | Document Control | East Site | Active | 200 | 176 | 3 | 1 | 20.2 | 88%
EMP0051 | Employee 051 | Procurement | Warehouse | Active | 184 | 154 | 3.8 | 4 | 13.5 | 83.7%
EMP0052 | Employee 052 | Procurement | Head Office | Active | 184 | 179 | 0.6 | 2 | 29.9 | 97.28%
EMP0053 | Employee 053 | Human Resources | Base Camp | Active | 184 | 157 | 3.4 | 4 | 47.9 | 85.33%
EMP0054 | Employee 054 | Project Administration | East Site | Active | 200 | 198 | 0.2 | 2 | 4.5 | 99%
EMP0055 | Employee 055 | Logistics | West Site | Active | 192 | 190 | 0.2 | 4 | 9.8 | 98.96%
EMP0056 | Employee 056 | Human Resources | Head Office | Active | 176 | 153 | 2.9 | 5 | 11.1 | 86.93%
EMP0057 | Employee 057 | Construction | Base Camp | Active | 176 | 171 | 0.6 | 2 | 23.5 | 97.16%
EMP0058 | Employee 058 | Finance | Warehouse | Active | 184 | 173 | 1.4 | 3 | 24.7 | 94.02%
EMP0059 | Employee 059 | Logistics | East Site | Active | 192 | 185 | 0.9 | 5 | 53.2 | 96.35%
EMP0060 | Employee 060 | Fleet & Transportation | Warehouse | Active | 200 | 168 | 4 | 3 | 15.3 | 84%
EMP0061 | Employee 061 | Fleet & Transportation | Warehouse | On Leave | 192 | 192 | 0 | 5 | 24.2 | 100%
EMP0062 | Employee 062 | Executive Office | Segment Factory | Active | 200 | 176 | 3 | 5 | 2.7 | 88%
EMP0063 | Employee 063 | Finance | East Site | Active | 192 | 161 | 3.9 | 2 | 32.1 | 83.85%
EMP0064 | Employee 064 | Fleet & Transportation | Base Camp | Active | 208 | 190 | 2.2 | 5 | 11.1 | 91.35%
EMP0065 | Employee 065 | Warehouse | Warehouse | Active | 192 | 184 | 1 | 2 | 15.7 | 95.83%
EMP0066 | Employee 066 | Finance | Segment Factory | Active | 208 | 191 | 2.1 | 1 | 14.2 | 91.83%
EMP0067 | Employee 067 | Construction | West Site | Active | 200 | 198 | 0.2 | 0 | 19.8 | 99%
EMP0068 | Employee 068 | Executive Office | Head Office | Inactive | 176 | 170 | 0.8 | 1 | 33.6 | 96.59%
EMP0069 | Employee 069 | Logistics | West Site | Active | 184 | 154 | 3.8 | 2 | 45.5 | 83.7%
EMP0070 | Employee 070 | Project Administration | East Site | Active | 176 | 155 | 2.6 | 5 | 5.9 | 88.07%
EMP0071 | Employee 071 | Construction | Head Office | Inactive | 184 | 172 | 1.5 | 1 | 8.2 | 93.48%
EMP0072 | Employee 072 | Procurement | Segment Factory | On Leave | 200 | 200 | 0 | 3 | 37.6 | 100%
EMP0073 | Employee 073 | Project Administration | Base Camp | Active | 176 | 149 | 3.4 | 0 | 42.4 | 84.66%
EMP0074 | Employee 074 | Construction | West Site | Active | 192 | 177 | 1.9 | 2 | 18.4 | 92.19%
EMP0075 | Employee 075 | Construction | Base Camp | Active | 176 | 156 | 2.5 | 2 | 44.1 | 88.64%
EMP0076 | Employee 076 | Document Control | Segment Factory | Active | 200 | 199 | 0.1 | 0 | 5.9 | 99.5%
EMP0077 | Employee 077 | Fleet & Transportation | East Site | Active | 184 | 170 | 1.8 | 4 | 26.6 | 92.39%
EMP0078 | Employee 078 | Warehouse | East Site | Active | 192 | 171 | 2.6 | 5 | 26.2 | 89.06%
EMP0079 | Employee 079 | Warehouse | Base Camp | Active | 184 | 170 | 1.8 | 2 | 39.3 | 92.39%
EMP0080 | Employee 080 | Document Control | Head Office | Active | 200 | 197 | 0.4 | 3 | 46.9 | 98.5%
EMP0081 | Employee 081 | Project Administration | East Site | Active | 200 | 183 | 2.1 | 4 | 22.5 | 91.5%
EMP0082 | Employee 082 | Construction | Base Camp | Active | 176 | 162 | 1.8 | 2 | 25.6 | 92.05%
EMP0083 | Employee 083 | Project Administration | Base Camp | Inactive | 184 | 173 | 1.4 | 3 | 6.4 | 94.02%
EMP0084 | Employee 084 | Construction | East Site | Active | 176 | 176 | 0 | 0 | 22 | 100%
EMP0085 | Employee 085 | Finance | Base Camp | On Leave | 176 | 166 | 1.2 | 5 | 44.8 | 94.32%
EMP0086 | Employee 086 | Warehouse | Head Office | Active | 208 | 201 | 0.9 | 0 | 8.7 | 96.63%
EMP0087 | Employee 087 | Warehouse | West Site | Active | 184 | 171 | 1.6 | 1 | 31.3 | 92.93%
EMP0088 | Employee 088 | Fleet & Transportation | Head Office | Active | 200 | 182 | 2.2 | 5 | 2.7 | 91%
EMP0089 | Employee 089 | Document Control | Segment Factory | Active | 192 | 168 | 3 | 5 | 41.4 | 87.5%
EMP0090 | Employee 090 | Document Control | Warehouse | On Leave | 208 | 181 | 3.4 | 2 | 54.4 | 87.02%
EMP0091 | Employee 091 | Warehouse | Segment Factory | On Leave | 208 | 205 | 0.4 | 3 | 39.9 | 98.56%
EMP0092 | Employee 092 | Construction | Warehouse | Active | 208 | 198 | 1.2 | 0 | 47.2 | 95.19%
EMP0093 | Employee 093 | Construction | Warehouse | Active | 208 | 183 | 3.1 | 3 | 2.2 | 87.98%
EMP0094 | Employee 094 | Finance | Segment Factory | Active | 208 | 197 | 1.4 | 2 | 53.9 | 94.71%
EMP0095 | Employee 095 | Construction | Warehouse | Inactive | 192 | 185 | 0.9 | 5 | 8.2 | 96.35%
EMP0096 | Employee 096 | Finance | Head Office | Active | 200 | 168 | 4 | 5 | 19.9 | 84%
EMP0097 | Employee 097 | Construction | Warehouse | Active | 184 | 170 | 1.8 | 4 | 20.5 | 92.39%
EMP0098 | Employee 098 | Human Resources | Base Camp | On Leave | 208 | 177 | 3.9 | 1 | 40.8 | 85.1%
EMP0099 | Employee 099 | Construction | Head Office | Active | 200 | 194 | 0.8 | 0 | 6.5 | 97%
EMP0100 | Employee 100 | Human Resources | Head Office | Inactive | 184 | 159 | 3.1 | 3 | 31.3 | 86.41%
EMP0101 | Employee 101 | Logistics | Head Office | Active | 184 | 179 | 0.6 | 2 | 29.1 | 97.28%
EMP0102 | Employee 102 | Construction | Warehouse | Active | 208 | 176 | 4 | 2 | 41.9 | 84.62%
EMP0103 | Employee 103 | Human Resources | Warehouse | Active | 192 | 183 | 1.1 | 2 | 33.8 | 95.31%
EMP0104 | Employee 104 | Construction | West Site | Active | 208 | 177 | 3.9 | 1 | 15 | 85.1%
EMP0105 | Employee 105 | Logistics | East Site | Active | 176 | 144 | 4 | 2 | 54.3 | 81.82%
EMP0106 | Employee 106 | Project Administration | Head Office | Active | 208 | 194 | 1.8 | 1 | 18.3 | 93.27%
EMP0107 | Employee 107 | Executive Office | Base Camp | Active | 200 | 172 | 3.5 | 2 | 15.4 | 86%
EMP0108 | Employee 108 | Construction | West Site | Active | 176 | 148 | 3.5 | 1 | 38.5 | 84.09%
EMP0109 | Employee 109 | Construction | Head Office | Inactive | 208 | 206 | 0.2 | 2 | 27 | 99.04%
EMP0110 | Employee 110 | Human Resources | Segment Factory | Inactive | 176 | 156 | 2.5 | 5 | 31.3 | 88.64%
EMP0111 | Employee 111 | Human Resources | Head Office | Active | 200 | 198 | 0.2 | 4 | 36.9 | 99%
EMP0112 | Employee 112 | Construction | Segment Factory | Inactive | 208 | 177 | 3.9 | 2 | 24.6 | 85.1%
EMP0113 | Employee 113 | Project Administration | Warehouse | On Leave | 200 | 188 | 1.5 | 3 | 52.2 | 94%
EMP0114 | Employee 114 | Warehouse | West Site | Active | 200 | 196 | 0.5 | 0 | 44.5 | 98%
EMP0115 | Employee 115 | Warehouse | East Site | Active | 176 | 157 | 2.4 | 2 | 46.9 | 89.2%
EMP0116 | Employee 116 | Fleet & Transportation | Warehouse | On Leave | 208 | 199 | 1.1 | 0 | 10.1 | 95.67%
EMP0117 | Employee 117 | Fleet & Transportation | Warehouse | Active | 184 | 174 | 1.2 | 1 | 10 | 94.57%
EMP0118 | Employee 118 | Construction | Head Office | Active | 184 | 173 | 1.4 | 5 | 7.1 | 94.02%
EMP0119 | Employee 119 | Logistics | Head Office | Active | 200 | 200 | 0 | 5 | 9.3 | 100%
EMP0120 | Employee 120 | Construction | Segment Factory | Active | 200 | 173 | 3.4 | 4 | 35.8 | 86.5%
EMP0121 | Employee 121 | Executive Office | West Site | Active | 176 | 155 | 2.6 | 4 | 26.5 | 88.07%
EMP0122 | Employee 122 | Fleet & Transportation | West Site | Active | 208 | 177 | 3.9 | 2 | 25 | 85.1%
EMP0123 | Employee 123 | Project Administration | Segment Factory | Active | 184 | 169 | 1.9 | 3 | 50.5 | 91.85%
EMP0124 | Employee 124 | Warehouse | Segment Factory | Active | 208 | 198 | 1.2 | 1 | 3.6 | 95.19%
EMP0125 | Employee 125 | Construction | East Site | Active | 200 | 197 | 0.4 | 3 | 15.8 | 98.5%
EMP0126 | Employee 126 | Project Administration | Warehouse | Active | 176 | 160 | 2 | 5 | 7.5 | 90.91%
EMP0127 | Employee 127 | Logistics | Head Office | Active | 176 | 163 | 1.6 | 3 | 4.9 | 92.61%
EMP0128 | Employee 128 | Construction | West Site | Active | 184 | 174 | 1.2 | 1 | 25 | 94.57%
EMP0129 | Employee 129 | Project Administration | West Site | Active | 208 | 206 | 0.2 | 1 | 36.7 | 99.04%
EMP0130 | Employee 130 | Document Control | Base Camp | Active | 192 | 179 | 1.6 | 5 | 7.3 | 93.23%
EMP0131 | Employee 131 | Fleet & Transportation | Base Camp | Active | 192 | 173 | 2.4 | 3 | 40.9 | 90.1%
EMP0132 | Employee 132 | Finance | Segment Factory | Active | 184 | 157 | 3.4 | 0 | 4.6 | 85.33%
EMP0133 | Employee 133 | Logistics | Warehouse | Active | 184 | 166 | 2.2 | 1 | 32 | 90.22%
EMP0134 | Employee 134 | Construction | Warehouse | Active | 176 | 144 | 4 | 4 | 52.5 | 81.82%
EMP0135 | Employee 135 | Construction | Base Camp | Active | 208 | 195 | 1.6 | 2 | 0.8 | 93.75%
EMP0136 | Employee 136 | Warehouse | Segment Factory | Active | 200 | 183 | 2.1 | 4 | 18.8 | 91.5%
EMP0137 | Employee 137 | Human Resources | Warehouse | Active | 192 | 190 | 0.2 | 1 | 15.2 | 98.96%
EMP0138 | Employee 138 | Document Control | East Site | Active | 200 | 184 | 2 | 4 | 15 | 92%
EMP0139 | Employee 139 | Logistics | Segment Factory | Active | 192 | 167 | 3.1 | 5 | 27 | 86.98%
EMP0140 | Employee 140 | Warehouse | Head Office | Active | 192 | 171 | 2.6 | 4 | 27.2 | 89.06%
EMP0141 | Employee 141 | Construction | Base Camp | Active | 176 | 158 | 2.2 | 2 | 24.7 | 89.77%
EMP0142 | Employee 142 | Warehouse | Base Camp | Active | 192 | 166 | 3.2 | 3 | 23.5 | 86.46%
EMP0143 | Employee 143 | Procurement | Head Office | Active | 184 | 166 | 2.2 | 4 | 27.3 | 90.22%
EMP0144 | Employee 144 | Human Resources | East Site | Active | 192 | 184 | 1 | 4 | 2.5 | 95.83%
EMP0145 | Employee 145 | Logistics | West Site | Active | 176 | 157 | 2.4 | 4 | 3.5 | 89.2%
EMP0146 | Employee 146 | Construction | Head Office | Active | 176 | 155 | 2.6 | 4 | 29.1 | 88.07%
EMP0147 | Employee 147 | Logistics | Head Office | Active | 176 | 145 | 3.9 | 3 | 53.3 | 82.39%
EMP0148 | Employee 148 | Project Administration | Warehouse | Active | 200 | 195 | 0.6 | 4 | 45.2 | 97.5%
EMP0149 | Employee 149 | Fleet & Transportation | East Site | On Leave | 192 | 161 | 3.9 | 1 | 51.4 | 83.85%
EMP0150 | Employee 150 | Project Administration | Base Camp | Active | 184 | 156 | 3.5 | 0 | 48 | 84.78%

## Procurement & Payment
PROCUREMENT, PO & PAYMENT CONTROL TRACKER
Management control ¦ PR • PO • Invoice • Payment • Outstanding commitments
PR No. | PO No. | Department | Vendor | Description | Commitment SAR | Status | PR Date | PO Date | Invoice Date | Paid Date | Paid SAR | Outstanding SAR
PR-0001 |  | Executive Office | Vendor Delta | Operational procurement package 001 | 141964.29 | On Hold | 2026-06-24 |  |  |  | 0 | 141964.29
PR-0002 |  | Logistics | Vendor Eta | Operational procurement package 002 | 564460.25 | On Hold | 2026-04-26 |  |  |  | 0 | 564460.25
PR-0003 | PO-7003 | Executive Office | Vendor Epsilon | Operational procurement package 003 | 149532.02 | PO Issued | 2026-04-22 | 2026-04-26 |  |  | 0 | 149532.02
PR-0004 | PO-7004 | Executive Office | Vendor Zeta | Operational procurement package 004 | 395158.54 | PO Issued | 2026-02-11 | 2026-02-22 |  |  | 0 | 395158.54
PR-0005 | PO-7005 | Fleet & Transportation | Vendor Gamma | Operational procurement package 005 | 598358.52 | Paid | 2026-05-04 | 2026-05-11 | 2026-06-05 | 2026-06-15 | 598358.52 | 0
PR-0006 | PO-7006 | Finance | Vendor Eta | Operational procurement package 006 | 403777.49 | Received | 2026-02-01 | 2026-02-06 |  |  | 0 | 403777.49
PR-0007 | PO-7007 | Fleet & Transportation | Vendor Beta | Operational procurement package 007 | 256375.58 | Invoiced | 2026-05-11 | 2026-05-21 | 2026-06-15 |  | 142005.26 | 114370.32
PR-0008 | PO-7008 | Human Resources | Vendor Alpha | Operational procurement package 008 | 482653.13 | Paid | 2026-07-03 | 2026-07-13 | 2026-07-29 | 2026-08-16 | 482653.13 | 0
PR-0009 |  | Logistics | Vendor Eta | Operational procurement package 009 | 640518.2 | On Hold | 2026-04-26 |  |  |  | 0 | 640518.2
PR-0010 |  | Fleet & Transportation | Vendor Eta | Operational procurement package 010 | 326916.49 | PR Raised | 2026-02-11 |  |  |  | 0 | 326916.49
PR-0011 | PO-7011 | Document Control | Vendor Alpha | Operational procurement package 011 | 306697.8 | Received | 2026-02-06 | 2026-02-13 |  |  | 0 | 306697.8
PR-0012 |  | Fleet & Transportation | Vendor Delta | Operational procurement package 012 | 91336.83 | PR Raised | 2026-03-05 |  |  |  | 0 | 91336.83
PR-0013 | PO-7013 | Project Administration | Vendor Beta | Operational procurement package 013 | 312793.35 | Paid | 2026-03-05 | 2026-03-16 | 2026-04-18 | 2026-05-05 | 312793.35 | 0
PR-0014 | PO-7014 | Project Administration | Vendor Zeta | Operational procurement package 014 | 507441.86 | Invoiced | 2026-02-13 | 2026-02-16 | 2026-03-20 |  | 275972.06 | 231469.8
PR-0015 | PO-7015 | Finance | Vendor Eta | Operational procurement package 015 | 69193.46 | Paid | 2026-03-25 | 2026-03-27 | 2026-04-08 | 2026-05-01 | 69193.46 | 0
PR-0016 | PO-7016 | Procurement | Vendor Epsilon | Operational procurement package 016 | 271872.09 | Paid | 2026-04-22 | 2026-04-26 | 2026-06-02 | 2026-06-23 | 271872.09 | 0
PR-0017 | PO-7017 | Logistics | Vendor Eta | Operational procurement package 017 | 415022.63 | Paid | 2026-07-01 | 2026-07-08 | 2026-08-18 | 2026-08-27 | 415022.63 | 0
PR-0018 | PO-7018 | Warehouse | Vendor Eta | Operational procurement package 018 | 351492.31 | Invoiced | 2026-03-04 | 2026-03-16 | 2026-04-10 |  | 121674.06 | 229818.25
PR-0019 | PO-7019 | Finance | Vendor Beta | Operational procurement package 019 | 405431.32 | Paid | 2026-05-17 | 2026-06-04 | 2026-07-15 | 2026-08-12 | 405431.32 | 0
PR-0020 | PO-7020 | Finance | Vendor Eta | Operational procurement package 020 | 323075.97 | PO Issued | 2026-01-16 | 2026-01-30 |  |  | 0 | 323075.97
PR-0021 | PO-7021 | Document Control | Vendor Gamma | Operational procurement package 021 | 72136.89 | Paid | 2026-01-11 | 2026-01-23 | 2026-02-13 | 2026-03-06 | 72136.89 | 0
PR-0022 | PO-7022 | Document Control | Vendor Beta | Operational procurement package 022 | 104602.42 | PO Issued | 2026-05-31 | 2026-06-05 |  |  | 0 | 104602.42
PR-0023 | PO-7023 | Finance | Vendor Delta | Operational procurement package 023 | 598621.97 | Paid | 2026-01-10 | 2026-01-21 | 2026-02-26 | 2026-03-14 | 598621.97 | 0
PR-0024 | PO-7024 | Warehouse | Vendor Delta | Operational procurement package 024 | 376980.41 | Invoiced | 2026-06-24 | 2026-07-08 | 2026-07-26 |  | 289852.31 | 87128.1
PR-0025 | PO-7025 | Human Resources | Vendor Theta | Operational procurement package 025 | 176737.36 | Invoiced | 2026-05-26 | 2026-06-07 | 2026-06-22 |  | 42761.35 | 133976.01
PR-0026 | PO-7026 | Warehouse | Vendor Beta | Operational procurement package 026 | 123764.12 | Invoiced | 2026-06-25 | 2026-07-12 | 2026-08-08 |  | 33105.24 | 90658.88
PR-0027 | PO-7027 | Finance | Vendor Alpha | Operational procurement package 027 | 615602.92 | Received | 2026-05-10 | 2026-05-13 |  |  | 0 | 615602.92
PR-0028 | PO-7028 | Procurement | Vendor Gamma | Operational procurement package 028 | 355594.29 | Invoiced | 2026-04-10 | 2026-04-28 | 2026-05-14 |  | 113778.93 | 241815.36
PR-0029 | PO-7029 | Executive Office | Vendor Gamma | Operational procurement package 029 | 194365.43 | Paid | 2026-02-18 | 2026-02-27 | 2026-04-08 | 2026-04-29 | 194365.43 | 0
PR-0030 | PO-7030 | Fleet & Transportation | Vendor Theta | Operational procurement package 030 | 273201.62 | Received | 2026-02-12 | 2026-02-28 |  |  | 0 | 273201.62
PR-0031 |  | Construction | Vendor Alpha | Operational procurement package 031 | 278671.92 | PR Raised | 2026-05-13 |  |  |  | 0 | 278671.92
PR-0032 | PO-7032 | Logistics | Vendor Theta | Operational procurement package 032 | 309088.39 | Paid | 2026-05-25 | 2026-06-09 | 2026-07-18 | 2026-08-16 | 309088.39 | 0
PR-0033 |  | Document Control | Vendor Beta | Operational procurement package 033 | 163294.37 | PR Raised | 2026-04-03 |  |  |  | 0 | 163294.37
PR-0034 | PO-7034 | Procurement | Vendor Gamma | Operational procurement package 034 | 346757.79 | Invoiced | 2026-04-02 | 2026-04-08 | 2026-04-21 |  | 177339.57 | 169418.22
PR-0035 |  | Logistics | Vendor Delta | Operational procurement package 035 | 110075.5 | On Hold | 2026-05-20 |  |  |  | 0 | 110075.5
PR-0036 |  | Executive Office | Vendor Theta | Operational procurement package 036 | 577770.72 | PR Raised | 2026-06-27 |  |  |  | 0 | 577770.72
PR-0037 | PO-7037 | Logistics | Vendor Theta | Operational procurement package 037 | 326803.34 | PO Issued | 2026-06-22 | 2026-07-01 |  |  | 0 | 326803.34
PR-0038 |  | Executive Office | Vendor Epsilon | Operational procurement package 038 | 414282.82 | On Hold | 2026-04-17 |  |  |  | 0 | 414282.82
PR-0039 | PO-7039 | Finance | Vendor Epsilon | Operational procurement package 039 | 515179.41 | Invoiced | 2026-05-23 | 2026-06-02 | 2026-06-19 |  | 153836.7 | 361342.71
PR-0040 | PO-7040 | Finance | Vendor Delta | Operational procurement package 040 | 463864.67 | Invoiced | 2026-03-26 | 2026-03-29 | 2026-04-20 |  | 135474.11 | 328390.56
PR-0041 | PO-7041 | Executive Office | Vendor Epsilon | Operational procurement package 041 | 468770.74 | Invoiced | 2026-04-30 | 2026-05-15 | 2026-05-25 |  | 258696.76 | 210073.98
PR-0042 |  | Human Resources | Vendor Epsilon | Operational procurement package 042 | 297054.22 | PR Raised | 2026-05-22 |  |  |  | 0 | 297054.22
PR-0043 | PO-7043 | Procurement | Vendor Eta | Operational procurement package 043 | 117210.94 | PO Issued | 2026-01-03 | 2026-01-09 |  |  | 0 | 117210.94
PR-0044 | PO-7044 | Logistics | Vendor Beta | Operational procurement package 044 | 588653.7 | Received | 2026-03-01 | 2026-03-19 |  |  | 0 | 588653.7
PR-0045 |  | Document Control | Vendor Eta | Operational procurement package 045 | 134670.44 | PR Raised | 2026-02-18 |  |  |  | 0 | 134670.44
PR-0046 | PO-7046 | Document Control | Vendor Zeta | Operational procurement package 046 | 24377.1 | Paid | 2026-01-13 | 2026-01-25 | 2026-02-13 | 2026-02-28 | 24377.1 | 0
PR-0047 | PO-7047 | Human Resources | Vendor Eta | Operational procurement package 047 | 138847.96 | Received | 2026-07-08 | 2026-07-18 |  |  | 0 | 138847.96
PR-0048 | PO-7048 | Logistics | Vendor Alpha | Operational procurement package 048 | 178954.81 | Paid | 2026-05-14 | 2026-05-23 | 2026-06-09 | 2026-06-20 | 178954.81 | 0
PR-0049 | PO-7049 | Human Resources | Vendor Zeta | Operational procurement package 049 | 501088.67 | Received | 2026-06-01 | 2026-06-10 |  |  | 0 | 501088.67
PR-0050 | PO-7050 | Warehouse | Vendor Delta | Operational procurement package 050 | 649734.06 | PO Issued | 2026-01-22 | 2026-02-09 |  |  | 0 | 649734.06
PR-0051 | PO-7051 | Project Administration | Vendor Zeta | Operational procurement package 051 | 91314.2 | PO Issued | 2026-01-14 | 2026-01-22 |  |  | 0 | 91314.2
PR-0052 |  | Construction | Vendor Theta | Operational procurement package 052 | 575313.45 | On Hold | 2026-06-19 |  |  |  | 0 | 575313.45
PR-0053 | PO-7053 | Construction | Vendor Gamma | Operational procurement package 053 | 339259.29 | Received | 2026-01-02 | 2026-01-11 |  |  | 0 | 339259.29
PR-0054 | PO-7054 | Project Administration | Vendor Eta | Operational procurement package 054 | 540842.76 | PO Issued | 2026-06-25 | 2026-07-05 |  |  | 0 | 540842.76
PR-0055 | PO-7055 | Executive Office | Vendor Alpha | Operational procurement package 055 | 320635.96 | PO Issued | 2026-06-10 | 2026-06-20 |  |  | 0 | 320635.96
PR-0056 | PO-7056 | Document Control | Vendor Zeta | Operational procurement package 056 | 171071.04 | Invoiced | 2026-05-20 | 2026-06-06 | 2026-06-23 |  | 93523.12 | 77547.92
PR-0057 | PO-7057 | Document Control | Vendor Eta | Operational procurement package 057 | 311425.61 | Paid | 2026-02-11 | 2026-02-25 | 2026-03-20 | 2026-04-14 | 311425.61 | 0
PR-0058 | PO-7058 | Executive Office | Vendor Theta | Operational procurement package 058 | 274624.26 | Invoiced | 2026-05-27 | 2026-06-10 | 2026-07-02 |  | 177997.97 | 96626.29
PR-0059 | PO-7059 | Project Administration | Vendor Zeta | Operational procurement package 059 | 587577.54 | Received | 2026-01-06 | 2026-01-22 |  |  | 0 | 587577.54
PR-0060 | PO-7060 | Project Administration | Vendor Epsilon | Operational procurement package 060 | 229961.45 | PO Issued | 2026-04-25 | 2026-04-28 |  |  | 0 | 229961.45
PR-0061 | PO-7061 | Warehouse | Vendor Epsilon | Operational procurement package 061 | 177194.21 | Invoiced | 2026-02-16 | 2026-02-23 | 2026-03-16 |  | 79292.64 | 97901.57
PR-0062 | PO-7062 | Finance | Vendor Theta | Operational procurement package 062 | 61374.86 | PO Issued | 2026-04-26 | 2026-05-11 |  |  | 0 | 61374.86
PR-0063 | PO-7063 | Finance | Vendor Beta | Operational procurement package 063 | 532527.65 | PO Issued | 2026-07-08 | 2026-07-14 |  |  | 0 | 532527.65
PR-0064 |  | Fleet & Transportation | Vendor Gamma | Operational procurement package 064 | 581086.51 | PR Raised | 2026-05-26 |  |  |  | 0 | 581086.51
PR-0065 | PO-7065 | Logistics | Vendor Gamma | Operational procurement package 065 | 486414.13 | PO Issued | 2026-04-09 | 2026-04-23 |  |  | 0 | 486414.13
PR-0066 | PO-7066 | Warehouse | Vendor Alpha | Operational procurement package 066 | 339221.81 | Received | 2026-06-01 | 2026-06-11 |  |  | 0 | 339221.81
PR-0067 | PO-7067 | Procurement | Vendor Alpha | Operational procurement package 067 | 336493.47 | Invoiced | 2026-04-05 | 2026-04-12 | 2026-05-11 |  | 253405.12 | 83088.35
PR-0068 | PO-7068 | Construction | Vendor Zeta | Operational procurement package 068 | 297993.61 | Invoiced | 2026-06-23 | 2026-07-10 | 2026-07-28 |  | 66024.92 | 231968.69
PR-0069 | PO-7069 | Human Resources | Vendor Delta | Operational procurement package 069 | 301399.15 | Received | 2026-04-29 | 2026-05-17 |  |  | 0 | 301399.15
PR-0070 | PO-7070 | Human Resources | Vendor Zeta | Operational procurement package 070 | 569030.92 | Paid | 2026-01-26 | 2026-02-05 | 2026-02-19 | 2026-03-14 | 569030.92 | 0
PR-0071 | PO-7071 | Human Resources | Vendor Epsilon | Operational procurement package 071 | 631981.44 | Invoiced | 2026-01-24 | 2026-01-28 | 2026-03-02 |  | 172726.63 | 459254.81
PR-0072 |  | Project Administration | Vendor Delta | Operational procurement package 072 | 364637.52 | PR Raised | 2026-01-13 |  |  |  | 0 | 364637.52
PR-0073 | PO-7073 | Human Resources | Vendor Beta | Operational procurement package 073 | 266983.9 | PO Issued | 2026-01-16 | 2026-01-24 |  |  | 0 | 266983.9
PR-0074 | PO-7074 | Logistics | Vendor Beta | Operational procurement package 074 | 504900.74 | Paid | 2026-01-01 | 2026-01-13 | 2026-02-21 | 2026-03-08 | 504900.74 | 0
PR-0075 | PO-7075 | Warehouse | Vendor Alpha | Operational procurement package 075 | 116572.97 | Paid | 2026-02-10 | 2026-02-12 | 2026-03-03 | 2026-03-18 | 116572.97 | 0
PR-0076 | PO-7076 | Logistics | Vendor Theta | Operational procurement package 076 | 273724.12 | Paid | 2026-05-06 | 2026-05-14 | 2026-06-02 | 2026-06-16 | 273724.12 | 0
PR-0077 | PO-7077 | Executive Office | Vendor Delta | Operational procurement package 077 | 20134.8 | Paid | 2026-02-06 | 2026-02-11 | 2026-03-27 | 2026-04-25 | 20134.8 | 0
PR-0078 |  | Procurement | Vendor Zeta | Operational procurement package 078 | 511423.79 | PR Raised | 2026-06-01 |  |  |  | 0 | 511423.79
PR-0079 | PO-7079 | Fleet & Transportation | Vendor Zeta | Operational procurement package 079 | 333511.87 | Paid | 2026-06-01 | 2026-06-11 | 2026-07-05 | 2026-07-31 | 333511.87 | 0
PR-0080 | PO-7080 | Executive Office | Vendor Eta | Operational procurement package 080 | 317734.39 | PO Issued | 2026-01-14 | 2026-01-24 |  |  | 0 | 317734.39
PR-0081 |  | Finance | Vendor Alpha | Operational procurement package 081 | 341515.63 | On Hold | 2026-02-19 |  |  |  | 0 | 341515.63
PR-0082 | PO-7082 | Project Administration | Vendor Delta | Operational procurement package 082 | 605102.27 | Invoiced | 2026-04-25 | 2026-05-02 | 2026-05-25 |  | 208053.11 | 397049.16
PR-0083 | PO-7083 | Warehouse | Vendor Theta | Operational procurement package 083 | 247862.52 | PO Issued | 2026-05-01 | 2026-05-14 |  |  | 0 | 247862.52
PR-0084 |  | Fleet & Transportation | Vendor Gamma | Operational procurement package 084 | 520695.49 | On Hold | 2026-05-04 |  |  |  | 0 | 520695.49
PR-0085 | PO-7085 | Document Control | Vendor Eta | Operational procurement package 085 | 426213.74 | PO Issued | 2026-03-15 | 2026-03-31 |  |  | 0 | 426213.74
PR-0086 |  | Finance | Vendor Beta | Operational procurement package 086 | 292625.52 | On Hold | 2026-04-10 |  |  |  | 0 | 292625.52
PR-0087 | PO-7087 | Executive Office | Vendor Beta | Operational procurement package 087 | 634970.6 | Paid | 2026-05-06 | 2026-05-16 | 2026-06-13 | 2026-06-28 | 634970.6 | 0
PR-0088 |  | Warehouse | Vendor Beta | Operational procurement package 088 | 381740.82 | On Hold | 2026-05-07 |  |  |  | 0 | 381740.82
PR-0089 | PO-7089 | Project Administration | Vendor Zeta | Operational procurement package 089 | 251552.71 | PO Issued | 2026-03-21 | 2026-03-27 |  |  | 0 | 251552.71
PR-0090 | PO-7090 | Finance | Vendor Delta | Operational procurement package 090 | 186030.65 | Paid | 2026-03-08 | 2026-03-20 | 2026-04-15 | 2026-04-25 | 186030.65 | 0

## KPI Scorecard
EXECUTIVE KPI SCORECARD
Target vs Actual ¦ Status • Variance • Management attention
KPI | Target | Actual | Variance | Achievement % | Direction | Status | Management Comment
Attendance Rate | 96% | 91.28% | -4.716% | 95.09% | Higher | Watch | Monitor closely
Active Workforce % | 90% | 84% | -6% | 93.33% | Higher | Watch | Monitor closely
Open Action Closure % | 80% | 38.33% | -41.67% | 47.92% | Higher | Critical | Management action required
Overdue Action Rate | 10% | 50.83% | 40.83% | 19.67% | Lower | Critical | Management action required
Procurement Paid % | 75% | 31.36% | -43.64% | 41.81% | Higher | Critical | Management action required
OT Exception Rate | 15% | 6.667% | -8.333% | 225% | Lower | On Track | Within target

## Lists
Departments | Owners | Priority | Action Status | Sites | Procurement Status
Construction | Project Manager | Critical | Open | Head Office | PR Raised
Logistics | Admin Manager | High | In Progress | Base Camp | PO Issued
Fleet & Transportation | Logistics Manager | Medium | Completed | West Site | Received
Project Administration | HR Manager | Low | On Hold | East Site | Invoiced
Warehouse | Procurement Lead |  |  | Warehouse | Paid
Procurement | Finance Lead |  |  | Segment Factory | On Hold
Document Control | Document Controller
Finance | Fleet Supervisor
Human Resources | Site Administrator
Executive Office | Executive Office